## Read Me
AmphenolCIT S/4HANA - Tech Debt & Innovation Planner
Companion to the strategy deck and quick reference guide. Draft v0.1 - Enterprise Architecture.
How to use
1. Settings | Set day rate, working days, availability and plan start date.
2. Tech Debt Register | Single backlog for ALL work types. Log every item with the quick reference guide fields. EX-### rows are illustrative - overwrite them.
3. Score | Business Value, Time Criticality, Risk Reduction/Opportunity Enablement and Job Size on 1-2-3-5-8-13-20. WSJF and rank calculate automatically. P1/P2 defects bypass ranking (expedite lane).
4. Capacity & Budget | Enter FTE and budget caps; set % allocation per work type per quarter. Compare guardrail capacity to live demand from the register.
5. Roadmap | Adjust start/end dates; Gantt bars redraw.
6. Sprint Tracker | Record planned vs done points per type each sprint to show real flow distribution.
7. KPI Dashboard | Live backlog counts and health signals; update 'Current' KPI values monthly for the portfolio review.
8. Cadence | The ceremonies that keep grooming and repetition going.
Colour legend
Yellow fill, blue text | Input - edit these
Grey fill | Formula - do not overwrite
Red highlight | Needs attention (stale item, P1/P2, over budget, allocation not 100%)
Definitions
Tech Debt | Something built or configured that works today but increases the cost or risk of future change (e.g. modifications, Z-fields holding standard data, P2P interfaces, missing tests).
Defect | Something that does not work as designed. Severity P1-P4.
Feature | New or improved business capability (e.g. a Fiori app, Work Zone site, new S/4 functionality).
Enabler | Platform / architecture work that makes features possible (e.g. Work Zone subaccount, Integration Suite landing zone, test automation).
Risk/Compliance | Security, audit, maintenance-deadline or licence-driven work.
Interest vs Principal | Interest = recurring cost of living with the debt (hrs/month). Principal = one-off cost to remove it. High interest + low principal = pay down first.

## KPI Dashboard
Visible Progress - KPI Dashboard
Backlog counts update live from the register. KPI baselines/targets are inputs to agree with leadership.
Backlog by type and status (live)
Item type | New | Triaged | Ready | In Progress | Testing | Done | Open total | Open effort (p-days) | Avg WSJF (open)
Feature | 3 | 0 | 1 | 0 | 0 | 0 | 4 | 50 | 5.125
Defect | 1 | 0 | 0 | 2 | 0 | 0 | 3 | 8 | 8.8333
Tech Debt | 2 | 4 | 1 | 0 | 0 | 0 | 7 | 188 | 3.2286
Enabler | 2 | 0 | 2 | 0 | 0 | 0 | 4 | 97 | 3.8
Risk/Compliance | 1 | 1 | 0 | 0 | 0 | 0 | 2 | 55 | 3.7
Total | 9 | 5 | 4 | 2 | 0 | 0 | 20 | 398
Health signals (live)
Stale items (New/Triaged > threshold) |  |  |  | 1
Open items blocking innovation |  |  |  | 10
Open Level C/D clean-core items |  |  |  | 5
Open P1/P2 defects |  |  |  | 1
Annual interest cost of open tech debt (USD) |  |  |  | 163125
Open tech debt principal (USD) |  |  |  | 141000
Outcome KPIs (agree baseline + targets; update 'Current' monthly)
KPI | Dimension | Unit | Baseline | Target Q2-2027 | Target Q4-2027 | Current | Direction | RAG | Source / tool
Share of active users launching Fiori apps monthly | UX | % | 0% | 40% | 75% |  | Up | Not measured
Fiori apps in productive use | UX | # | 0 | 40 | 120 |  | Up | Not measured
Users onboarded to Work Zone sites | UX | # | 0 | 150 | 600 |  | Up | Not measured
Interfaces on Integration Suite (of total) | Integration | % | 5% | 35% | 70% |  | Up | Not measured
Interface failures per month | Integration | # | 120 | 60 | 20 |  | Down | Not measured
Custom objects (Z) in use | Extensibility | # | 2500 | 2000 | 1600 |  | Down | Not measured
ATC clean-core findings Level C/D | Extensibility | # | 900 | 700 | 450 |  | Down | Not measured
Business-data custom fields mapped to standard or exposed | Data | % | 0% | 50% | 90% |  | Up | Not measured
Master data quality score (rule pass rate) | Data | % | 72% | 85% | 95% |  | Up | Not measured
Median lead time request -> production (days) | Operations | days | 45 | 30 | 20 |  | Down | Not measured
Tech debt share of delivered capacity | Operations | % | 5% | 25% | 20% |  | Hold | Not measured
Behind latest S/4 FPS / release (months) | Operations | months | 12 | 12 | 3 |  | Down | Not measured
Baselines/targets are illustrative placeholders; RAG compares Current to the Q2-2027 target (G = met, A = improving vs baseline, R = not improving).

## Tech Debt Register
Unified Backlog & Tech Debt Register
One backlog for Features, Defects, Tech Debt, Enablers and Risk/Compliance. Yellow = input; grey = calculated. Rows EX-### are ILLUSTRATIVE - overwrite with real items.
ID | Title | Item Type | Clean Core Dimension | Area / Module | Description / symptom | Root cause (Fowler quadrant) | Clean Core Level (A-D) | Blocks innovation? (Y/N) | Bug severity (P1-P4) | Business Value | Time Criticality | Risk Reduction / Opportunity Enablement | Job Size | WSJF score | Priority rank | Interest (hrs / month lost) | Principal (effort person-days) | Est. cost (USD) | Annual interest cost (USD) | Payback (months) | Business owner | IT owner | Status | Target quarter | Date raised | Date closed | Age (days) | Stale? | Notes / evidence link
EX-001 | Business data held in custom Z-fields on material master (MARA append) | Tech Debt | Data | MM | Z-fields not exposed via CDS/OData; standard Fiori apps, APIs and analytics cannot see the data. Users revert to SE16N/Excel. | Deliberate-Prudent | C | Y | n/a | 13 | 8 | 13 | 8 | 4.3 | 10 | 40 | 25 | 18750 | 45000 | 5 | Materials Mgmt lead | MM functional lead | Triaged | Q1-2027 | 2026-09-01 |  | 26 |  | Evidence: SE11 append ZAMARA; map each Z-field to standard field or Custom Fields app
EX-002 | Activate Fiori launchpad + role-based spaces for AP / AR clerks | Feature | UX | FI | Finance users on SAP GUI only; Manage Supplier Line Items, Clear GL Accounts etc. not in use. | n/a | A | N | n/a | 13 | 5 | 8 | 5 | 5.2 | 5 | 20 | 15 | 11250 | 22500 | 6 | Finance controller | Fiori/Basis lead | Ready | Q4-2026 | 2026-09-05 |  | 22 |  | Use Fiori Apps Library recommendations report from ST03N usage
EX-003 | SAP Build Work Zone (standard) subaccount, IdP and content federation | Enabler | UX | BTP | No central entry point; users bookmark GUI transactions and separate portals. | n/a | A | Y | n/a | 8 | 5 | 13 | 5 | 5.2 | 5 | 0 | 20 | 15000 | 0 |  | CIO office | BTP platform lead | Ready | Q4-2026 | 2026-09-05 |  | 22 |  | Prereq: SAP Cloud Identity Services, Cloud Connector, content provider from S/4 FLP
EX-004 | Point-to-point RFC / file interfaces to MES re-platformed to Integration Suite | Tech Debt | Integration | Integration | 12 custom RFC/file jobs, no monitoring, failures found by users. | Inadvertent-Prudent | B | Y | n/a | 8 | 5 | 13 | 13 | 2 | 18 | 30 | 60 | 45000 | 33750 | 16 | Plant ops director | Integration lead | New | Q2-2027 | 2026-09-10 |  | 17 |  | Run Integration Suite Migration Assessment + ISA-M classification
EX-005 | Intercompany STO pricing condition wrong for plant 2100 | Defect | Process | SD | Wrong transfer price on intercompany billing; manual correction each month-end. | Inadvertent-Reckless | n/a | N | P3 | 5 | 8 | 5 | 2 | 9 | 2 | 16 | 3 | 2250 | 18000 | 1.5 | Sales ops | SD functional lead | In Progress | Q4-2026 | 2026-08-20 |  | 38
EX-006 | Modifications in sales-order user exits (MV45AFZZ) refactored to released BAdIs | Tech Debt | Extensibility | SD | Implicit enhancements + modifications slow every upgrade and block clean core. | Deliberate-Reckless | D | Y | n/a | 5 | 3 | 13 | 8 | 2.6 | 15 | 12 | 30 | 22500 | 13500 | 20 | Sales ops | ABAP dev lead | Triaged | Q2-2027 | 2026-09-12 |  | 15 |  | ATC clean-core check variant findings
EX-007 | Decommission unused custom code (no usage in 12 months) | Tech Debt | Extensibility | Cross-app | Approx. 30% of Z-objects show no execution in SCMON/SUSG data. | Inadvertent-Prudent | C | N | n/a | 3 | 2 | 8 | 3 | 4.3 | 10 | 8 | 10 | 7500 | 9000 | 10 | CIO office | ABAP dev lead | Triaged | Q1-2027 | 2026-09-12 |  | 15 |  | Custom Code Migration app scoping; retire before remediate
EX-008 | Adopt Monitor Material Coverage / MRP Live Fiori apps for planners | Feature | Process | PP | Planners use MD04 + Excel; exception-based planning not used. | n/a | A | N | n/a | 13 | 5 | 5 | 5 | 4.6 | 9 | 25 | 15 | 11250 | 28125 | 4.8 | Supply chain VP | PP functional lead | New | Q1-2027 | 2026-09-15 |  | 12
EX-009 | S/4HANA Feature Pack / release currency plan | Risk/Compliance | Operations | Basis | System behind latest FPS; missing innovations and security fixes. | Deliberate-Prudent | n/a | Y | n/a | 8 | 8 | 13 | 13 | 2.2 | 17 | 0 | 45 | 33750 | 0 |  | CIO office | Basis lead | New | Q2-2027 | 2026-09-15 |  | 12 |  | Run SAP Readiness Check for the target release
EX-010 | Duplicate business partners (customer/supplier) cleansing | Tech Debt | Data | Cross-app | Estimated duplicates cause blocked payments and credit errors. | Inadvertent-Reckless | n/a | Y | n/a | 8 | 5 | 8 | 8 | 2.6 | 15 | 30 | 25 | 18750 | 33750 | 6.7 | Master data owner | Data lead | Triaged | Q1-2027 | 2026-09-01 |  | 26 |  | Profile with Data Quality rules; evaluate SAP MDG consolidation
EX-011 | ORDERS IDoc failures from EDI partner | Defect | Integration | SD | Status 51 errors daily; orders re-keyed manually. | Inadvertent-Prudent | n/a | N | P2 | 8 | 13 | 8 | 2 | 14.5 | 1 | 20 | 4 | 3000 | 22500 | 1.6 | Customer service | Integration lead | In Progress | Q4-2026 | 2026-09-18 |  | 9 |  | BD87
EX-012 | Integration Suite landing zone: naming, transport (cTMS), monitoring in Cloud ALM | Enabler | Integration | BTP | Integration Suite just started; no standards yet, risk of new debt. | n/a | A | Y | n/a | 5 | 8 | 13 | 5 | 5.2 | 5 | 0 | 15 | 11250 | 0 |  | CIO office | Integration lead | Ready | Q4-2026 | 2026-09-05 |  | 22
EX-013 | Replace custom ALV reports with standard analytical Fiori apps / CDS | Tech Debt | UX | FI | 40+ Z-reports duplicate standard analytics. | Deliberate-Prudent | C | N | n/a | 5 | 2 | 5 | 8 | 1.5 | 20 | 15 | 30 | 22500 | 16875 | 16 | Finance controller | ABAP dev lead | New | Q3-2027 | 2026-09-20 |  | 7
EX-014 | Work Zone site for plant supervisors (Fiori + non-SAP tiles) | Feature | UX | PP | Supervisors switch between 5 tools per shift. | n/a | A | N | n/a | 8 | 3 | 5 | 5 | 3.2 | 12 | 10 | 15 | 11250 | 11250 | 12 | Plant ops director | BTP platform lead | New | Q2-2027 | 2026-09-20 |  | 7 |  | Depends on EX-003
EX-015 | Move transport management to Cloud ALM Change & Deployment | Enabler | Operations | Basis | Manual transport sequencing causes import errors. | Inadvertent-Prudent | n/a | N | n/a | 3 | 3 | 8 | 5 | 2.8 | 14 | 12 | 12 | 9000 | 13500 | 8 | CIO office | Basis lead | New | Q2-2027 | 2026-09-21 |  | 6
EX-016 | Delivery note form prints wrong plant address | Defect | Process | SD | Cosmetic; workaround exists. | Inadvertent-Prudent | n/a | N | P4 | 1 | 1 | 1 | 1 | 3 | 13 | 2 | 1 | 750 | 2250 | 4 | Shipping | SD functional lead | New | Backlog | 2026-06-10 |  | 109 | STALE
EX-017 | Z-field duplicates standard field (sales region on customer) | Tech Debt | Data | SD | Same value kept in two places; reports disagree. | Inadvertent-Reckless | C | Y | n/a | 5 | 3 | 8 | 3 | 5.3 | 4 | 10 | 8 | 6000 | 11250 | 6.4 | Sales ops | Data lead | Ready | Q1-2027 | 2026-09-01 |  | 26
EX-018 | Automated regression tests for top 20 end-to-end processes | Enabler | Operations | Cross-app | Manual testing makes every change risky and slow. | n/a | n/a | Y | n/a | 8 | 5 | 13 | 13 | 2 | 18 | 40 | 50 | 37500 | 45000 | 10 | CIO office | QA lead | New | Q2-2027 | 2026-09-21 |  | 6 |  | Cloud ALM test management + automation tool
EX-019 | PI/PO interface inventory and migration wave plan | Risk/Compliance | Integration | Integration | Legacy middleware approaching end of mainstream maintenance. | Deliberate-Prudent | n/a | Y | n/a | 5 | 8 | 13 | 5 | 5.2 | 5 | 0 | 10 | 7500 | 0 |  | CIO office | Integration lead | Triaged | Q1-2027 | 2026-09-10 |  | 17 |  | Only if PI/PO is in landscape - confirm
EX-020 | Joule / AI use-case readiness spike | Feature | Process | Cross-app | Business asking for AI features; need readiness view (licensing, clean core, data). | n/a | A | N | n/a | 5 | 2 | 8 | 2 | 7.5 | 3 | 0 | 5 | 3750 | 0 |  | CIO office | Enterprise architect | New | Q3-2027 | 2026-09-25 |  | 2 |  | Timeboxed spike
Formulas:
Age (days) = IF([Date raised]="","",IF([Date closed]="",TODAY(),[Date closed])-[Date raised])
Note on G4: Fowler technical-debt quadrant: deliberate vs inadvertent, prudent vs reckless.
Note on H4: SAP clean core extensibility level: A = released APIs / ABAP Cloud; B = classic APIs; C = internal/unreleased objects; D = modifications / not recommended.
Note on J4: Only for Defects. P1/P2 go to the expedite lane and bypass WSJF.
Note on K4: Business Value (Fibonacci 1-20): revenue, cost, user productivity, compliance value to the business.
Note on L4: Time Criticality (1-20): does value decay if we wait? Fixed dates, month-end, audit, contract, maintenance deadlines.
Note on M4: Risk Reduction / Opportunity Enablement (1-20): does it reduce risk (security, upgrade, audit) or unlock other items (e.g. Fiori, Work Zone, AI)? Tech debt usually scores high here.
Note on N4: Job Size (1-20): relative effort. Use the same Fibonacci scale; NOT person-days.
Note on O4: WSJF = (Business Value + Time Criticality + Risk Reduction/Opportunity Enablement) / Job Size (SAFe).
Note on Q4: Interest: hours per month the organisation loses because the debt exists (workarounds, manual fixes, extra testing, incidents).
Note on R4: Principal: estimated person-days to remove the debt.
Note on T4: Annual interest cost = hrs/month x 12 x day rate / 8.
Note on U4: Payback = one-off fix cost / monthly interest cost. < 12 months is a strong candidate.

## Capacity & Budget
Capacity Allocation & Budget Guardrails
Fund a stable team, then split its capacity by work type. Yellow = inputs. Demand is pulled live from the register (Principal person-days, open items).
1. Capacity by quarter
Quarter | Team FTE | Working days | Availability % | Capacity (person-days) | Budget cap (USD) | Capacity cost (USD) | Within budget? |  | Note
Q4-2026 | 8 | 60 | 70% | 336 | 380000 | 360000 | Yes |  | FTE and budget caps are placeholders. Capacity cost = FTE x working days x day rate (Settings).
Q1-2027 | 8 | 60 | 70% | 336 | 380000 | 360000 | Yes
Q2-2027 | 9 | 60 | 70% | 378 | 420000 | 405000 | Yes
Q3-2027 | 9 | 60 | 70% | 378 | 420000 | 405000 | Yes
Q4-2027 | 9 | 60 | 70% | 378 | 420000 | 405000 | Yes
2. Allocation guardrails (% of capacity by work type) - must total 100%
Quarter | Feature | Defect | Tech Debt | Enabler | Risk/Compliance | Total | Check
Q4-2026 | 30% | 20% | 25% | 20% | 5% | 100% | OK
Q1-2027 | 35% | 15% | 25% | 20% | 5% | 100% | OK
Q2-2027 | 40% | 15% | 25% | 15% | 5% | 100% | OK
Q3-2027 | 45% | 15% | 20% | 15% | 5% | 100% | OK
Q4-2027 | 50% | 15% | 20% | 10% | 5% | 100% | OK
3. Planned capacity (person-days) vs open demand from register
Quarter | Feature - capacity | Feature - demand | Defect - capacity | Defect - demand | Tech Debt - capacity | Tech Debt - demand | Enabler - capacity | Enabler - demand | Risk/Compliance - capacity | Risk/Compliance - demand | Total capacity | Total demand | Gap (+ = spare)
Q4-2026 | 101 | 15 | 67 | 7 | 84 | 0 | 67 | 35 | 17 | 0 | 336 | 57 | 279
Q1-2027 | 118 | 15 | 50 | 0 | 84 | 68 | 67 | 0 | 17 | 10 | 336 | 93 | 243
Q2-2027 | 151 | 15 | 57 | 0 | 95 | 90 | 57 | 62 | 19 | 45 | 379 | 212 | 167
Q3-2027 | 170 | 5 | 57 | 0 | 76 | 30 | 57 | 0 | 19 | 0 | 379 | 35 | 344
Q4-2027 | 189 | 0 | 57 | 0 | 76 | 0 | 38 | 0 | 19 | 0 | 379 | 0 | 379
Amber = demand for that work type exceeds its guardrail -> re-prioritise, move the quarter, or consciously flex the allocation at the monthly portfolio review.
Rule of thumb: never let Tech Debt + Enabler drop below ~25% while clean-core KPIs are red; P1/P2 defects are funded from the Defect bucket first.

## Roadmap
15-Month Roadmap (Oct 2026 - Dec 2027)
Enter start / end dates; bars draw automatically. Dates are proposals for discussion.
Workstream | Activity | Owner | Start | End | Oct-26 | Nov-26 | Dec-26 | Jan-27 | Feb-27 | Mar-27 | Apr-27 | May-27 | Jun-27 | Jul-27 | Aug-27 | Sep-27 | Oct-27 | Nov-27 | Dec-27
Governance | Stand up CCoE / design authority, backlog tool, cadences | EA + CIO office | 2026-10-05 | 2026-11-13 | 1 | 1
Governance | Discovery & baseline (Readiness Check, Pathfinder, ATC, SCMON, interface + data inventory) | EA | 2026-10-05 | 2026-12-18 | 1 | 1 | 1
Governance | Monthly portfolio review + quarterly roadmap refresh | CIO office | 2026-11-01 | 2027-12-31 |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
UX / Fiori | Fiori foundation: FLP, spaces & pages, roles, performance | Basis / Fiori lead | 2026-10-19 | 2027-01-29 | 1 | 1 | 1 | 1
UX / Fiori | Wave 1 Fiori apps: Finance (AP/AR/GL) | Finance + Fiori lead | 2026-12-01 | 2027-03-31 |  |  | 1 | 1 | 1 | 1
UX / Fiori | Wave 2 Fiori apps: Supply chain (MRP, inventory, purchasing) | SCM + Fiori lead | 2027-03-01 | 2027-07-30 | [5 empty] | 1 | 1 | 1 | 1 | 1
UX / Fiori | Wave 3 Fiori apps: Sales, quality, maintenance | Business leads | 2027-07-01 | 2027-11-30 | [9 empty] | 1 | 1 | 1 | 1 | 1
Work Zone | Work Zone standard: subaccount, IdP, content federation | BTP lead | 2026-11-02 | 2027-01-29 |  | 1 | 1 | 1
Work Zone | Pilot site (finance) then plant supervisor site | BTP lead | 2027-02-01 | 2027-06-30 |  |  |  |  | 1 | 1 | 1 | 1 | 1
Integration | Integration Suite landing zone + standards + monitoring | Integration lead | 2026-10-19 | 2027-01-15 | 1 | 1 | 1 | 1
Integration | Interface inventory, ISA-M classification, wave plan | Integration lead | 2026-11-01 | 2027-01-31 |  | 1 | 1 | 1
Integration | Migration waves 1-3 (P2P / PI-PO -> Integration Suite) | Integration lead | 2027-02-01 | 2027-12-17 |  |  |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
Data | Custom field inventory + map to standard / Custom Fields app | Data lead | 2026-10-19 | 2027-01-29 | 1 | 1 | 1 | 1
Data | Data quality rules, owners, dashboard; BP de-duplication | Data lead | 2026-12-01 | 2027-06-30 |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1
Data | MDG / governance tool decision + implementation start | Data lead | 2027-04-01 | 2027-12-17 | [6 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
Clean Core | Retire unused custom code | ABAP lead | 2026-12-01 | 2027-03-31 |  |  | 1 | 1 | 1 | 1
Clean Core | Remediate Level C/D objects; new builds ABAP Cloud / BTP only | ABAP lead | 2027-02-01 | 2027-12-17 |  |  |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
Platform / Ops | Cloud ALM: requirements, test mgmt, change & deployment, monitoring | Basis lead | 2026-10-19 | 2027-03-31 | 1 | 1 | 1 | 1 | 1 | 1
Platform / Ops | Test automation for top-20 processes | QA lead | 2027-01-04 | 2027-06-30 |  |  |  | 1 | 1 | 1 | 1 | 1 | 1
Platform / Ops | Release / FPS upgrade (target release TBC) | Basis lead | 2027-07-01 | 2027-10-29 | [9 empty] | 1 | 1 | 1 | 1
Innovation | AI / Joule readiness spike + Build Process Automation pilots | EA | 2027-05-03 | 2027-09-30 | [7 empty] | 1 | 1 | 1 | 1 | 1
Formulas:
Oct-26 = IF(AND([Start]<=EOMONTH(DATE(2026,10,1),0),[End]>=DATE(2026,10,1)),1,"")
Nov-26 = IF(AND([Start]<=EOMONTH(DATE(2026,11,1),0),[End]>=DATE(2026,11,1)),1,"")
Dec-26 = IF(AND([Start]<=EOMONTH(DATE(2026,12,1),0),[End]>=DATE(2026,12,1)),1,"")
Jan-27 = IF(AND([Start]<=EOMONTH(DATE(2027,1,1),0),[End]>=DATE(2027,1,1)),1,"")
Feb-27 = IF(AND([Start]<=EOMONTH(DATE(2027,2,1),0),[End]>=DATE(2027,2,1)),1,"")
Mar-27 = IF(AND([Start]<=EOMONTH(DATE(2027,3,1),0),[End]>=DATE(2027,3,1)),1,"")
Apr-27 = IF(AND([Start]<=EOMONTH(DATE(2027,4,1),0),[End]>=DATE(2027,4,1)),1,"")
May-27 = IF(AND([Start]<=EOMONTH(DATE(2027,5,1),0),[End]>=DATE(2027,5,1)),1,"")
Jun-27 = IF(AND([Start]<=EOMONTH(DATE(2027,6,1),0),[End]>=DATE(2027,6,1)),1,"")
Jul-27 = IF(AND([Start]<=EOMONTH(DATE(2027,7,1),0),[End]>=DATE(2027,7,1)),1,"")
Aug-27 = IF(AND([Start]<=EOMONTH(DATE(2027,8,1),0),[End]>=DATE(2027,8,1)),1,"")
Sep-27 = IF(AND([Start]<=EOMONTH(DATE(2027,9,1),0),[End]>=DATE(2027,9,1)),1,"")
Oct-27 = IF(AND([Start]<=EOMONTH(DATE(2027,10,1),0),[End]>=DATE(2027,10,1)),1,"")
Nov-27 = IF(AND([Start]<=EOMONTH(DATE(2027,11,1),0),[End]>=DATE(2027,11,1)),1,"")
Dec-27 = IF(AND([Start]<=EOMONTH(DATE(2027,12,1),0),[End]>=DATE(2027,12,1)),1,"")

## Cadence
Operating Cadence - Grooming, Review & Repetition
The rhythm that keeps the backlog healthy and progress visible.
Ceremony | Frequency | Duration | Participants | Inputs | Outputs / decisions | Owner
Stand-up (per team) | Daily | 15 min | Delivery team | Board | Blockers raised; WIP respected | Scrum master
Intake triage | Weekly | 45 min | Product owner, functional leads, AMS lead | New requests, incidents, ATC/monitoring findings | Classify type, dimension, severity; P1/P2 -> expedite; reject duplicates | Product owner
Backlog refinement (grooming) | Weekly / bi-weekly | 60-90 min | PO, leads, architects | Top ~30 ranked items | Sized, WSJF scored, Definition of Ready met | Product owner
Sprint planning | Every 2 weeks | 2 h | Delivery team, PO | Ready items + capacity guardrails | Sprint goal; mix per allocation % | Scrum master
Sprint review / demo | Every 2 weeks | 1 h | Team + business users | Done items | Accepted work; feedback into backlog | Product owner
Retrospective | Every 2 weeks | 45 min | Delivery team | Flow metrics | 1-2 improvement actions | Scrum master
Architecture / design authority | Bi-weekly | 60 min | EA, BTP, integration, data, security | New designs, clean core exceptions | Approve extension pattern (A-D level), integration pattern (ISA-M) | Enterprise architect
Portfolio & capacity review | Monthly | 60 min | CIO, business process owners, PO, EA | KPI dashboard, capacity vs demand | Re-balance allocation %, approve epics, budget check | CIO office
Roadmap refresh / PI planning | Quarterly | 0.5-1 day | All leads + business | Roadmap, KPI trends, SAP release news | Next-quarter plan, re-ranked epics | EA + CIO office
Tech debt register health check | Quarterly | 60 min | EA, dev lead, PO | Stale items, ATC trend, SCMON data | Close stale items, re-score, retire obsolete code | Enterprise architect
SAP innovation scan | Semi-annual | Half day | EA, leads, SAP CSP / partner | Release notes, Pathfinder, Process Insights, Fiori app library | New feature candidates added to backlog | Enterprise architect

## Sprint Tracker
Sprint Tracker & Flow Distribution
Enter story points planned and completed per work type each sprint. Flow distribution shows where capacity really went.
Sprint | Start | End | Capacity (pts) | Planned - Feature | Planned - Defect | Planned - Tech Debt | Planned - Enabler | Planned - Risk/Compliance | Done - Feature | Done - Defect | Done - Tech Debt | Done - Enabler | Done - Risk/Compliance | Planned total | Done total | Say/Do % | Tech Debt share of done % | Defect share of done %
S01 | 2026-10-05 | 2026-10-16 | 40 | 12 | 8 | 10 | 8 | 2 | 10 | 6 | 9 | 6 | 2 | 40 | 33 | 82.5% | 27.27% | 18.18%
S02 | 2026-10-19 | 2026-10-30 | [11 empty] | 0 | 0
S03 | 2026-11-02 | 2026-11-13 | [11 empty] | 0 | 0
S04 | 2026-11-16 | 2026-11-27 | [11 empty] | 0 | 0
S05 | 2026-11-30 | 2026-12-11 | [11 empty] | 0 | 0
S06 | 2026-12-14 | 2026-12-25 | [11 empty] | 0 | 0
S07 | 2026-12-28 | 2027-01-08 | [11 empty] | 0 | 0
S08 | 2027-01-11 | 2027-01-22 | [11 empty] | 0 | 0
S09 | 2027-01-25 | 2027-02-05 | [11 empty] | 0 | 0
S10 | 2027-02-08 | 2027-02-19 | [11 empty] | 0 | 0
S11 | 2027-02-22 | 2027-03-05 | [11 empty] | 0 | 0
S12 | 2027-03-08 | 2027-03-19 | [11 empty] | 0 | 0
S13 | 2027-03-22 | 2027-04-02 | [11 empty] | 0 | 0
Row S01 contains example values showing the expected format - overwrite with actuals.
Formulas:
End = [Start]+11

## Settings
Settings & Assumptions
Yellow cells are inputs. All values below are placeholders - replace with AmphenolCIT actuals.
Setting | Value | Note / source
Blended day rate (USD / person-day) | 750 | Placeholder: blend of internal + AMS partner rates. Replace with finance-approved rate.
Working days per quarter | 60 | Assumption: ~12 weeks x 5 days after holidays.
Team availability for backlog work (%) | 70% | Assumption: 30% reserved for run/ops tickets, meetings, leave.
Sprint length (working days) | 10 | 2-week sprints.
Stale item threshold (days) | 90 | Items older than this in New/Triaged are flagged in the register.
Plan start date | 2026-10-05 | First sprint start (Monday).

## Lists
Lists (drop-down sources)
Edit these lists to change the drop-downs in the Tech Debt Register. Keep one value per cell.
ItemType | Dimension | Area | Status | Quarter | Fib | YesNo | CCLevel | Quadrant | Severity
Feature | Process | FI | New | Q4-2026 | 1 | Y | A | Deliberate-Prudent | P1
Defect | Extensibility | CO | Triaged | Q1-2027 | 2 | N | B | Deliberate-Reckless | P2
Tech Debt | Data | SD | Ready | Q2-2027 | 3 |  | C | Inadvertent-Prudent | P3
Enabler | Integration | MM | In Progress | Q3-2027 | 5 |  | D | Inadvertent-Reckless | P4
Risk/Compliance | Operations | PP | Testing | Q4-2027 | 8 |  | n/a | n/a | n/a
| UX | QM | Done | Backlog | 13
|  | PM | Rejected |  | 20
|  | EWM/WM | Deferred
Basis
BTP
Integration
Cross-app