## Slide 1
AMPHENOLCIT | ENTERPRISE ARCHITECTURE
From go-live to value
A plan to pay down S/4HANA technical debt and unlock Fiori, SAP Build Work Zone, Integration Suite and trusted data — without breaking the budget
Draft for discussion | September 2026
Notes: Purpose: agree how AmphenolCIT will plan, prioritise and fund post-go-live technical debt alongside new functionality. The deck is paired with a Planner workbook (backlog, capacity, roadmap, KPIs) and a Quick Reference Guide for collecting tech debt. All numbers are placeholders until discovery is complete.

## Slide 2
One year after go-live: the platform is live, the value isn’t yet
What we heard from the team
Fiori not in use
Users still on SAP GUI; role-based Fiori apps and launchpad not rolled out.
Hungry for innovation
Strong demand for the latest S/4HANA functions and SAP Build Work Zone.
Integration Suite: early days
Usage just started; standards, monitoring and a migration plan are not yet in place.
Data quality issues
Errors and low trust in reports; data quality is not measured or owned.
Custom fields hold the data
Business data sits in Z-fields that standard Fiori apps, APIs and analytics cannot see.
The pattern: scope deferred to “phase 2” at go-live has become debt that charges interest every month — manual workarounds, invisible data, fragile interfaces — and it blocks the innovation the business is asking for. The fix is a managed, continuous backlog, not another big project.
AmphenolCIT | S/4HANA Tech Debt & Innovation Strategy | Draft for discussion 2
Notes: Summarise the interviews. The five symptoms are connected: Z-field data and missing Fiori roles are why standard apps look empty; weak integration monitoring and missing data ownership drive the data quality issues. Treat them as one programme with one backlog.

## Slide 3
What we mean by technical debt in S/4HANA
Anything that works today but makes change slower, riskier or impossible tomorrow
Principal & interest
Principal: the one-off effort to fix it.
Interest: what it costs every month we keep it — workarounds, incidents, extra testing, blocked features.
Rule: pay down debt with high interest and low principal first; accept and document the rest.
Every register item records both, so debt competes on value, not on noise.
Custom code & modifications
Z-objects, user-exit code, unused code
Clean core: Extensibility
User experience
GUI-only, no Fiori roles, many entry points
Clean core: UX
Integration
Point-to-point, unmonitored IDoc/RFC/file
Clean core: Integration
Data & custom fields
Z-field data, duplicates, no data owners
Clean core: Data
Process workarounds
Excel steps, re-keying, unused standard
Clean core: Processes
Platform & operations
Release lag, manual transports, no tests
Clean core: Operations
AmphenolCIT | S/4HANA Tech Debt & Innovation Strategy | Draft for discussion 3
Notes: Use this vocabulary in every conversation. The six categories map to SAP's five clean core dimensions plus user experience. Section 2 of the Quick Reference Guide lists the symptoms, evidence sources and fix patterns per category.

## Slide 4
SAP’s answer: keep the core clean, extend on the side
SAP clean core dimensions, with our initial gap assessment (to be validated in discovery)
Dimension
What “clean” looks like
Gap
Processes
Standard, best-practice processes; fit-to-standard
M
Extensibility
Released APIs, ABAP Cloud, key-user and BTP side-by-side extensions
H
Data
Owned, governed, high-quality master and transactional data
H
Integration
Standard APIs/events, central middleware and monitoring
H
Operations
Current release, automated test, transport and monitoring
M
H = high gap, M = medium gap. Hypothesis from interviews only.
Extensibility levels A–D
A
Released APIs, ABAP Cloud, key-user, BTP
Target for all new work
B
Classic APIs SAP lists as stable
Acceptable; monitor
C
Internal / unreleased SAP objects
Remediate when touched
D
Modifications, implicit enhancements
Retire or refactor first
Per SAP’s current extensibility guidance; confirm against the latest version.
AmphenolCIT | S/4HANA Tech Debt & Innovation Strategy | Draft for discussion 4
Notes: SAP frames post-go-live health as 'clean core' across five dimensions. For code, SAP's current guidance grades each extension A (released, upgrade-stable) to D (modifications). Our KPI will be the trend of C and D items and the share of new work built at level A. For custom fields, the Custom Fields app (key-user extensibility) is level A and exposes the field to CDS, OData and Fiori automatically.

## Slide 5
SAP tooling to discover, plan, build and measure
Most of this is already included in SAP Enterprise Support / RISE or is free — confirm entitlements
Discover
SAP Readiness Check (release / FPS upgrade)
Innovation & Optimization Pathfinder (usage-based Fiori & feature recommendations)
Signavio Process Insights (process KPIs, improvement hints)
ATC with clean-core checks; SCMON / SUSG usage
Integration Suite Migration Assessment
Plan & govern
SAP Cloud ALM: requirements, user stories, backlog, roadmap
SAP LeanIX: application & tech-debt portfolio (if licensed)
SAP Activate (Run phase, continuous improvement)
ISA-M for integration patterns
Clean core guidance & BTP Guidance Framework
Build & run
Fiori launchpad, spaces & pages, Fiori Apps Reference Library
SAP Build Work Zone (standard / advanced)
Integration Suite; Cloud Connector; Cloud Identity Services
Custom Fields app; ABAP Cloud / RAP; CAP on BTP
MDG / data quality rules; Build Process Automation
Monitor & measure
Cloud ALM: integration & exception, job, health monitoring
Cloud ALM test management & Change and Deployment
Fiori / Work Zone usage analytics
Custom Code Migration app trends
SAP Enterprise Support / Preferred Success services
AmphenolCIT | S/4HANA Tech Debt & Innovation Strategy | Draft for discussion 5
Notes: Start with the free / included tools: Readiness Check, Pathfinder (upload ST03N usage to get Fiori app recommendations), ATC clean-core checks, SCMON/SUSG for unused code, Cloud ALM for backlog, testing and monitoring. LeanIX, Signavio and MDG depend on licences - to be confirmed. Ask the SAP account team / CSP about Enterprise Support or Preferred Success services that can run parts of discovery at no extra cost.

## Slide 6
Proven frameworks we borrow — lightly
Use the parts that solve our problem; avoid framework overhead
Flow Framework
Four work types (features, defects, risks, debts) and flow distribution — shows where capacity really goes.
SAFe WSJF & capacity allocation
Rank by cost of delay ÷ size; set % guardrails per work type each quarter.
Fowler tech-debt quadrant
Deliberate vs inadvertent, prudent vs reckless — explains why debt exists and stops repeats.
Kanban flow metrics
WIP limits, lead time, throughput, aging items — simple visible progress.
DORA metrics
Deployment frequency, lead time, change failure rate, restore time — for BTP / integration delivery.
TOGAF-style design authority
Architecture board approves extension and integration patterns; prevents new debt.
ITIL 4 problem management
Turns repeat incidents into root-cause backlog items instead of recurring tickets.
Delivery tools
Cloud ALM, Jira / Azure DevOps or ServiceNow SPM for the board; Tricentis or Cloud ALM for test automation.
AmphenolCIT | S/4HANA Tech Debt & Innovation Strategy | Draft for discussion 6
Notes: We are not adopting full SAFe. We borrow WSJF and capacity allocation from SAFe, work types and flow distribution from the Flow Framework, and the Fowler quadrant to classify root causes. The board can live in Cloud ALM (included) or the existing enterprise tool (Jira / Azure DevOps / ServiceNow) - pick the one the IT team already uses.

## Slide 7
How work flows to the IT team
One front door, clear gates, and an expedite lane for production issues
Intake
Anyone
Request, incident, ATC / monitoring finding logged
Triage
PO + leads, weekly
Type, dimension, severity; duplicates closed
Refine
PO + architects
Sized, WSJF, owners → Definition of Ready
Prioritise
Portfolio, monthly
Ranked inside capacity guardrails
Plan
Team, bi-weekly
Sprint goal; mix per allocation %
Build & test
Delivery team
Design authority for new extensions; automated regression
Release
Change board
Transport / cTMS; release notes
Measure
PO + EA
KPIs, demo, feedback into backlog
Expedite lane: P1 / P2 defects skip triage and ranking, are swarmed immediately and funded from the defect allocation. Everything else waits its turn.
Definition of Ready
Business owner named, acceptance criteria, WSJF scored, clean core level and design approved, test data known.
Definition of Done
Tested (automated where possible), documented in Cloud ALM, no new level C/D code without waiver, KPI impact recorded.
AmphenolCIT | S/4HANA Tech Debt & Innovation Strategy | Draft for discussion 7
Notes: One front door stops side-channel requests. Weekly triage keeps the backlog clean; refinement makes items Ready; the monthly portfolio review decides what gets capacity. The design authority step is how we stop creating new debt while paying down the old. Definitions of Ready and Done make the gates explicit.

## Slide 8
One backlog, five work types
Everything competes for the same capacity — so trade-offs become visible
Theme
Clean core dimension, e.g. Data
Epic
Custom-field remediation for material master
Feature
Expose Z-fields via Custom Fields app
Story / task
Map ZZ_REGION to standard field; test; migrate
Work types
Feature
New capability, e.g. Fiori wave, Work Zone site
Defect
Doesn’t work as designed; P1–P4
Tech debt
Works but slows / blocks change; has interest
Enabler
Platform work others depend on, e.g. landing zone
Risk / compliance
Security, audit, maintenance deadlines
Every item carries: dimension, clean core level, interest, principal, WSJF inputs, business + IT owner, target quarter. See Planner → Tech Debt Register.
AmphenolCIT | S/4HANA Tech Debt & Innovation Strategy | Draft for discussion 8
Notes: A separate tech-debt list never gets prioritised. By putting all five work types in one ranked backlog, the business sees that choosing a new feature means deferring a debt item, and vice versa. The hierarchy links sprint-level tasks up to clean core themes, so progress rolls up to leadership KPIs.

## Slide 9
Prioritising bugs vs features vs tech debt
Three decisions, made at three different levels
1
Expedite
Daily
P1 / P2 defects and security issues go first. Non-negotiable, but capped by the defect allocation; overflow triggers a portfolio conversation.
2
Allocate
Monthly / quarterly
Portfolio sets % of capacity per work type each quarter (next slide). This is the budget decision, made once — not item by item.
3
Rank
Weekly refinement
Inside each bucket, rank by WSJF. Tech debt scores on risk reduction and opportunity enablement, not just business value.
WSJF
(Business value + Time criticality + Risk reduction / Opportunity enablement) ÷ Job size
Tech debt: interest vs principal
Pay down now
High interest, low principal
Plan an epic
High interest, high principal
Fix when touched
Low interest, low principal
Accept & document
Low interest, high principal
Interest ↑
Principal →
AmphenolCIT | S/4HANA Tech Debt & Innovation Strategy | Draft for discussion 9
Notes: Separating the three decisions stops every item turning into a debate. Leadership decides the split once per quarter; the team ranks within it. WSJF uses a Fibonacci scale 1-20 - the scoring anchors are in the Quick Reference Guide, section 5. For tech debt, the interest/principal grid is a quick sanity check on the WSJF result.

## Slide 10
Capacity guardrails keep the budget flat
Fund a stable team, then shift the mix as debt comes down (illustrative %)
Chart: Share of team capacity by work type (%)
| Q4-26 | Q1-27 | Q2-27 | Q3-27 | Q4-27
Feature | 30 | 35 | 40 | 45 | 50
Defect | 20 | 15 | 15 | 15 | 15
Tech debt | 25 | 25 | 25 | 20 | 20
Enabler | 20 | 20 | 15 | 15 | 10
Risk/compliance | 5 | 5 | 5 | 5 | 5
Funding tactics that don’t need new budget
Stable team, flexible mix: fund capacity once; the portfolio moves the % each quarter.
Bundle: fix debt in the objects a feature already touches (Boy Scout rule).
Retire before remediate: unused code and interfaces cost nothing to delete.
Use what’s paid for: Cloud ALM, Pathfinder, Readiness Check, BTP credits, Enterprise Support services.
Self-fund: redeploy savings from fewer tickets, retired middleware and AMS effort.
Stage-gate epics: release funding in slices tied to KPI movement.
AmphenolCIT | S/4HANA Tech Debt & Innovation Strategy | Draft for discussion 10
Notes: Front-load enablers and tech debt while the foundation is built (Work Zone, Integration Suite landing zone, Fiori roles, custom-field clean-up), then shift toward features as the platform stabilises. Keep tech debt + enablers at or above ~25-30% while clean core KPIs are red. The Planner's Capacity & Budget tab compares these guardrails with live demand from the register.

## Slide 11
Grooming and repetition: the operating cadence
Same meetings, same day, every cycle — the rhythm is what makes the backlog trustworthy
Daily
Stand-up (15 min)
Weekly
Intake triage (45 min)
Backlog refinement (60–90 min)
Bi-weekly
Sprint planning
Sprint review / demo with users
Retrospective
Design authority
Monthly
Portfolio & capacity review
KPI dashboard to leadership
Quarterly
Roadmap refresh / PI planning
Tech debt register health check
Semi-annual
SAP innovation scan (release notes, Pathfinder, Fiori app library)
Details, participants, inputs and outputs: Planner → Cadence tab.
AmphenolCIT | S/4HANA Tech Debt & Innovation Strategy | Draft for discussion 11
Notes: Repetition is the point. Weekly triage and refinement keep the top of the backlog Ready; the bi-weekly demo shows users progress; the monthly portfolio review is where the capacity split and budget are checked; the quarterly health check closes stale items and re-scores debt. The semi-annual innovation scan feeds new S/4 and BTP features into the backlog so the business sees innovation, not only fixes.

## Slide 12
Making progress visible
A handful of KPIs per dimension, reviewed monthly (baselines to be measured in discovery)
Fiori adoption
0% → 75%
% active users on Fiori
Work Zone reach
0 → 600
Users with a role-based site
Integration
5% → 70%
% interfaces on Integration Suite
Clean core
↓ 50%
ATC level C/D findings
Data quality
72% → 95%
DQ rule pass rate
Custom fields
0% → 90%
Z-fields mapped or exposed
Flow
45 → 20
Median lead time (days)
Release currency
12 → 3
Months behind latest FPS
Show, don’t tell
Board: Kanban/sprint board visible to business (Cloud ALM or existing tool).
Demo: every two weeks, users see working Fiori apps, sites and fixes.
Trends: tech-debt interest, C/D findings and flow distribution over time.
Wins: one-page monthly note — what shipped, what it saved, what’s next.
AmphenolCIT | S/4HANA Tech Debt & Innovation Strategy | Draft for discussion 12
Notes: Targets shown are to Q4-2027 and are placeholders to be set once baselines are measured. The Planner's KPI Dashboard computes live backlog counts and health signals (stale items, open C/D items, annual interest cost of open debt) and a RAG status against targets.

## Slide 13
Roadmap: 15 months, six workstreams
Foundations first, then scale; dates are proposals
Q4 2026
Q1 2027
Q2 2027
Q3 2027
Q4 2027
Mobilise & baseline
Foundations & quick wins
Scale
Optimise & innovate
UX / Fiori
Fiori foundation
Finance wave
Supply chain wave
Sales / QM / PM
Work Zone
Subaccount, IdP
Pilot + plant supervisor site
Integration
Landing zone
Inventory, ISA-M
Migration waves 1–3
Data
Z-field inventory
DQ rules + BP clean-up
MDG decision & start
Clean core
Retire unused code
Remediate C/D; ABAP Cloud for all new
Platform / ops
Cloud ALM set-up
Test automation
Release / FPS upgrade
AmphenolCIT | S/4HANA Tech Debt & Innovation Strategy | Draft for discussion 13
Notes: Phase 0 (Oct-Nov 2026): mobilise governance and baseline with SAP tools. Phase 1 (to ~Feb 2027): Fiori foundation and first finance wave, Work Zone and Integration Suite landing zones, custom-field inventory, Cloud ALM. Phase 2 (2027): scale Fiori by role, migrate interfaces in waves, data quality programme, remediate C/D code. Phase 3 (H2 2027): release upgrade, AI/Joule readiness, process automation. Full activity-level Gantt is in the Planner's Roadmap tab.

## Slide 14
Three plays for the biggest gaps
Each play starts with SAP standard and builds only what standard can’t do
Fiori & Work Zone
Pull 12 months of transaction usage; get app recommendations (Pathfinder / Fiori Apps Library)
Design roles as spaces & pages per job, not per module
Roll out in business waves with key users as champions
Work Zone standard as the single entry point: Fiori, BTP apps and non-SAP links
Measure adoption; retire GUI transactions as apps land
Integration Suite
Landing zone: naming, packages, security, cTMS transports, alerting via Cloud ALM
Inventory every interface; classify with ISA-M
Prefer standard APIs and events from SAP Business Accelerator Hub
Migrate in waves: highest-failure and PI/PO interfaces first
Stop new point-to-point builds via design authority
Data & custom fields
Inventory every business-data Z-field (use the 8-question checklist)
Map to standard where S/4 now has a home; else re-create with Custom Fields app
Assign data owners; define DQ rules and a monthly score
Clean duplicates (business partner, material) before migrating fields
Decide on MDG / governance tooling with a business case
AmphenolCIT | S/4HANA Tech Debt & Innovation Strategy | Draft for discussion 14
Notes: Custom fields are the linchpin: while business data sits in SE11 appends, standard Fiori apps, OData APIs, Work Zone content and analytics cannot use it. Fixing that unlocks the Fiori and Work Zone plays. Integration Suite standards must be in place before volume grows, or the new platform becomes the next generation of debt.

## Slide 15
The first 90 days
Visible early wins while the baseline is built
Days 1–30
Mobilise
Name product owner, EA, design authority
Choose backlog tool (Cloud ALM or existing)
Load the Planner register; run first triage
Run Readiness Check, Pathfinder, ATC clean-core, SCMON
Start interface and Z-field inventories
Days 31–60
Baseline & foundations
Score and rank top 50 items with WSJF
Agree capacity guardrails and budget cap
Fiori launchpad foundation + first finance roles
Work Zone subaccount, IdP; Integration Suite landing zone
First KPI dashboard to leadership
Days 61–90
First wins
First Fiori apps live for finance users
Pilot Work Zone site demoed
Top 3 failing interfaces fixed or migrated
First Z-fields mapped / exposed; DQ score published
Quarterly roadmap refresh with business
AmphenolCIT | S/4HANA Tech Debt & Innovation Strategy | Draft for discussion 15
Notes: The 90-day plan is designed so users see something new by day 90 (Fiori apps, a Work Zone pilot, fewer interface failures), which builds support for the longer clean-core work.

## Slide 16
Questions we need answered to finalise the plan
Please bring answers (or owners) to the next session
Landscape & licensing
S/4HANA deployment (RISE private, on-premise, public) and current release / FPS?
BTP contract model and entitlements (Work Zone edition, Integration Suite, credits)?
Is PI/PO in the landscape, and until when?
Budget & team
Current IT/AMS run budget and team size; what is fixed vs flexible?
Is the partner contract ticket-based or capacity-based?
Who can approve capacity shifts between work types?
Backlog & tools
Where do requests and incidents live today (ServiceNow, Jira, Excel, Cloud ALM)?
Is SAP Cloud ALM activated, and which apps are in use?
Is there an existing design authority / architecture board?
UX & Work Zone
Fiori front-end: embedded or hub? Any roles built at go-live?
Which user groups want Work Zone first, and for what?
Any non-SAP apps that must appear on the launchpad?
Data & custom fields
How many business-data Z-fields, in which objects?
Which data domains hurt most, and who owns them?
Is MDG or another governance tool licensed or planned?
Outcomes
Top 3 business outcomes leadership expects in 12 months?
Any hard dates (audits, acquisitions, plant roll-outs, maintenance ends)?
Appetite for AI / Joule use cases in 2027?
AmphenolCIT | S/4HANA Tech Debt & Innovation Strategy | Draft for discussion 16
Notes: These questions change the plan materially: deployment model and BTP entitlements decide tooling and cost; budget model decides how capacity allocation is enforced; custom field volume sizes the data workstream. The Quick Reference Guide has the full interview question bank by role.

## Slide 17
Decisions requested
1
Adopt one backlog for all five work types, with the register as the single source
2
Approve capacity guardrails (starting ~45% tech debt + enablers) within the current budget
3
Name a product owner, business owners per dimension, and a design authority
4
Choose the backlog tool: SAP Cloud ALM or the existing enterprise tool
5
Start the 30-day discovery using SAP’s free tools
Next steps
Share Quick Reference Guide with leads; run role interviews (2 weeks)
Load findings into the Planner register; first triage
Run SAP discovery tools; baseline KPIs
Scoring workshop: WSJF top 50
Portfolio review: confirm guardrails, roadmap and 90-day plan
Companion files: Planner (.xlsx) and Quick Reference Guide (.docx)
Notes: Close by asking for the five decisions. The first four are organisational and cost nothing; the fifth starts discovery using tools included in existing SAP contracts.