## Schedule
Project NorthStar - SAP S/4HANA 2023 SPS06 upgrade schedule
As of Sun 18 Oct 2026 ¦ Update the Status column daily (drop-down). Phase rows roll up by themselves. ¦ CONFIDENTIAL AND PROPRIETARY TO INTERNATIONAL
[11 empty] | 2026-10-12 | [6 empty] | 2026-10-19 | [6 empty] | 2026-10-26 | [6 empty] | 2026-11-02 | [6 empty] | 2026-11-09 | [6 empty] | 2026-11-16 | [6 empty] | 2026-11-23 | [6 empty] | 2026-11-30 | [6 empty] | 2026-12-07 | [6 empty] | 2026-12-14 | [6 empty] | 2026-12-21 | [6 empty] | 2026-12-28
ID | Task | Team | Days | Start | Finish | Status | % Complete | Predecessors | Detail tasks | Type | 2026-10-12 | 2026-10-13 | 2026-10-14 | 2026-10-15 | 2026-10-16 | 2026-10-17 | 2026-10-18 | 2026-10-19 | 2026-10-20 | 2026-10-21 | 2026-10-22 | 2026-10-23 | 2026-10-24 | 2026-10-25 | 2026-10-26 | 2026-10-27 | 2026-10-28 | 2026-10-29 | 2026-10-30 | 2026-10-31 | 2026-11-01 | 2026-11-02 | 2026-11-03 | 2026-11-04 | 2026-11-05 | 2026-11-06 | 2026-11-07 | 2026-11-08 | 2026-11-09 | 2026-11-10 | 2026-11-11 | 2026-11-12 | 2026-11-13 | 2026-11-14 | 2026-11-15 | 2026-11-16 | 2026-11-17 | 2026-11-18 | 2026-11-19 | 2026-11-20 | 2026-11-21 | 2026-11-22 | 2026-11-23 | 2026-11-24 | 2026-11-25 | 2026-11-26 | 2026-11-27 | 2026-11-28 | 2026-11-29 | 2026-11-30 | 2026-12-01 | 2026-12-02 | 2026-12-03 | 2026-12-04 | 2026-12-05 | 2026-12-06 | 2026-12-07 | 2026-12-08 | 2026-12-09 | 2026-12-10 | 2026-12-11 | 2026-12-12 | 2026-12-13 | 2026-12-14 | 2026-12-15 | 2026-12-16 | 2026-12-17 | 2026-12-18 | 2026-12-19 | 2026-12-20 | 2026-12-21 | 2026-12-22 | 2026-12-23 | 2026-12-24 | 2026-12-25 | 2026-12-26 | 2026-12-27 | 2026-12-28 | 2026-12-29 | 2026-12-30 | 2026-12-31 | 2027-01-01 | 2027-01-02 | 2027-01-03
0 | Start-up |  | 14 | 2026-10-02 | 2026-10-15 | Complete | 100% |  |  | Summary
0.1 | Triage SAP side-effect notes | PwC Tech | 5 | 2026-10-02 | 2026-10-06 | Complete | 100% |  | H.4 | Task
0.2 | Plan XS4 stack and request update | INTL Basis | 2 | 2026-10-03 | 2026-10-04 | Complete | 100% |  | H.1, H.2 | Task
0.3 | Close first XS4 update run (SUM reset) | SAP ECS | 8 | 2026-10-07 | 2026-10-14 | Complete | 100% | 0.2 | H.3 | Task
0.4 | ◆ Approach set: Sandbox = copy of DS4 | INTL Basis | 0 | 2026-10-15 | 2026-10-15 | Complete | 100% | 0.3 | H.5 | Milestone |  |  |  | ◆
1 | Prepare Sandbox |  | 14 | 2026-10-15 | 2026-10-28 | On Track | 17.28% |  |  | Summary
1.1 | Align plan with PwC Tech | PwC Tech | 2 | 2026-10-15 | 2026-10-16 | Complete | 100% | 0.4 | 0.01a | Task
1.2 | Review plan (functional streams) | PwC Functional | 4 | 2026-10-16 | 2026-10-19 | On Track | 75% | 1.1 | 0.01b | Task
1.3 | Implement SAP Notes in DS4 | INTL Basis | 2 | 2026-10-15 | 2026-10-16 | Complete | 100% | 0.4 | 0.02 | Task
1.4 | Request DS4 to XS4 copy from ECS | INTL Basis | 2 | 2026-10-15 | 2026-10-16 | Complete | 100% | 0.4 | 0.04a | Task
1.5 | Create Maintenance Planner plans | INTL Basis | 2 | 2026-10-15 | 2026-10-16 | Complete | 100% |  | 0.05 | Task
1.6 | Run SI-check and pre-checks | INTL Basis | 7 | 2026-10-16 | 2026-10-22 | On Track | 42.86% | 1.3 | 0.03, 0.16 | Task
1.7 | Approve plan at Steering | INTL PMO | 1 | 2026-10-20 | 2026-10-20 | Not Started | 0% | 1.2 | 0.01 | Task
1.8 | Request remaining copies and upgrades | INTL Basis | 3 | 2026-10-19 | 2026-10-21 | Not Started | 0% | 1.5 | 0.04, 0.06 | Task
1.9 | Prepare copy isolation checklist | INTL Basis | 3 | 2026-10-19 | 2026-10-21 | Not Started | 0% |  | 0.10 | Task
1.10 | Line up SAP support and on-call | INTL Basis | 5 | 2026-10-19 | 2026-10-23 | Not Started | 0% | 1.2 | 0.07, 0.08, 0.09 | Task
1.11 | Send vendor questions | INTL Basis | 10 | 2026-10-19 | 2026-10-28 | Not Started | 0% |  | 0.11 | Task
1.12 | Check custom code (ATC) | PwC Tech | 5 | 2026-10-19 | 2026-10-23 | Not Started | 0% |  | 0.13, 0.14 | Task
1.13 | Assess Fiori app impact | PwC Tech | 10 | 2026-10-19 | 2026-10-28 | Not Started | 0% |  | 0.17, 0.18 | Task
1.14 | Create data-migration users (SDMI) | INTL Security | 5 | 2026-10-19 | 2026-10-23 | Not Started | 0% |  | 0.15 | Task
1.15 | Prepare CFIN/SLT and GTS runbooks | PwC Functional | 10 | 2026-10-19 | 2026-10-28 | Not Started | 0% |  | 0.19, 0.20 | Task
1.16 | Agree Mock3 rules with Syniti | PwC Data Migration | 2 | 2026-10-19 | 2026-10-20 | Not Started | 0% |  | 0.21 | Task
1.17 | Publish transport rules | INTL Basis | 3 | 2026-10-21 | 2026-10-23 | Not Started | 0% | 1.7 | 0.12 | Task
1.18 | Tag regression scripts | INTL Testing | 5 | 2026-10-19 | 2026-10-23 | Not Started | 0% |  | 0.22 | Task
1.19 | ◆ G0 Ready for Sandbox | INTL PMO | 0 | 2026-10-22 | 2026-10-22 | Not Started | 0% | 1.3, 1.4, 1.5, 1.6, 1.7, 1.8, 1.9 | G0 | Milestone | [10 empty] | ◆
2 | Sandbox XS4 |  | 9 | 2026-10-21 | 2026-10-29 | Not Started | 0% |  |  | Summary
2.1 | Copy DS4 to XS4 | SAP ECS | 2 | 2026-10-21 | 2026-10-22 | Not Started | 0% | 1.3, 1.4 | 1.01 | Task
2.2 | Isolate XS4 | INTL Basis | 1 | 2026-10-22 | 2026-10-22 | Not Started | 0% | 2.1, 1.9 | 1.02 | Task
2.3 | Check notes and resubmit SUM request | INTL Basis | 1 | 2026-10-22 | 2026-10-22 | Not Started | 0% | 2.2 | 1.03 | Task
2.4 | Upgrade XS4 (downtime Sat 24 Oct) | SAP ECS | 4 | 2026-10-22 | 2026-10-25 | Not Started | 0% | 2.3, 1.19 | 1.04 | Task
2.5 | Adjust custom code (SPDD/SPAU) | PwC Tech | 3 | 2026-10-24 | 2026-10-26 | Not Started | 0% | 2.4SS | 1.05 | Task
2.6 | Run technical and Fiori checks | INTL Basis | 2 | 2026-10-25 | 2026-10-26 | Not Started | 0% | 2.4 | 1.06, 1.07 | Task
2.7 | Update roles (SU25, GRC) | INTL Security | 2 | 2026-10-26 | 2026-10-27 | Not Started | 0% | 2.6 | 1.08 | Task
2.8 | Trial SAP note bundle | PwC Tech | 3 | 2026-10-26 | 2026-10-28 | Not Started | 0% | 2.5 | 1.09 | Task
2.9 | Test Sandbox (30 tests) | PwC Functional | 3 | 2026-10-26 | 2026-10-28 | Not Started | 0% | 2.6 | 1.10 | Task
2.10 | Confirm upgrade windows with ECS | INTL Basis | 1 | 2026-10-28 | 2026-10-28 | Not Started | 0% | 2.4 | 1.11 | Task
2.11 | ◆ G1 Sandbox sign-off | INTL PMO | 0 | 2026-10-29 | 2026-10-29 | Not Started | 0% | 2.5, 2.6, 2.7, 2.8, 2.9, 2.10 | G1 | Milestone | [17 empty] | ◆
3 | Development DS4 (+ DS5 copy) |  | 18 | 2026-10-27 | 2026-11-13 | Not Started | 0% |  |  | Summary
3.1 | Copy DS4 to DS5 (fallback) | SAP ECS | 2 | 2026-10-27 | 2026-10-28 | Not Started | 0% | 1.8 | 2.01 | Task
3.2 | Open DS5 for fixes | INTL Basis | 2 | 2026-10-28 | 2026-10-29 | Not Started | 0% | 3.1 | 2.02 | Task
3.3 | Freeze DS4 transports | PwC Tech | 1 | 2026-10-30 | 2026-10-30 | Not Started | 0% | 1.17 | 2.03 | Task
3.4 | Upgrade DS4 (downtime Sat 31 Oct) | SAP ECS | 3 | 2026-10-30 | 2026-11-01 | Not Started | 0% | 2.11 | 2.04 | Task
3.5 | Adjust custom code (SPDD/SPAU) | PwC Tech | 3 | 2026-10-31 | 2026-11-02 | Not Started | 0% | 3.4SS | 2.05 | Task
3.6 | Run technical checks | INTL Basis | 2 | 2026-11-01 | 2026-11-02 | Not Started | 0% | 3.4 | 2.06 | Task
3.7 | Update roles | INTL Security | 2 | 2026-11-02 | 2026-11-03 | Not Started | 0% | 3.6 | 2.07 | Task
3.8 | Apply notes and unit test | PwC Tech | 3 | 2026-11-02 | 2026-11-04 | Not Started | 0% | 3.5 | 2.08 | Task
3.9 | Test integrations in Dev | PwC Functional | 2 | 2026-11-03 | 2026-11-04 | Not Started | 0% | 3.6 | 2.09 | Task
3.10 | Keep DS5 and DS4 in sync | PwC Tech | 15 | 2026-10-30 | 2026-11-13 | Not Started | 0% | 3.2 | 2.10 | Task
3.11 | ◆ G2 Dev ready | INTL PMO | 0 | 2026-11-04 | 2026-11-04 | Not Started | 0% | 3.5, 3.6, 3.7, 3.8, 3.9 | G2 | Milestone | [23 empty] | ◆
4 | QA QS4 (+ QS5 copy) |  | 9 | 2026-11-04 | 2026-11-12 | Not Started | 0% |  |  | Summary
4.1 | Copy QS4 to QS5 (fallback) | SAP ECS | 2 | 2026-11-04 | 2026-11-05 | Not Started | 0% | 1.8 | 3.01 | Task
4.2 | Isolate QS5 | INTL Basis | 2 | 2026-11-05 | 2026-11-06 | Not Started | 0% | 4.1 | 3.02 | Task
4.3 | Close SIT2 and freeze results | INTL Testing | 1 | 2026-11-06 | 2026-11-06 | Not Started | 0% |  | 3.03 | Task
4.4 | Pause QS4 interfaces | INTL Basis | 1 | 2026-11-06 | 2026-11-06 | Not Started | 0% | 1.15 | 3.04 | Task
4.5 | Upgrade QS4 (downtime Sat 7 Nov) | SAP ECS | 4 | 2026-11-05 | 2026-11-08 | Not Started | 0% | 3.11 | 3.05 | Task
4.6 | Run technical checks | INTL Basis | 1 | 2026-11-08 | 2026-11-08 | Not Started | 0% | 4.5 | 3.06 | Task
4.7 | Resume CFIN, GTS and BTP links | PwC Functional | 2 | 2026-11-08 | 2026-11-09 | Not Started | 0% | 4.6 | 3.07 | Task
4.8 | Run regression (P1 scripts) | PwC Functional | 4 | 2026-11-09 | 2026-11-12 | Not Started | 0% | 4.7, 4.3 | 3.08 | Task
4.9 | Test security | INTL Security | 3 | 2026-11-09 | 2026-11-11 | Not Started | 0% | 4.6 | 3.09 | Task
4.10 | Validate data loads (Syniti) | PwC Data Migration | 3 | 2026-11-09 | 2026-11-11 | Not Started | 0% | 4.6 | 3.10 | Task
4.11 | Ready QS5 as fallback | PwC Functional | 3 | 2026-11-09 | 2026-11-11 | Not Started | 0% | 4.2 | 3.11 | Task
4.12 | Fix and retest defects | PwC Functional | 4 | 2026-11-09 | 2026-11-12 | Not Started | 0% | 4.8SS | 3.12 | Task
4.13 | ◆ G3 Go for pre-production | INTL PMO | 0 | 2026-11-12 | 2026-11-12 | Not Started | 0% | 4.5, 4.6, 4.7, 4.8, 4.9, 4.10, 4.11, 4.12 | G3 | Milestone | [31 empty] | ◆
5 | Pre-production SS4 |  | 26 | 2026-11-09 | 2026-12-04 | Not Started | 0% |  |  | Summary
5.1 | Run UAT week 1 (FPS02) | Business (UAT) | 5 | 2026-11-09 | 2026-11-13 | Not Started | 0% |  | 4.01 | Task
5.2 | Pause SS4 interfaces | INTL Basis | 1 | 2026-11-13 | 2026-11-13 | Not Started | 0% | 4.13 | 4.02 | Task
5.3 | Upgrade SS4 (downtime Fri-Sat 13-14 Nov) | SAP ECS | 4 | 2026-11-12 | 2026-11-15 | Not Started | 0% | 4.13 | 4.03 | Task
5.4 | Run technical checks | INTL Basis | 2 | 2026-11-14 | 2026-11-15 | Not Started | 0% | 5.3SS | 4.04 | Task
5.5 | Resume and verify interfaces | PwC Functional | 1 | 2026-11-15 | 2026-11-15 | Not Started | 0% | 5.4 | 4.05 | Task
5.6 | Run UAT weeks 2-4 (SPS06) | Business (UAT) | 19 | 2026-11-16 | 2026-12-04 | Not Started | 0% | 5.5 | 4.06 | Task
5.7 | Check performance | INTL Testing | 3 | 2026-11-16 | 2026-11-18 | Not Started | 0% | 5.5 | 4.07 | Task
5.8 | ◆ G4 Go for production | INTL PMO | 0 | 2026-11-19 | 2026-11-19 | Not Started | 0% | 5.4, 5.5, 5.7 | G4 | Milestone | [38 empty] | ◆
6 | Production PS4 |  | 12 | 2026-11-14 | 2026-11-25 | Not Started | 0% |  |  | Summary
6.1 | Hold PS4 transports | INTL Basis | 9 | 2026-11-14 | 2026-11-22 | Not Started | 0% | 5.3SS | 5.01 | Task
6.2 | Upgrade PS4 (downtime Fri-Sat 20-21 Nov) | SAP ECS | 4 | 2026-11-19 | 2026-11-22 | Not Started | 0% | 5.8 | 5.02 | Task
6.3 | Run technical checks | INTL Basis | 3 | 2026-11-21 | 2026-11-23 | Not Started | 0% | 6.2SS | 5.03 | Task
6.4 | Verify connections | INTL Basis | 1 | 2026-11-23 | 2026-11-23 | Not Started | 0% | 6.3 | 5.04 | Task
6.5 | ◆ G5 Upgrade closed | INTL PMO | 0 | 2026-11-25 | 2026-11-25 | Not Started | 0% | 6.3, 6.4 | G5 | Milestone | [44 empty] | ◆
7 | N+1 DS5 / QS5 |  | 4 | 2026-12-01 | 2026-12-04 | Not Started | 0% |  |  | Summary
7.1 | Upgrade DS5 | SAP ECS | 1 | 2026-12-01 | 2026-12-01 | Not Started | 0% | 5.8 | 6.01 | Task
7.2 | Upgrade QS5 | SAP ECS | 1 | 2026-12-03 | 2026-12-03 | Not Started | 0% | 7.1 | 6.02 | Task
7.3 | Retrofit and reconnect N+1 | INTL Basis | 4 | 2026-12-01 | 2026-12-04 | Not Started | 0% | 7.1 | 6.03 | Task
8 | Close-out |  | 40 | 2026-11-23 | 2027-01-01 | Not Started | 0% |  |  | Summary
8.1 | Confirm data migrations finished (SDMI) | INTL Basis | 12 | 2026-11-23 | 2026-12-04 | Not Started | 0% | 6.2 | 7.03 | Task
8.2 | Close out the upgrade | INTL Basis | 5 | 2026-11-30 | 2026-12-04 | Not Started | 0% | 6.5 | 7.04 | Task
8.3 | Watch new side-effect notes weekly | PwC Tech | 40 | 2026-11-23 | 2027-01-01 | Not Started | 0% | 6.3 | 7.01 | Task
8.4 | Support cutover on SPS06 | INTL PMO | 25 | 2026-12-07 | 2026-12-31 | Not Started | 0% | 6.5 | 7.02 | Task
8.5 | Decide obsolete-data handling | INTL Basis | 1 | 2027-01-01 | 2027-01-01 | Not Started | 0% |  | 7.05 | Task
How to read the bars
Phase
Complete
In progress: elapsed
In progress: remaining
Planned
At risk
Blocked
As-of date
Weekend
◆ | Gate or milestone (green when complete)
Days are calendar days. Upgrade downtimes are on weekends; dates in the task name.
Note on G4: Edit daily on task and gate rows (drop-down). Phase rows roll up automatically.
Note on H4: Calculated: 100% when Complete, 0% when Not Started; for open tasks the share of planned days elapsed by the As-of date (max 90%). Type over it with an actual figure if you prefer.
Note on I4: MS Project notation: 2.4 = finish-to-start; 2.4SS = start-to-start.
Note on J4: Rows in the Detail Plan tab that this step groups.

## Exec Summary
Executive summary
Edit the yellow cells daily, save, then load this file in the dashboard ("Update data"). The dashboard headline comes from here.
Item | Value
As of | 2026-10-18
Overall status | On Track
Headline | Sandbox preparation is completing on plan. XS4 is copied from DS4 on Wed 21 - Thu 22 Oct and upgraded on Sat 24 Oct.
Key message 1 | Done: SAP Notes in DS4, ECS copy request raised, Maintenance Planner plans for every system.
Key message 2 | PwC Tech team aligned; PwC Functional team reviewing the plan before Steering on Tue 20 Oct.
Key message 3 | Production upgrade Sat 21 Nov, before cutover (7 Dec) and go-live (1 Jan 2027).
History note | Thu 15 Oct: approach changed - the Sandbox (XS4) is rebuilt as a copy of DS4 before its upgrade.
Project | Project NorthStar
Upgrade | SAP S/4HANA 2023 FPS02 to SPS06 (RISE with SAP, Private Cloud)
Plan version | v4.0 (18 Oct 2026)
Plan owner | Girish Ogirala (INTL Basis)
Go-live | 2027-01-01
Team alignment
Team | Plan alignment | Status | Next step
INTL Basis | Plan owner | On Track | SI-check in DS4 and QS4; isolation checklist; remaining ECS requests Mon 19 Oct
PwC Tech | Aligned | On Track | Custom code check (ATC) and Fiori impact from Mon 19 Oct
PwC Functional | Reviewing | On Track | Review complete Mon 19 Oct; CFIN/SLT and GTS runbooks
SAP ECS | Copy request raised | On Track | Copy DS4 to XS4 Wed 21 - Thu 22 Oct; XS4 upgrade Sat 24 Oct
Asks of leadership
Ask | Detail | By | From
Approve the upgrade plan | Copy approach, five weekend upgrade windows (24 Oct - 21 Nov), gates G0-G5, Plan B/C | 2026-10-20 | Steering
Confirm weekend cover | SAP MaxAttention, ECS and the on-call rota for the weekends 24 Oct - 22 Nov | 2026-10-22 | Steering / INTL Basis
Plan numbers (calculated from Schedule)
Tasks and gates | 79
Complete | 8
On Track | 2
Not Started | 69
At Risk | 0
Blocked | 0
Overdue | 0
Next gate date | 2026-10-22
Next gate | ◆ G0 Ready for Sandbox
Note on B5: Set to the date of this update. Overdue and % complete are calculated from it.

## Milestones
Milestones and gates
Gate and upgrade rows take their status from the Schedule (column H). Project rows are context from the Plan on a Page.
ID | Date | Milestone | Type | Criteria / notes | Decision owner | Status | Schedule ID
G0 | 2026-10-22 | Ready for Sandbox | Gate | Notes 2399707/2502552 in DS4 and transported; SI-check RC < 8 in DS4 and QS4; SRs accepted with windows; MPID per system; copy isolation checklist signed | INTL PMO (Steering) | Not Started | 1.19
XS4 | 2026-10-24 | Sandbox XS4 on SPS06 | Upgrade | Downtime Sat 24 Oct, Sun 25 contingency | SAP ECS / INTL Basis | Not Started | 2.4
G1 | 2026-10-29 | Sandbox sign-off | Gate | XS4 upgrade clean; Sandbox Test Plan "Yes" items passed; SPDD/SPAU and note effort sized; downtime measured; vendor answers received or tracked | INTL PMO (Steering) | Not Started | 2.11
DS4 | 2026-10-31 | Development DS4 on SPS06 | Upgrade | Downtime Sat 31 Oct, Sun 1 Nov contingency; DS5 live as temporary Dev | SAP ECS / INTL Basis | Not Started | 3.4
G2 | 2026-11-04 | Dev ready | Gate | SPDD/SPAU, note and role transports released; no blocking unit-test failure; zero priority-1 ATC findings | INTL PMO (Steering) | Not Started | 3.11
SIT2 | 2026-11-06 | SIT2 ends (QS4-200) | Project | Plan on a Page | Project | Not Started | -
QS4 | 2026-11-07 | QA QS4 on SPS06 | Upgrade | Downtime Sat 7 Nov, Sun 8 contingency | SAP ECS / INTL Basis | Not Started | 4.5
G3 | 2026-11-12 | Go for pre-production | Gate | P1 re-run >= 95% pass; zero open Sev1/Sev2 upgrade defects; CFIN, GTS, BTP integrations green; security passed; migration objects load on SPS06 | INTL PMO (Steering) | Not Started | 4.13
SS4 | 2026-11-14 | Pre-production SS4 on SPS06 | Upgrade | Downtime Fri night 13 - Sat 14 Nov, Sun 15 contingency | SAP ECS / INTL Basis | Not Started | 5.3
G4 | 2026-11-19 | Go for production | Gate | SS4 stable; UAT running on SPS06 without upgrade blockers; performance delta acceptable; legacy end-to-end OK | INTL PMO (Steering) | Not Started | 5.8
PS4 | 2026-11-21 | Production PS4 on SPS06 | Upgrade | Downtime Fri night 20 - Sat 21 Nov, Sun 22 contingency | SAP ECS / INTL Basis | Not Started | 6.2
G5 | 2026-11-25 | Upgrade closed | Gate | PS4 technical verification signed; UAT clean on SPS06; open items handed to Go/No-Go | INTL PMO -> Go/No-Go board | Not Started | 6.5
GNG | 2026-11-30 | Go / No-Go (30 Nov - 4 Dec) | Project | Plan on a Page (at UAT end) | Project | Not Started | -
N+1 | 2026-12-03 | DS5 / QS5 on SPS06 | Upgrade | DS5 Tue 1 Dec, QS5 Thu 3 Dec | SAP ECS / INTL Basis | Not Started | 7.2
CUT | 2026-12-07 | Cutover starts (7 - 31 Dec) | Project | Plan on a Page | Project | Not Started | -
GL | 2027-01-01 | Go-live | Project | Plan on a Page | Project | Not Started | -
Plan B |  | Plan B (ECS cannot meet a window, or G1 fails): shift the chain by one week - XS4 31 Oct, DS4 7 Nov (after SIT2, so DS5 is not needed for SIT2 fixes), QS4 14 Nov, SS4 21 Nov, PS4 28 Nov (Thanksgiving weekend). G5 moves to Wed 2 Dec, inside the Go/No-Go week; UAT weeks 1-2 run on FPS02 and weeks 3-4 on SPS06.
Plan C |  | Plan C (G3 fails): SS4 and PS4 stay on FPS02 and go live on FPS02. DS5 and QS5 (FPS02 copies) become the delivery line for fixes to SS4 and PS4; DS4 and QS4 stay on SPS06 as the post-go-live upgrade line. Remaining systems are upgraded after hypercare.

## Detail Plan
Detail plan
Reference detail behind each Schedule row. Status follows the Schedule (column B = Schedule ID). R = Responsible, A = Accountable, C = Consulted. Days = calendar days.
ID | Schedule ID | Phase | Workstream | Task | System(s) | Start | End | Responsible | Accountable | Consulted | Depends on | Deliverable / exit | Source | Status | Notes | Days | Overdue | BPMN node
H.1 | 0.2 | P0 Prepare Sandbox & prerequisites | TEC - Technical upgrade (Basis / ECS) | Maintenance Planner transaction 1002693650 for XS4 (target SAP S/4HANA 2023 SPS06, SUM 2.0 SP26) | XS4 | 2026-10-03 | 2026-10-04 | INTL Basis | INTL Basis | SAP ECS | - | Stack file attached to SR 31018471 | MP plan.pdf | Complete | Plan status Completed; created 3 Oct, modified 4 Oct 2026 | 2 |  | -
H.2 | 0.2 | P0 Prepare Sandbox & prerequisites | TEC - Technical upgrade (Basis / ECS) | SR 31018471 raised: Update Software Version of Application (BASIC_1.5.09), XS4, window 9 Oct 02:45-10:45 UTC | XS4 | 2026-10-03 | 2026-10-03 | INTL Basis | INTL Basis | SAP ECS | - | SR validated by ECS 5 Oct | SR log | Complete | SAP for Me also shows Request ID 31018481 for this SR | 1 |  | -
H.3 | 0.3 | P0 Prepare Sandbox & prerequisites | TEC - Technical upgrade (Basis / ECS) | First XS4 update run (SR 31018471) paused at Configuration (12%) by the SI-check: latest version of SAP Note 2502552 needed first; ECS reset SUM on 14 Oct | XS4 | 2026-10-07 | 2026-10-14 | SAP ECS | INTL Basis | INTL Basis | H.2 | SUM reset; SR 31018471 kept for the rerun after the copy (1.03) | SR log | Complete | Lesson applied: notes go into DS4 first (0.02), then XS4 is copied from DS4 (H.5) | 8 |  | -
H.4 | 0.1 | P0 Prepare Sandbox & prerequisites | CODE - Custom code, notes, SPDD/SPAU | Side-effect report for MP 1002693650 triaged: 135 in-scope notes (2 HotNews: 3777415, 3563542), 178 conditional | All | 2026-10-02 | 2026-10-06 | PwC Technical | INTL Basis | PwC Functional | - | SAP_Notes_Side_Effect_Register_SPS06.xlsx | SER | Complete | Register delivered 6 Oct | 5 |  | -
H.5 | 0.4 | P0 Prepare Sandbox & prerequisites | GOV - Governance & SAP engagement | Approach changed: rebuild the Sandbox XS4 as a copy of DS4, then rerun SUM, so the rehearsal runs on Development code and configuration (decision D1) | DS4 > XS4 | 2026-10-15 | 2026-10-15 | INTL Basis | INTL Basis | PwC Technical; SAP ECS | H.3 | Sandbox preparation started | USER | Complete | Sandbox preparation runs from Thu 15 Oct | 1 |  | -
0.01a | 1.1 | P0 Prepare Sandbox & prerequisites | GOV - Governance & SAP engagement | Align the upgrade plan with the PwC Technical team (copy strategy, SPDD/SPAU, notes, ATC, weekend windows) | - | 2026-10-15 | 2026-10-16 | INTL Basis | INTL Basis | PwC Technical | H.5 | PwC Technical aligned | USER | Complete | PwC Technical team aligned (USER, 18 Oct) | 2 |  | -
0.01b | 1.2 | P0 Prepare Sandbox & prerequisites | GOV - Governance & SAP engagement | PwC Functional teams review the plan: stream impacts, regression scope, CFIN/SLT and GTS runbooks, Sandbox test plan | - | 2026-10-16 | 2026-10-19 | PwC Functional | INTL Basis | PwC Technical; INTL Test Lead | 0.01a | Review comments closed | USER | On Track | Review in progress (USER, 18 Oct) | 4 |  | -
0.01 | 1.7 | P0 Prepare Sandbox & prerequisites | GOV - Governance & SAP engagement | Approve plan v4 at Steering: copy strategy (XS4, DS5, QS5), weekend windows, gates G0-G5, Plan B/C | - | 2026-10-20 | 2026-10-20 | INTL Basis | INTL PMO | PwC Technical; PwC Functional | 0.01b | Plan v4 baselined; owners named | USER | Not Started |  | 1 |  | -
0.02 | 1.3 | P0 Prepare Sandbox & prerequisites | TEC - Technical upgrade (Basis / ECS) | Implement the latest versions of SAP Notes 2399707 and 2502552 (TCI) in DS4; release the transport to QS4, SS4, PS4 before each SUM. Check the number: 2502552 (the 12 Oct attempt used 2502662) | DS4 > QS4/SS4/PS4 | 2026-10-15 | 2026-10-16 | INTL Basis | INTL Basis | PwC Technical | H.5 | Notes at latest version in DS4; transport in import queues | UG 2.1, 4.4; SR log | Complete | UG 2.1: a shared transport must be imported into the next system before its upgrade starts | 2 |  | 1, C2
0.03 | 1.6 | P0 Prepare Sandbox & prerequisites | TEC - Technical upgrade (Basis / ECS) | Run SI-check /SDF/RC_START_CHECK (target 2023 SPS06) with "Check Consistency for All" in DS4 and QS4; fix RC 8/12; record RC 7 exemptions | DS4, QS4 | 2026-10-16 | 2026-10-21 | INTL Basis | INTL Basis | PwC Functional | 0.02 | No RC >= 8 open; exemption log | UG 4.4 | On Track | SUM stops at start on RC 12 and before downtime on RC >= 8 | 6 |  | 1, C2
0.04a | 1.4 | P0 Prepare Sandbox & prerequisites | GOV - Governance & SAP engagement | Raise the ECS SR for the system copy DS4 > XS4 (copy Wed 21 - Thu 22 Oct) | DS4 > XS4 | 2026-10-15 | 2026-10-16 | INTL Basis | INTL Basis | SAP ECS | H.5 | Copy SR raised (number in SR Tracker) | USER | Complete | Raised (USER, 18 Oct) | 2 |  | -
0.04 | 1.8 | P0 Prepare Sandbox & prerequisites | GOV - Governance & SAP engagement | Raise the remaining ECS SRs with weekend windows: copies DS4>DS5, QS4>QS5; updates DS4, QS4, SS4, PS4, DS5, QS5 (see SR Tracker); request uptime start time explicitly | All | 2026-10-19 | 2026-10-19 | INTL Basis | INTL Basis | SAP ECS; INTL PMO | 0.05 | SR numbers and confirmed windows in SR Tracker | UG 5; SR log | Not Started | ECS validated SR 31018471 within 2 days and preparation started 36 h before downtime | 1 |  | 2, C1
0.05 | 1.5 | P0 Prepare Sandbox & prerequisites | TEC - Technical upgrade (Basis / ECS) | Maintenance Planner: one transaction per system (DS4, QS4, SS4, PS4, DS5, QS5) with the same target stack as 1002693650; attach each MPID to its SR | All | 2026-10-15 | 2026-10-16 | INTL Basis | INTL Basis | SAP ECS | - | MPID per system; identical target levels | UG 4.2; MP | Complete | Created (USER, 18 Oct); MP 1002693650 covered XS4 only | 2 |  | 2
0.06 | 1.8 | P0 Prepare Sandbox & prerequisites | TEC - Technical upgrade (Basis / ECS) | Ask ECS: are HANA 2.00.089.5 (SPS08) and kernel 916 (in the MP download list) applied inside each SUM window, or do they need DB/OS SRs (DB_1.1.11/12, INFRA_1.6.12) with separate downtime? | All | 2026-10-19 | 2026-10-21 | INTL Basis | INTL Basis | SAP ECS | - | Written ECS answer; windows adjusted if needed | UG 4.3; MP download list | Not Started | UG 4.3: OS and DB patching need a separate downtime | 3 |  | 2, 9
0.07 | 1.10 | P0 Prepare Sandbox & prerequisites | GOV - Governance & SAP engagement | SAP MaxAttention: plan safeguarding review, SI-check and side-effect review, escalation path and weekend coverage for 24 Oct - 22 Nov | - | 2026-10-19 | 2026-10-23 | INTL Basis | INTL Basis | SAP MaxAttention | 0.01b | Review notes; named contacts per weekend | USER | Not Started |  | 5 |  | -
0.08 | 1.10 | P0 Prepare Sandbox & prerequisites | GOV - Governance & SAP engagement | SAP BTP team: confirm actions for AFC, MBC, DRC (Mexico) and Work Zone around each S/4 window; tenant maintenance dates; copies stay disconnected | - | 2026-10-19 | 2026-10-23 | INTL Basis | INTL Basis | SAP BTP team; PwC Functional | 0.01b | BTP checklist per window | USER | Not Started |  | 5 |  | -
0.09 | 1.10 | P0 Prepare Sandbox & prerequisites | GOV - Governance & SAP engagement | Incident and escalation protocol: SAP for Me priorities, ECS SR contacts, weekend on-call rota (Basis onsite/offshore, PwC, ECS, MaxAttention) | - | 2026-10-19 | 2026-10-21 | INTL Basis | INTL Basis | INTL PMO; SAP MaxAttention | - | Rota and contact sheet published | USER | Not Started | Five consecutive weekend windows (24 Oct - 22 Nov) | 3 |  | -
0.10 | 1.9 | P0 Prepare Sandbox & prerequisites | GOV - Governance & SAP engagement | Copy isolation checklist for XS4, DS5, QS5: GTS, SLT/CFIN, AFC, MBC/banks, DRC/PAC, Work Zone, Ariba, OneSource, OpenText, SailPoint, Syniti, e-mail, printers, jobs | XS4, DS5, QS5 | 2026-10-19 | 2026-10-21 | INTL Basis | INTL Basis | PwC Functional; PwC Data Migration; INTL SAP Security | - | Checklist with owner per connection | USER | Not Started | A copy keeps every RFC, port, certificate and job of its source | 3 |  | 4
0.11 | 1.11 | P0 Prepare Sandbox & prerequisites | GOV - Governance & SAP engagement | Vendor outreach: send the e-mails in "Vendor Questions" (OpenText, Thomson Reuters, SailPoint, Syniti); answers due Wed 28 Oct | - | 2026-10-19 | 2026-10-28 | INTL Basis | INTL Basis | PwC Functional; PwC Data Migration; Partner vendors | - | Written answers filed | UG 4.2 | Not Started | UG 4.2: checking third-party add-ons with their vendors is the customer's responsibility | 10 |  | 3
0.12 | 1.17 | P0 Prepare Sandbox & prerequisites | GOV - Governance & SAP engagement | Publish transport windows A-E and the DS5 dual-maintenance rule; defect tag UPG-SPS06 in qTest/ADO | All | 2026-10-21 | 2026-10-23 | INTL Basis | INTL PMO | PwC Technical; INTL Test Lead | 0.01 | Rules briefed to developers and testers | UG 3.1 | Not Started | Release 2 is paused (USER), so dual maintenance covers SIT2, Mock3 and UAT fixes only | 3 |  | 4
0.13 | 1.12 | P0 Prepare Sandbox & prerequisites | CODE - Custom code, notes, SPDD/SPAU | Confirm a customer package (Z*) exists in DS4; list objects created by manual note corrections (passive deletion risk, Note 2513585) | DS4 | 2026-10-19 | 2026-10-22 | PwC Technical | PwC Technical | INTL Basis | - | Package confirmed; objects to rescue listed | UG 3.5 | Not Started | Packages cannot be created during the update | 4 |  | 5
0.14 | 1.12 | P0 Prepare Sandbox & prerequisites | CODE - Custom code, notes, SPDD/SPAU | Custom code check: import Simplification DB (CCMSIDB via SYCM, Note 2241080), ATC run with baseline against 2023 SPS06 in DS4 | DS4 | 2026-10-19 | 2026-10-23 | PwC Technical | PwC Technical | INTL Basis | - | ATC findings list; priority-1 items owned | UG 4.5 | Not Started | Needs SAP_SATC_ADMIN and S_YCM (UG 4.5.1.1) | 5 |  | 5
0.15 | 1.14 | P0 Prepare Sandbox & prerequisites | SEC - Security, GRC, SailPoint | SDMI users: create via SDM_USER in every client of DS4, QS4, SS4, PS4 (Notes 2664638, 2850918), or tell ECS to create them in SUM | All | 2026-10-19 | 2026-10-23 | INTL SAP Security | INTL Basis | SAP ECS | - | SDMI user per client or SR instruction | UG 6.1 | Not Started | Without the user, SDMIs do not start and data is not migrated | 5 |  | 7
0.16 | 1.6 | P0 Prepare Sandbox & prerequisites | TEC - Technical upgrade (Basis / ECS) | ODP jobs: check own variants of ODQ_CLEANUP / ODQ_DAEMON vs technical job definitions (Note 2677355) | DS4, QS4 | 2026-10-19 | 2026-10-22 | INTL Basis | INTL Basis | - | - | Decision recorded | UG 4.7 | On Track |  | 4 |  | -
0.17 | 1.13 | P0 Prepare Sandbox & prerequisites | FIO - Fiori, Work Zone, SAP GUI | Fiori Upgrade Impact Analysis (Fiori apps library) for apps in use: UI content moves FPS02 > FPS03 per MP; list deprecated and successor apps | DS4 | 2026-10-19 | 2026-10-28 | PwC Technical | PwC Technical | INTL Basis | - | App impact list with owner | UG 3.3; MP | Not Started | MP: SAP Fiori for S/4HANA 2023 02 > 03 (02/2025) FPS; FES 2023 stays 02 | 10 |  | 6
0.18 | 1.13 | P0 Prepare Sandbox & prerequisites | FIO - Fiori, Work Zone, SAP GUI | SAP GUI: confirm the deployed GUI version supports the target (Notes 147519, 26417) | - | 2026-10-19 | 2026-10-22 | INTL Basis | INTL Basis | - | - | Confirmation | UG 3.2 | Not Started |  | 4 |  | 6
0.19 | 1.15 | P0 Prepare Sandbox & prerequisites | INT - Integrations (CFIN, GTS, BTP, partners) | CFIN / SLT runbook: suspend and resume replication on QL4 around QS4 and SS4 windows; QL5 repoint plan for QS5; DMIS compatibility confirmed | QL4, QL5 | 2026-10-19 | 2026-10-28 | PwC Functional | PwC Functional | INTL Basis; SAP MaxAttention | - | Runbook approved | USER | Not Started | QL4 = SLT for the N line, QL5 = SLT for N+1 (USER) | 10 |  | 4
0.20 | 1.15 | P0 Prepare Sandbox & prerequisites | INT - Integrations (CFIN, GTS, BTP, partners) | GTS plan: map S/4 client to GTS client (DS4-DG4, QS4-QG4, SS4-QG4/300); plug-in regression scenarios; QG4-300 UAT pause for the SS4 window | DG4, QG4 | 2026-10-19 | 2026-10-23 | PwC Functional | PwC Functional | INTL Basis; INTL PO / IT Leads | - | GTS connection map and test list | USER | Not Started | GTS has no pre-production; QG4 client 300 hosts UAT (USER) | 5 |  | 4
0.21 | 1.16 | P0 Prepare Sandbox & prerequisites | DM - Data migration (Syniti) | Mock3 protection: Mock3 (SS4-100, 19 Oct - 6 Nov) runs fully on FPS02; no SS4 refresh; Syniti connection unchanged; Mock3 fixes via DS5 after 30 Oct | SS4 | 2026-10-19 | 2026-10-20 | PwC Data Migration | INTL PMO | INTL Basis; Partner vendors | - | Mock3 change rules agreed with Syniti | POAP | Not Started | No change to the Mock3 environment is required for the upgrade | 2 |  | -
0.22 | 1.18 | P0 Prepare Sandbox & prerequisites | TST - Testing | Regression set: SIT2 P1 scripts per stream tagged in qTest for the QS4 re-run; Sandbox test plan owners named | - | 2026-10-19 | 2026-10-23 | INTL Test Lead | INTL Test Lead | PwC Functional | - | Tagged P1 set; Sandbox test owners | USER | Not Started | No test automation (USER): all regression is manual | 5 |  | 8
G0 | 1.19 | P0 Prepare Sandbox & prerequisites | GOV - Governance & SAP engagement | GATE G0 - Ready for Sandbox: notes in DS4, SI-check clean, SRs accepted, MPIDs, isolation checklist signed | - | 2026-10-22 | 2026-10-22 | INTL PMO | INTL PMO | INTL Basis; PwC Technical | 0.01, 0.02, 0.03, 0.04a, 0.04, 0.05, 0.06, 0.09, 0.10 | Go for XS4 SUM | UG 2.2 | Not Started |  | 1 |  | G0
1.01 | 2.1 | P1 Sandbox XS4 (copy of DS4) | TEC - Technical upgrade (Basis / ECS) | ECS system copy DS4 > XS4 (XS4 overwritten; SR 31018471 waits for the rerun) | DS4 > XS4 | 2026-10-21 | 2026-10-22 | SAP ECS | INTL Basis | INTL Basis | 0.02, 0.04a | XS4 = DS4 code and configuration | USER | Not Started | Taken from a DS4 backup: no DS4 downtime expected (confirm with ECS) | 2 |  | 10
1.02 | 2.2 | P1 Sandbox XS4 (copy of DS4) | TEC - Technical upgrade (Basis / ECS) | XS4 post-copy: BDLS, disable RFC/ports/certificates per isolation checklist, SCOT, suspend jobs (BTCTRNS1), STMS, lock users | XS4 | 2026-10-22 | 2026-10-22 | INTL Basis | INTL Basis | PwC Functional | 1.01, 0.10 | Isolation evidence | USER | Not Started |  | 1 |  | 10
1.03 | 2.3 | P1 Sandbox XS4 (copy of DS4) | TEC - Technical upgrade (Basis / ECS) | XS4: confirm 2399707 / 2502552 at latest version, SI-check RC < 8, check modifications (SE95) and update the SPDD/SPAU answers in SR 31018471 (were "No"); send the SR back | XS4 | 2026-10-22 | 2026-10-22 | INTL Basis | INTL Basis | PwC Technical | 1.02 | SR 31018471 back with ECS | SR log; UG 3.5, 4.4 | Not Started | The copy brings DS4 modifications into XS4 | 1 |  | 11, C1, C2
1.04 | 2.4 | P1 Sandbox XS4 (copy of DS4) | TEC - Technical upgrade (Basis / ECS) | ECS SUM on XS4: uptime Thu 22 - Fri 23 Oct (dev lock set automatically); downtime Sat 24 Oct (Sun 25 contingency) | XS4 | 2026-10-22 | 2026-10-25 | SAP ECS | INTL Basis | INTL Basis | 1.03, G0 | XS4 on SPS06; runtime and downtime measured | UG 5; SR log | Not Started | First run planned 8 h downtime (SR window) | 4 |  | 11, C3, C7
1.05 | 2.5 | P1 Sandbox XS4 (copy of DS4) | CODE - Custom code, notes, SPDD/SPAU | XS4 SPDD (during SUM), SPAU, then SPAU_ENH: prototype and size the DS4 adjustment | XS4 | 2026-10-24 | 2026-10-26 | PwC Technical | PwC Technical | INTL Basis | 1.04 SS | Worklist and effort for DS4 | UG 3.5 | Not Started | SPAU_ENH only after SPDD/SPAU (UG 3.5) | 3 |  | 11, C5, C8
1.06 | 2.6 | P1 Sandbox XS4 (copy of DS4) | TEC - Technical upgrade (Basis / ECS) | XS4 technical checks: SICK, SM21, ST22, SM37, SM59, STMS, SMICM, SGEN, component levels vs MP, SDM_MON | XS4 | 2026-10-25 | 2026-10-26 | INTL Basis | INTL Basis | SAP ECS | 1.04 | Checklist signed | UG 6.1 | Not Started |  | 2 |  | 11, C9
1.07 | 2.6 | P1 Sandbox XS4 (copy of DS4) | FIO - Fiori, Work Zone, SAP GUI | XS4 Fiori follow-ups: Notes 3336823 and 2902673, /UI2/INVALIDATE_CLIENT_CACHES, /UI2/INVALIDATE_GLOBAL_CACHES, app descriptors if BEC catalogs, SICF /sap/public/bc/its | XS4 | 2026-10-26 | 2026-10-26 | INTL Basis | INTL Basis | PwC Technical | 1.06 | Launchpad and key apps load | UG 6.3 | Not Started | Not in the ECS standard subscription (UG 6.3) | 1 |  | 11, C10
1.08 | 2.7 | P1 Sandbox XS4 (copy of DS4) | SEC - Security, GRC, SailPoint | XS4 SU25 steps 2a/2b, SU24 and role delta; GRC AC 12.0 SP32 post-steps (sync jobs, risk analysis) | XS4 | 2026-10-26 | 2026-10-27 | INTL SAP Security | INTL SAP Security | INTL Basis | 1.06 | Role delta list sized for DS4 | UG 6.4; MP | Not Started | Notes 3809657 and 3782096 (SU25) are in the SER in-scope list | 2 |  | 11, C11
1.09 | 2.8 | P1 Sandbox XS4 (copy of DS4) | CODE - Custom code, notes, SPDD/SPAU | XS4 note bundle trial: HotNews 3777415 and 3563542 first, then High, then Medium in-scope notes | XS4 | 2026-10-26 | 2026-10-28 | PwC Technical | PwC Technical | PwC Functional | 1.05 | Bundle sequence and effort for DS4 | SER | Not Started |  | 3 |  | 11, C8
1.10 | 2.9 | P1 Sandbox XS4 (copy of DS4) | TST - Testing | Execute the Sandbox Test Plan (30 tests; see sheet); log defects UPG-SPS06 | XS4 | 2026-10-26 | 2026-10-28 | PwC Functional | INTL Test Lead | INTL Basis; INTL SAP Security | 1.06, 1.07 | All "Yes" tests passed; each "Partial" has a named follow-up | USER | Not Started |  | 3 |  | 12, C13
1.11 | 2.10 | P1 Sandbox XS4 (copy of DS4) | TEC - Technical upgrade (Basis / ECS) | Lessons learned; confirm downtime per system with ECS (DS4, QS4, SS4, PS4 windows) | XS4 | 2026-10-28 | 2026-10-28 | INTL Basis | INTL Basis | SAP ECS | 1.04 | Windows reconfirmed | USER | Not Started |  | 1 |  | 11
G1 | 2.11 | P1 Sandbox XS4 (copy of DS4) | GOV - Governance & SAP engagement | GATE G1 - Sandbox sign-off: go for DS4 (Thu 29 Oct 12:00 CT, before DS4 uptime starts) | - | 2026-10-29 | 2026-10-29 | INTL PMO | INTL PMO | INTL Basis; PwC Technical; INTL Test Lead | 1.05-1.11 | Go for DS4 or Plan B | USER | Not Started |  | 1 |  | G1
2.01 | 3.1 | P2 Development DS4 + DS5 copy | TEC - Technical upgrade (Basis / ECS) | ECS system copy DS4 > DS5 (temporary Dev on FPS02 = fallback) | DS4 > DS5 | 2026-10-27 | 2026-10-28 | SAP ECS | INTL Basis | INTL Basis | 0.04 | DS5 = DS4 at copy time | UG 3.1 | Not Started | SAP temporary-landscape pattern (UG 3.1) | 2 |  | 13
2.02 | 3.2 | P2 Development DS4 + DS5 copy | TEC - Technical upgrade (Basis / ECS) | DS5 post-copy: BDLS, isolation (no DG4, no SLT, no BTP), add to TMS with routes DS5 > QS4/SS4 (FPS02 fixes) and DS5 > QS5; re-import DS4 transports released after the copy point | DS5 | 2026-10-28 | 2026-10-29 | INTL Basis | INTL Basis | PwC Technical | 2.01 | DS5 open for fixes Fri 30 Oct | UG 3.1 | Not Started |  | 2 |  | 13
2.03 | 3.3 | P2 Development DS4 + DS5 copy | GOV - Governance & SAP engagement | DS4 release cut-off: SIT2 fixes released and imported to QS4 by Fri 30 Oct 12:00 CT | DS4 > QS4 | 2026-10-30 | 2026-10-30 | PwC Technical | INTL PMO | INTL Basis | 0.12 | Nothing open in DS4 | UG 3.1 | Not Started |  | 1 |  | 14
2.04 | 3.4 | P2 Development DS4 + DS5 copy | TEC - Technical upgrade (Basis / ECS) | ECS SUM on DS4: uptime Fri 30 Oct (dev lock); downtime Sat 31 Oct (Sun 1 Nov contingency) | DS4 | 2026-10-30 | 2026-11-01 | SAP ECS | INTL Basis | INTL Basis | G1 | DS4 on SPS06 | UG 5 | Not Started | Weekend window (USER) | 3 |  | 14, C3, C7
2.05 | 3.5 | P2 Development DS4 + DS5 copy | CODE - Custom code, notes, SPDD/SPAU | DS4 SPDD during SUM (transport ID <SID>K9xxxxx into SR), then SPAU and SPAU_ENH; release both adjustment transports for reuse | DS4 | 2026-10-31 | 2026-11-02 | PwC Technical | PwC Technical | INTL Basis; SAP ECS | 2.04 SS | SPDD + SPAU transports for QS4, SS4, PS4, DS5, QS5 | UG 3.5; SR form | Not Started | Subsequent systems reuse them in phase ADJUSTPRP | 3 |  | 14, C5, C8
2.06 | 3.6 | P2 Development DS4 + DS5 copy | TEC - Technical upgrade (Basis / ECS) | DS4 post-processing: technical checks, Fiori follow-ups, SDM_MON, Work Zone dev content | DS4 | 2026-11-01 | 2026-11-02 | INTL Basis | INTL Basis | PwC Technical | 2.04 | Checklist signed | UG 6.1, 6.3 | Not Started |  | 2 |  | 14, C9, C10
2.07 | 3.7 | P2 Development DS4 + DS5 copy | SEC - Security, GRC, SailPoint | DS4 SU25 2a/2b, SU24, PFCG roles, GRC post-steps; role transports released | DS4 | 2026-11-02 | 2026-11-03 | INTL SAP Security | INTL SAP Security | INTL Basis | 2.06 | Role transports | UG 6.4 | Not Started |  | 2 |  | 14, C11
2.08 | 3.8 | P2 Development DS4 + DS5 copy | CODE - Custom code, notes, SPDD/SPAU | DS4 note bundle (SNOTE) in transports; ATC re-run on SPS06; RICEFW unit tests (interfaces, enhancements, forms, workflows, custom Fiori) | DS4 | 2026-11-02 | 2026-11-04 | PwC Technical | PwC Technical | PwC Functional | 2.05 | Note transports; unit-test evidence; zero priority-1 ATC findings | SER; UG 4.5 | Not Started |  | 3 |  | 14, C8
2.09 | 3.9 | P2 Development DS4 + DS5 copy | INT - Integrations (CFIN, GTS, BTP, partners) | DS4 integration unit checks with dev endpoints: DG4, AFC, MBC, DRC, Work Zone, SailPoint (dev), OpenText | DS4 | 2026-11-03 | 2026-11-04 | PwC Functional | PwC Functional | INTL Basis; SAP BTP team | 2.06 | Connections tested | USER | Not Started |  | 2 |  | 14, C12
2.10 | 3.10 | P2 Development DS4 + DS5 copy | GOV - Governance & SAP engagement | Dual maintenance: SIT2, Mock3 and UAT fixes built in DS5 (FPS02) for QS4/SS4, and re-applied in DS4 (SPS06); retrofit log reconciled daily | DS5, DS4 | 2026-10-30 | 2026-11-13 | PwC Technical | PwC Technical | INTL Basis | 2.02 | Retrofit log: every DS5 change also in DS4 | UG 3.1 | Not Started | Ends when SS4 is on SPS06 (14 Nov) | 15 |  | 15
G2 | 3.11 | P2 Development DS4 + DS5 copy | GOV - Governance & SAP engagement | GATE G2 - Dev ready: adjustment, note and role transports released; no blocking unit-test failure | - | 2026-11-04 | 2026-11-04 | INTL PMO | INTL PMO | PwC Technical; INTL Basis | 2.05-2.09 | Go for QS4 | UG 3.5 | Not Started |  | 1 |  | G2
3.01 | 4.1 | P3 QA QS4 + QS5 copy | TEC - Technical upgrade (Basis / ECS) | ECS system copy QS4 > QS5 from backup (QS4 stays in SIT2) | QS4 > QS5 | 2026-11-04 | 2026-11-05 | SAP ECS | INTL Basis | INTL Basis | 0.04 | QS5 = QS4 (FPS02) = fallback QA | UG 3.1 | Not Started |  | 2 |  | 16
3.02 | 4.2 | P3 QA QS4 + QS5 copy | TEC - Technical upgrade (Basis / ECS) | QS5 post-copy: BDLS, isolation (no QG4, no QL4, no BTP, no PAC/banks), TMS route DS5 > QS5 | QS5 | 2026-11-05 | 2026-11-06 | INTL Basis | INTL Basis | PwC Functional | 3.01 | Isolation evidence | USER | Not Started |  | 2 |  | 16
3.03 | 4.3 | P3 QA QS4 + QS5 copy | TST - Testing | SIT2 exit (6 Nov); FPS02 results frozen in qTest as the baseline for the SPS06 re-run | QS4-200 | 2026-11-06 | 2026-11-06 | INTL Test Lead | INTL Test Lead | PwC Functional | - | Baseline frozen | POAP | Not Started | Transport imports into QS4 end Thu 5 Nov (SUM uptime) | 1 |  | 18
3.04 | 4.4 | P3 QA QS4 + QS5 copy | INT - Integrations (CFIN, GTS, BTP, partners) | QS4 ramp-down Fri 6 Nov: suspend SLT (QL4), drain qRFC/AIF/IDoc, pause GTS transfers, SailPoint, AFC tasks; stop jobs, lock users, clear update errors | QS4, QL4, QG4 | 2026-11-06 | 2026-11-06 | INTL Basis | INTL Basis | PwC Functional; INTL SAP Security | 0.19, 0.20 | Hand-over to ECS before the downtime (Sat 7 Nov) | UG 5 | Not Started | Runs during SUM uptime, before the downtime | 1 |  | 17, C6
3.05 | 4.5 | P3 QA QS4 + QS5 copy | TEC - Technical upgrade (Basis / ECS) | ECS SUM on QS4 (clients 100, 200): uptime Thu 5 - Fri 6 Nov; downtime Sat 7 Nov (Sun 8 contingency); adjustment transports via ADJUSTPRP | QS4 | 2026-11-05 | 2026-11-08 | SAP ECS | INTL Basis | INTL Basis | G2 | QS4 on SPS06 | UG 3.5, 5 | Not Started | Straight after SIT2 (USER option 1) | 4 |  | 17, C3, C7
3.06 | 4.6 | P3 QA QS4 + QS5 copy | TEC - Technical upgrade (Basis / ECS) | QS4 post-processing: checks, note and role transports, Fiori follow-ups, SDM_MON, Work Zone content re-sync | QS4 | 2026-11-08 | 2026-11-08 | INTL Basis | INTL Basis | INTL SAP Security; PwC Technical | 3.05 | Checklist signed | UG 6 | Not Started |  | 1 |  | 17, C9, C10, C11
3.07 | 4.7 | P3 QA QS4 + QS5 copy | INT - Integrations (CFIN, GTS, BTP, partners) | QS4 resume: SLT replication from QL4 and CFIN reconciliation (AIF); GTS retransfer check; SailPoint aggregation; BTP connections | QS4, QL4, QG4 | 2026-11-08 | 2026-11-09 | PwC Functional | PwC Functional | INTL Basis; SAP BTP team | 3.06 | Replication and integrations healthy | USER | Not Started |  | 2 |  | 17, C12
3.08 | 4.8 | P3 QA QS4 + QS5 copy | TST - Testing | QS4-200 SPS06 regression: re-run P1 scripts per stream (STP/Ariba, OTC, RTR, ITD, CFIN, GTS, VIM, AFC, DRC MX, MBC, OneSource with TR onsite w/c 9 Nov) | QS4-200 | 2026-11-09 | 2026-11-12 | PwC Functional | INTL Test Lead | INTL PO / IT Leads; Partner vendors | 3.07, 3.03 | P1 pass >= 95%, no open Sev1/Sev2 | USER | Not Started | TR is onsite w/c 9 Nov (POAP) | 4 |  | 18, C13
3.09 | 4.9 | P3 QA QS4 + QS5 copy | SEC - Security, GRC, SailPoint | QS4 security regression: negative tests, GRC AC checks, SailPoint provisioning, Work Zone role collections | QS4 | 2026-11-09 | 2026-11-11 | INTL SAP Security | INTL SAP Security | INTL Basis | 3.06 | Role test evidence | UG 6.4 | Not Started |  | 3 |  | 18, C13
3.10 | 4.10 | P3 QA QS4 + QS5 copy | DM - Data migration (Syniti) | Migration validation on SPS06: Syniti sample loads per object into QS4-100; migration notes 3805046, 3791609, 3789840 checked | QS4-100 | 2026-11-09 | 2026-11-11 | PwC Data Migration | PwC Data Migration | Partner vendors; INTL Basis | 3.06 | Objects load on SPS06 | SER | Not Started | Cutover loads (7 Dec) run on SPS06 | 3 |  | 18
3.11 | 4.11 | P3 QA QS4 + QS5 copy | INT - Integrations (CFIN, GTS, BTP, partners) | QS5 fallback readiness: QL5 repointed to QS5; CFIN smoke on QS5 (only needed for Plan C) | QS5, QL5 | 2026-11-09 | 2026-11-11 | PwC Functional | PwC Functional | INTL Basis | 3.02 | QS5 usable as fallback QA | USER | Not Started |  | 3 |  | 16
3.12 | 4.12 | P3 QA QS4 + QS5 copy | TST - Testing | Defect triage against the FPS02 baseline; fix and retest UPG-SPS06 defects (fixes in DS4 now that DS4 and QS4 are both SPS06) | DS4 > QS4 | 2026-11-09 | 2026-11-12 | PwC Functional | INTL Test Lead | PwC Technical | 3.08 SS | Defect log closed or accepted | UG 3.1 | Not Started |  | 4 |  | 18, C14
G3 | 4.13 | P3 QA QS4 + QS5 copy | GOV - Governance & SAP engagement | GATE G3 - Go for SS4: P1 >= 95%, zero open Sev1/Sev2 upgrade defects, CFIN/GTS/BTP green, security passed; otherwise Plan C | - | 2026-11-12 | 2026-11-12 | INTL PMO | INTL PMO | INTL Basis; INTL Test Lead; PwC Functional | 3.05-3.12 | Go / Plan C | USER | Not Started |  | 1 |  | G3
4.01 | 5.1 | P4 Pre-production SS4 | TST - Testing | UAT week 1 on SS4 (FPS02) as planned; UAT fixes for SS4 via DS5 until SS4 is upgraded; SS4 imports end Thu 12 Nov | SS4-100 | 2026-11-09 | 2026-11-13 | INTL PO / IT Leads | INTL Test Lead | PwC Functional | - | UAT week 1 results | POAP | Not Started |  | 5 |  | 20
4.02 | 5.2 | P4 Pre-production SS4 | INT - Integrations (CFIN, GTS, BTP, partners) | SS4 ramp-down Fri 13 Nov: SLT, GTS QG4-300, SailPoint, AFC, MBC, DRC queues, OneSource, jobs, users | SS4, QG4-300 | 2026-11-13 | 2026-11-13 | INTL Basis | INTL Basis | PwC Functional; INTL SAP Security | G3 | Hand-over to ECS | UG 5 | Not Started |  | 1 |  | 19, C6
4.03 | 5.3 | P4 Pre-production SS4 | TEC - Technical upgrade (Basis / ECS) | ECS SUM on SS4: uptime Thu 12 - Fri 13 Nov; downtime Fri night 13 - Sat 14 Nov (Sun 15 contingency) | SS4 | 2026-11-12 | 2026-11-15 | SAP ECS | INTL Basis | INTL Basis | G3 | SS4 on SPS06 | UG 5 | Not Started | Weekend window, no UAT weekday lost (USER) | 4 |  | 19, C3, C7
4.04 | 5.4 | P4 Pre-production SS4 | TEC - Technical upgrade (Basis / ECS) | SS4 post-processing: checks, transports, Fiori follow-ups, SDM_MON, Work Zone UAT content, roles | SS4 | 2026-11-14 | 2026-11-15 | INTL Basis | INTL Basis | INTL SAP Security; PwC Technical | 4.03 SS | Checklist signed | UG 6 | Not Started |  | 2 |  | 19, C9, C10, C11
4.05 | 5.5 | P4 Pre-production SS4 | INT - Integrations (CFIN, GTS, BTP, partners) | SS4 resume and verify: SLT/CFIN, GTS QG4-300 end-to-end, AFC, MBC, DRC, OneSource, SailPoint, legacy interfaces | SS4, QG4-300 | 2026-11-15 | 2026-11-15 | PwC Functional | PwC Functional | INTL Basis; SAP BTP team | 4.04 | Integrations green before testers return | USER | Not Started |  | 1 |  | 19, C12
4.06 | 5.6 | P4 Pre-production SS4 | TST - Testing | Technical smoke Mon 16 Nov 08:00; UAT weeks 2-4 continue on SPS06 (16 Nov - 4 Dec) | SS4-100 | 2026-11-16 | 2026-12-04 | INTL PO / IT Leads | INTL Test Lead | PwC Functional | 4.05 | UAT exit (4 Dec) | POAP | Not Started |  | 19 |  | 20, C13
4.07 | 5.7 | P4 Pre-production SS4 | TST - Testing | Performance delta check on SS4 SPS06: key scenarios from the FPS02 performance test (14 Oct - 6 Nov) | SS4-100 | 2026-11-16 | 2026-11-18 | INTL Test Lead | INTL Test Lead | INTL Basis; SAP MaxAttention | 4.05 | No material degradation | POAP | Not Started |  | 3 |  | 20
G4 | 5.8 | P4 Pre-production SS4 | GOV - Governance & SAP engagement | GATE G4 - Go for PS4: SS4 stable, performance delta acceptable, no upgrade blockers; start DS5/QS5 realignment | - | 2026-11-19 | 2026-11-19 | INTL PMO | INTL PMO | INTL Basis; INTL Test Lead | 4.04, 4.05, 4.07 | Go for PS4 | USER | Not Started |  | 1 |  | G4
5.01 | 6.1 | P5 Production PS4 | TEC - Technical upgrade (Basis / ECS) | PS4 import hold while PS4 is FPS02 (from 14 Nov until PS4 post-processing) | PS4 | 2026-11-14 | 2026-11-22 | INTL Basis | INTL Basis | INTL PMO | 4.03 SS | Queue held, then released | UG 3.1 | Not Started |  | 9 |  | 21
5.02 | 6.2 | P5 Production PS4 | TEC - Technical upgrade (Basis / ECS) | ECS SUM on PS4: uptime Thu 19 - Fri 20 Nov; downtime Fri night 20 - Sat 21 Nov (Sun 22 contingency); pre-upgrade backup | PS4 | 2026-11-19 | 2026-11-22 | SAP ECS | INTL Basis | INTL Basis; SAP MaxAttention | G4 | PS4 on SPS06 | UG 5 | Not Started | Before cutover starts (7 Dec) | 4 |  | 21, C3, C7
5.03 | 6.3 | P5 Production PS4 | TEC - Technical upgrade (Basis / ECS) | PS4 post-processing: checks, release queued transports, roles, Fiori follow-ups, Work Zone production content, SDM_MON | PS4 | 2026-11-21 | 2026-11-23 | INTL Basis | INTL Basis | INTL SAP Security | 5.02 SS | Technical verification signed | UG 6 | Not Started |  | 3 |  | 21, C9, C10, C11
5.04 | 6.4 | P5 Production PS4 | INT - Integrations (CFIN, GTS, BTP, partners) | PS4 connection checks for integrations already configured (BTP production tenants, Cloud Connector, SLT, GTS) - no business data before cutover | PS4 | 2026-11-23 | 2026-11-23 | INTL Basis | INTL Basis | PwC Functional; SAP BTP team | 5.03 | Connections verified | POAP | Not Started |  | 1 |  | 21, C12
G5 | 6.5 | P5 Production PS4 | GOV - Governance & SAP engagement | GATE G5 - Upgrade closed: PS4 verified, UAT clean on SPS06; feeds Go/No-Go (30 Nov - 4 Dec) | - | 2026-11-25 | 2026-11-25 | INTL PMO | INTL PMO | INTL Basis; INTL Test Lead | 5.03, 5.04 | Upgrade closed | POAP | Not Started | Thanksgiving is Thu 26 Nov | 1 |  | G5
6.01 | 7.1 | P6 N+1 realign DS5 / QS5 | TEC - Technical upgrade (Basis / ECS) | ECS SUM on DS5 (adjustment transports reused) | DS5 | 2026-12-01 | 2026-12-01 | SAP ECS | INTL Basis | INTL Basis | G4 | DS5 on SPS06 | USER | Not Started | DS5/QS5 kept as fallback until G4 (USER) | 1 |  | 22, C3, C7
6.02 | 7.2 | P6 N+1 realign DS5 / QS5 | TEC - Technical upgrade (Basis / ECS) | ECS SUM on QS5 | QS5 | 2026-12-03 | 2026-12-03 | SAP ECS | INTL Basis | INTL Basis | 6.01 | QS5 on SPS06 | USER | Not Started |  | 1 |  | 22, C3, C7
6.03 | 7.3 | P6 N+1 realign DS5 / QS5 | TEC - Technical upgrade (Basis / ECS) | DS5/QS5 post-processing; retrofit DS4 changes since the copy; reconnect N+1 integrations (QL5 etc.) per N+1 design | DS5, QS5 | 2026-12-01 | 2026-12-04 | INTL Basis | INTL Basis | PwC Technical; PwC Functional | 6.01 | N+1 line equals PS4 level | UG 3.1 | Not Started | Release 2 paused (USER) | 4 |  | 22
7.01 | 8.3 | P7 Stabilize to go-live | CODE - Custom code, notes, SPDD/SPAU | Side-effect watch: re-run the side-effect report weekly until go-live | All | 2026-11-23 | 2027-01-01 | PwC Technical | INTL Basis | SAP MaxAttention | 5.03 | Watch log | SER | Not Started |  | 40 |  | 23
7.02 | 8.4 | P7 Stabilize to go-live | TST - Testing | Cutover on SPS06 (7 - 31 Dec): SPS06 items in the cutover checklist | PS4 | 2026-12-07 | 2026-12-31 | INTL PMO | INTL PMO | PwC Data Migration; INTL Basis | G5 | Checklist | POAP | Not Started |  | 25 |  | -
7.03 | 8.1 | P7 Stabilize to go-live | TEC - Technical upgrade (Basis / ECS) | SDMI completion: SDM_MON shows all SDMIs finished in all clients of every upgraded system | All | 2026-11-23 | 2026-12-04 | INTL Basis | INTL Basis | SAP ECS | 5.02 | Screenshot per system | UG 6.1 | Not Started | All SDMIs must finish before the next upgrade | 12 |  | 23, C9
7.04 | 8.2 | P7 Stabilize to go-live | GOV - Governance & SAP engagement | Upgrade close-out: lessons learned, SR closure, MaxAttention summary | - | 2026-11-30 | 2026-12-04 | INTL Basis | INTL PMO | SAP MaxAttention; PwC Technical | G5 | Close-out report | USER | Not Started |  | 5 |  | -
7.05 | 8.5 | P7 Stabilize to go-live | TEC - Technical upgrade (Basis / ECS) | Obsolete data handling (SODH, Note 3335020): not before go-live; plan after hypercare | PS4 | 2027-01-01 | 2027-01-01 | INTL Basis | INTL Basis | PwC Functional | - | Decision recorded | UG 6.2 | Not Started | PS4 holds no business data before cutover | 1 |  | -
Note on O4: Follows the Schedule row in column B. Update status on the Schedule tab.

## Systems
System landscape
N = go-live line, N+1 = DS5/QS5 copies (fallback until G4). Update "Current level" to SPS06 when a system is done.
SID | Role | Line | Clients | Current level | Target level | Copy | Upgrade window | SR | Connected to | Status | Notes | Copy date | Downtime date
XS4 | Sandbox (rehearsal) | Sandbox | tbc | FPS02 | SPS06 | Copy of DS4, 21-22 Oct | Sat 24 Oct | SR 31018471 | Isolated after copy | On Track | Prep on track since 15 Oct; copy SR raised; SR 31018471 reused for the SUM rerun | 2026-10-21 | 2026-10-24
DS4 | Development | N (go-live line) | 110 | FPS02 | SPS06 | - | Sat 31 Oct | tbc | DG4; dev BTP tenants | Not Started | Dev lock from Fri 30 Oct (SUM uptime) |  | 2026-10-31
DS5 | Temporary Dev / N+1 Dev | N+1 (fallback) | tbc | FPS02 | SPS06 (1 Dec) | Copy of DS4, 27-28 Oct | Tue 1 Dec | tbc | Isolated; TMS to QS4/SS4 (FPS02 fixes) and QS5 | Not Started | Fallback until G4 | 2026-10-27 | 2026-12-01
QS4 | QA (SIT) | N (go-live line) | 100, 200 | FPS02 | SPS06 | - | Sat 7 Nov | tbc | QG4; QL4 (SLT); QA BTP tenants; legacy | Not Started | SIT2 in client 200 until 6 Nov |  | 2026-11-07
QS5 | Temporary QA / N+1 QA | N+1 (fallback) | tbc | FPS02 | SPS06 (3 Dec) | Copy of QS4, 4-5 Nov | Thu 3 Dec | tbc | Isolated; QL5 (SLT) repoint | Not Started | Fallback until G4 | 2026-11-04 | 2026-12-03
SS4 | Pre-production (UAT) | N (go-live line) | 100 | FPS02 | SPS06 | - | Fri-Sat 13-14 Nov | tbc | QG4-300 (GTS UAT); SLT; BTP; legacy | Not Started | Mock3 + performance test to 6 Nov; UAT from 9 Nov |  | 2026-11-14
PS4 | Production | N (go-live line) | tbc | FPS02 | SPS06 | - | Fri-Sat 20-21 Nov | tbc | Production endpoints (pre-cutover) | Not Started | Cutover 7-31 Dec; go-live 1 Jan 2027 |  | 2026-11-21
QL4 | SLT server for Central Finance | N | - | not changed | not changed | - | Suspend/resume around QS4 and SS4 | - | QS4 (CFIN) | Not Started | Confirm DMIS compatibility
QL5 | SLT server for Central Finance | N+1 | - | not changed | not changed | - | Repoint to QS5 after copy | - | QS5 (CFIN) | Not Started
DG4 | SAP GTS Development | GTS | tbc | not changed | not changed | - | Paused during DS4 window | - | DS4 | Not Started | GTS release to confirm
QG4 | SAP GTS QA (client 300 = UAT) | GTS | 300 (UAT) + SIT client tbc | not changed | not changed | - | Paused during QS4 and SS4 windows | - | QS4; SS4 (client 300) | Not Started | No GTS pre-production exists
BTP | AFC, MBC, DRC (MX), Work Zone Standard | SaaS | - | SAP-managed | SAP-managed | - | Connection checks after each window | - | DS4, QS4, SS4, PS4 | Not Started | Copies stay disconnected

## SR Tracker
SAP ECS service requests
Service identifiers from the SR form and the Upgrade Guide (UG 2.1, 3.5, 4.2, 4.3). Copy SR identifiers to be confirmed from the ECS catalog.
SR number | System | Service identifier | Purpose | Window | SAP status | Status | Owner | Next action | Raised on
31018471 | XS4 | BASIC_1.5.09 Update Software Version of Application (non-chargeable) | XS4 FPS02 > SPS06, MP 1002693650 | New: uptime Thu 22 - Fri 23 Oct, downtime Sat 24 Oct (first window was 9 Oct 02:45-10:45 UTC) | Customer Action (14 Oct) | On Track | INTL Basis | After copy (1.01) and note check (1.03): update SPDD/SPAU answers and new window; send back to ECS | 2026-10-03
raised (add no.) | DS4 > XS4 | System copy (identifier per ECS catalog) | Sandbox equal to current DS4 scope | Wed 21 - Thu 22 Oct | - | On Track | INTL Basis | Confirm the copy start time with ECS
to raise | DS4 > DS5 | System copy (per ECS catalog) | Temporary Dev on FPS02 (fallback) | Tue 27 - Wed 28 Oct | - | Not Started | INTL Basis | Raise Mon 19 Oct
to raise | QS4 > QS5 | System copy (per ECS catalog) | Temporary QA on FPS02 (fallback) | Wed 4 - Thu 5 Nov | - | Not Started | INTL Basis | Raise Mon 19 Oct
to raise | DS4 | BASIC_1.5.09 | DS4 FPS02 > SPS06 (SPDD/SPAU here) | Uptime Fri 30 Oct; downtime Sat 31 Oct | - | Not Started | INTL Basis | Raise Mon 19 Oct with DS4 MPID
to raise | QS4 | BASIC_1.5.09 | QS4 FPS02 > SPS06 (reuse DS4 transports) | Downtime Sat 7 Nov | - | Not Started | INTL Basis | Raise Mon 19 Oct; add SPDD/SPAU transport IDs after DS4
to raise | SS4 | BASIC_1.5.09 | SS4 FPS02 > SPS06 | Downtime Fri night 13 - Sat 14 Nov | - | Not Started | INTL Basis | Raise Mon 19 Oct
to raise | PS4 | BASIC_1.5.09 | PS4 FPS02 > SPS06 | Downtime Fri night 20 - Sat 21 Nov | - | Not Started | INTL Basis | Raise Mon 19 Oct
to raise | DS5 | BASIC_1.5.09 | DS5 FPS02 > SPS06 after G4 | Tue 1 Dec | - | Not Started | INTL Basis | Raise after G4 (19 Nov)
to raise | QS5 | BASIC_1.5.09 | QS5 FPS02 > SPS06 after G4 | Thu 3 Dec | - | Not Started | INTL Basis | Raise after G4 (19 Nov)
if needed | All | DB_1.1.11 / DB_1.1.12 (HANA), INFRA_1.6.12 (OS) | Only if ECS requires separate DB/OS updates (task 0.06) | Separate downtime (UG 4.3) | - | Not Started | INTL Basis | Decide on ECS answer
optional | All | TO_NWABAP_1.5.08 (billable upgrade package) | ECS performs SPDD/SPAU steps | - | - | Not Started | INTL Basis | Decision D-O5
optional | All | BASIC_1.5.03 (billable CAS) | ECS performs application notes or Fiori follow-ups | - | - | Not Started | INTL Basis | Decision D-O4

## RAID
Risks, assumptions, issues, decisions
Rating: High / Medium / Low. Status: Open / Closed.
ID | Type | Description | Impact | Rating | Mitigation / response | Owner | Due | Status
I1 | Issue | First XS4 update run paused by the SI-check (latest version of Note 2502552 needed); ECS reset SUM 14 Oct | Sandbox rehearsal rescheduled to Sat 24 Oct | Low | Closed by the approach change on 15 Oct (D1): notes in DS4 (0.02, done), copy DS4 to XS4 (1.01), SI-check, SR 31018471 back to ECS (1.03) | INTL Basis | 2026-10-15 | Closed
I2 | Issue | Maintenance Plan 1002693650 covered XS4 only | No stack file for other systems | Low | Closed: MP transaction per system created (0.05, done) | INTL Basis | 2026-10-16 | Closed
I3 | Issue | Note number check in SR updates (2502662 was entered instead of 2502552 on 12 Oct) | Wrong note attempted | Low | Closed: four-eyes check of note numbers in every SR update | INTL Basis | 2026-10-15 | Closed
R1 | Risk | ECS cannot schedule three copies and six SUM runs on the requested dates | Chain slips | High | Copy SR for XS4 raised; remaining SRs Mon 19 Oct; MaxAttention escalation; Plan B (+1 week) | INTL Basis | 2026-10-23 | Open
R2 | Risk | SAP updates Note 2502552 between systems and the SI-check pauses SUM | Window lost | High | Check the note version 48 h before each window; re-run SI-check | INTL Basis | 2026-11-20 | Open
R3 | Risk | Copies (XS4, DS5, QS5) send data to GTS, SLT, MBC/banks, DRC/PAC, Ariba, OneSource, SailPoint | Duplicate or false business messages | High | Isolation checklist (0.10) executed and evidenced before any user logs on | INTL Basis | 2026-11-06 | Open
R4 | Risk | Five consecutive weekend windows (24 Oct - 22 Nov) for a 3-person Basis team | Fatigue, errors | High | Rota across onsite/offshore; ECS + MaxAttention cover; no Basis change work on weekdays after a window | INTL Basis | 2026-10-21 | Open
R5 | Risk | Dual maintenance DS5/DS4: a fix applied in one system only | Regression at cutover | Medium | Retrofit log reconciled daily (2.10); Release 2 paused | PwC Technical | 2026-11-13 | Open
R6 | Risk | QS4 regression window is 4 days (9-12 Nov) | Defects reach SS4 | High | P1 scripts only; FPS02 baseline; TR onsite the same week; Sandbox evidence first | INTL Test Lead | 2026-11-12 | Open
R7 | Risk | UAT week 1 on FPS02, weeks 2-4 on SPS06 | Defect attribution | Medium | Tag UPG-SPS06; compare against QS4 results | INTL Test Lead | 2026-11-16 | Open
R8 | Risk | Mock3 runs on FPS02; cutover loads run on SPS06 | Load failures at cutover | Medium | Syniti sample loads on SPS06 in QS4-100 (3.10); Syniti questions | PwC Data Migration | 2026-11-11 | Open
R9 | Risk | Partner confirmations (OpenText, SailPoint, Syniti, TR) not received before G1 / G3 | Unsupported combination | High | E-mails sent 19-20 Oct; answers due 28 Oct; hold at G3 if open | INTL Basis | 2026-10-28 | Open
R10 | Risk | GTS has no pre-production: the SS4 window interrupts GTS UAT in QG4-300 | GTS UAT loses time | Medium | Weekend window; GTS end-to-end proven in QS4 first (9-12 Nov) | PwC Functional (GTS) | 2026-11-16 | Open
R11 | Risk | ECS requires a separate HANA/OS downtime | Extra windows | Medium | Ask now (0.06); combine with copy windows where possible | INTL Basis | 2026-10-21 | Open
R12 | Risk | Fiori UI content FPS03 deprecates apps in use | Missing tiles | Medium | Impact analysis (0.17); successor apps in roles | PwC Technical | 2026-10-28 | Open
R13 | Risk | CFIN replication backlog after resume | Reconciliation delay | Medium | Drain before; reconcile after (3.07, 4.05) | PwC Functional (CFIN) | 2026-11-15 | Open
R14 | Risk | New side effects published after SPS06 is installed | Unexpected defects | Low | Weekly side-effect watch (7.01) | PwC Technical | 2027-01-01 | Open
A1 | Assumption | Project dates per Plan on a Page (9/21) and user updates: SIT2 28 Sep - 6 Nov (QS4-200); Mock3 19 Oct - 6 Nov and performance test 14 Oct - 6 Nov (SS4-100); UAT 9 Nov - 4 Dec (SS4-100); Go/No-Go at UAT end; cutover 7 - 31 Dec; go-live 1 Jan 2027 | - | - | - | INTL PMO |  | Open
A2 | Assumption | Downtime per system is about 8 h (XS4 SR window); actual duration is measured in XS4 (1.11) | - | - | - | INTL Basis |  | Open
A3 | Assumption | Copies are taken from backups, so DS4 and QS4 stay available during the copy (ECS to confirm) | - | - | - | INTL Basis |  | Open
A4 | Assumption | No test automation; all regression is manual (USER) | - | - | - | INTL Test Lead |  | Open
A5 | Assumption | Release 2 is paused (USER); N+1 activity is limited to fallback and fixes | - | - | - | INTL PMO |  | Open
A6 | Assumption | PS4 holds no business data before cutover (7 Dec) | - | - | - | INTL PMO |  | Open
A7 | Assumption | Times are US Central (SR log shows America/Chicago); ECS windows are agreed in UTC | - | - | - | INTL Basis |  | Open
D1 | Decision | Copy DS4 to XS4, then rerun SUM on XS4; Sandbox preparation from Thu 15 Oct (USER) | - | - | - | Girish Ogirala | 2026-10-15 | Closed
D2 | Decision | Copy DS4 > DS5 and QS4 > QS5, then upgrade DS4 and QS4 (SAP temporary landscape, UG 3.1) (USER) | - | - | - | Girish Ogirala | 2026-10-17 | Closed
D3 | Decision | Weekend windows: DS4 31 Oct, QS4 7 Nov, SS4 13-14 Nov, PS4 20-21 Nov (USER option 1 + weekend) | - | - | - | Girish Ogirala | 2026-10-17 | Closed
D4 | Decision | DS5/QS5 stay FPS02 as fallback until G4, then upgrade w/c 30 Nov (USER) | - | - | - | Girish Ogirala | 2026-10-17 | Closed
D5 | Decision | No test automation (USER) | - | - | - | Girish Ogirala | 2026-10-17 | Closed
D-O1 | Decision | OPEN: SDMI in uptime (default, recommended) or forced in downtime (must be stated in the SR, UG 6.1) | - | Medium | Recommend default uptime | INTL Basis | 2026-10-22 | Open
D-O2 | Decision | OPEN: connect XS4 to DG4 for GTS tests? Recommend no; prove GTS in QS4 + QG4 | - | Low | Recommend no | PwC Functional (GTS) | 2026-10-22 | Open
D-O3 | Decision | OPEN: use Data Transition Validation (Note 3117879) for QS4-200 finance reports? Optional | - | Low | Optional | INTL Test Lead | 2026-10-23 | Open
D-O4 | Decision | OPEN: Fiori follow-ups by INTL Basis or ECS CAS (BASIC_1.5.03, billable) | - | Low | Recommend INTL Basis | INTL Basis | 2026-10-22 | Open
D-O5 | Decision | OPEN: SPDD/SPAU by PwC Technical or ECS billable package (TO_NWABAP_1.5.08) | - | Low | Recommend PwC unless XS4 shows high volume | INTL Basis | 2026-10-28 | Open

## Sandbox Test Plan
Sandbox (XS4) test plan - definition of done before G1
XS4 is isolated after the copy, so connected scenarios are proven in QS4 / SS4 (column F).
Test ID | Area | Test | Done when | Can run in XS4? | Otherwise proven in | Owner | Status | Evidence / defect
SBX-01 | Technical | SUM finished; component levels equal MP 1002693650 target | System status shows S4CORE 108 SP06, SAP_BASIS 758 SP06, add-on SPs as MP | Yes | - | INTL Basis | Not Started
SBX-02 | Technical | Downtime and runtime measured | Actual vs 8 h window recorded; windows confirmed (1.11) | Yes | - | INTL Basis | Not Started
SBX-03 | Technical | SI-check before downtime | No RC >= 8; RC 7 exemptions logged | Yes | - | INTL Basis | Not Started
SBX-04 | Code | SPDD, SPAU, SPAU_ENH worklist | Object count and effort for DS4 | Yes | - | PwC Technical | Not Started
SBX-05 | Technical | System health: SICK, SM21, ST22, SM37, SM59, STMS, SMICM, SGEN | No new dumps or errors vs DS4 baseline | Yes | - | INTL Basis | Not Started
SBX-06 | Technical | Silent data migration | SDM_MON complete in all clients; SDM_USER present | Yes | - | INTL Basis | Not Started
SBX-07 | Fiori | Embedded launchpad and top apps per stream | Tiles open; caches invalidated; SICF nodes active | Yes | - | INTL Basis + PwC Technical | Not Started
SBX-08 | Fiori | Work Zone tiles | Tiles open from Work Zone | No | DS4 2 Nov; QS4 8-12 Nov | INTL Basis | Not Started
SBX-09 | Code | ATC on SPS06; critical custom programs, enhancements, forms, workflows | Zero priority-1 ATC findings; smoke list passed | Yes | - | PwC Technical | Not Started
SBX-10 | Security | SU25 2a/2b; role delta; stream test users log on | Role delta list; users work | Yes | - | INTL SAP Security | Not Started
SBX-11 | Security | GRC AC 12.0 SP32 post-steps and risk analysis | Sync jobs and analysis run | Partial | Connected systems: QS4 9-11 Nov | INTL SAP Security | Not Started
SBX-12 | Code | Side-effect notes: HotNews 3777415, 3563542, then High | Implemented and tested; bundle order fixed | Yes | - | PwC Technical | Not Started
SBX-13 | OTC | Order > delivery > billing; credit memo | Documents post; tax via OneSource disconnected | Partial | OneSource: QS4 9-12 Nov with TR | PwC Functional | Not Started
SBX-14 | STP | PR > PO > GR > invoice | Documents post; no Ariba send | Partial | Ariba CIG: QS4 9-12 Nov | PwC Functional | Not Started
SBX-15 | RTR | GL posting, FX valuation, allocation, depreciation run | Results match DS4 logic | Yes | - | PwC Functional | Not Started
SBX-16 | ITD | GR/GI, stock, material ledger | Postings and valuation correct (HotNews 3777415 area) | Yes | - | PwC Functional | Not Started
SBX-17 | CFIN | AIF monitor, mapping, replicated documents | Replication works | No | QS4 via QL4 9-12 Nov | PwC Functional (CFIN) | Not Started
SBX-18 | VIM | DP document, parking, approval workflow, posting; VIM Fiori apps | Flow completes without capture | Partial | Capture and archive: QS4 9-12 Nov | PwC Functional (VIM) | Not Started
SBX-19 | DRC | Mexico eDocument created in the eDocument cockpit | eDocument created; not submitted | Partial | PAC submission: QS4 9-12 Nov | PwC Functional (DRC) | Not Started
SBX-20 | MBC | Payment run creates the payment file | File created; not sent | Partial | Transmission: QS4 9-12 Nov | PwC Functional (MBC) | Not Started
SBX-21 | AFC | Programs and variants used by AFC tasks run locally | Jobs finish | Partial | AFC tenant: DS4 3-4 Nov, QS4 9-12 Nov | PwC Functional (AFC) | Not Started
SBX-22 | GTS | Plug-in customizing and transfer programs open without errors | No dumps; no RFC to GTS | Partial | With QG4: QS4 9-12 Nov | PwC Functional (GTS) | Not Started
SBX-23 | SailPoint | SailPoint objects active; connector user role after SU25 | Objects active; role OK | Partial | Aggregation/provisioning: QS4 9-11 Nov | INTL SAP Security | Not Started
SBX-24 | Data migration | Syniti objects active; sample load if data allows | Objects active | Partial | Sample loads: QS4-100 9-11 Nov | PwC Data Migration | Not Started
SBX-25 | Output | Forms render; spool and print preview | Output correct | Yes | - | PwC Technical | Not Started
SBX-26 | Batch | Top background jobs with production variants | Jobs finish without errors | Yes | - | PwC Functional | Not Started
SBX-27 | Performance | Key transaction response vs DS4 | No obvious degradation (sizing differs) | Partial | SS4 delta check 16-18 Nov | INTL Test Lead | Not Started
SBX-28 | Interfaces | IDoc/RFC/OData simulated inbound and outbound | Messages process locally | Partial | Real partners: QS4 9-12 Nov | PwC Functional | Not Started
SBX-29 | Isolation | No outbound connection to real endpoints | Isolation checklist evidenced | Yes | - | INTL Basis | Not Started
SBX-30 | Front end | SAP GUI version in use logs on and runs key transactions | Works | Yes | - | INTL Basis | Not Started
Definition of done (G1)
1. Every "Yes" test passed with evidence in qTest.
2. Every "Partial" or "No" test has a named follow-up test, system and date (column F).
3. All UPG-SPS06 defects from XS4 triaged; none Sev1/Sev2 open.
4. SPDD/SPAU and note effort sized for DS4; downtime confirmed with ECS.
5. G1 signed by INTL PMO with INTL Basis, PwC Technical and INTL Test Lead.

## Integrations
Integration impact and plan
One row per connected application. Copy isolation applies to XS4, DS5 and QS5.
Application | Systems | What SPS06 changes | Copy isolation (XS4, DS5, QS5) | During upgrade windows | Test where / when | Owner | Status
Central Finance + SLT | S/4 (CFIN in same system); QL4 (N), QL5 (N+1) | CFIN application code (incl. AIF) changes inside the stack; SER in-scope AIF note 3767655. SLT servers are not upgraded. | XS4 and DS5 have no SLT; QS5 copies QS4 settings: block QL4 links and repoint to QL5 (task 3.11) | Suspend replication on QL4 before QS4 (6 Nov) and SS4 (13 Nov); drain AIF; resume and reconcile after | QS4 9-12 Nov (P1 CFIN); SS4 UAT from 16 Nov | PwC Functional (CFIN) + INTL Basis | Not Started
SAP GTS | DG4 (Dev), QG4 (QA; client 300 = UAT) | GTS is not upgraded. The S/4 side of the integration (plug-in in the S/4 core) changes with the stack. | XS4, DS5, QS5 must not reach DG4/QG4 (they would send under the source logical system) | Pause transfers for DS4, QS4 and SS4 windows; retransfer check after | QS4-200 with QG4 9-12 Nov; QG4-300 with SS4 UAT from 16 Nov (no GTS pre-prod) | PwC Functional (GTS) + INTL Basis | Not Started
SAP AFC (BTP) | AFC tenant(s); S/4 via Cloud Connector | AFC itself is SaaS. S/4 programs and variants scheduled by AFC run on the new stack. | Copies are not registered in AFC; do not add them | Pause AFC task runs against the system in its window | Connection + one closing task in DS4 (3-4 Nov) and QS4 (9-12 Nov) | PwC Functional (AFC) + SAP BTP team | Not Started
SAP MBC (BTP) | MBC tenant; S/4 payment and bank-statement interfaces | Payment medium and bank-statement processing run on the new stack; SER in-scope notes per stream test focus. | High risk: a copy keeps the MBC certificate and destination. Disable in XS4, DS5, QS5 | Hold payment file transmission during windows | F110 file creation in XS4 (no send); end-to-end in QS4 9-12 Nov | PwC Functional (MBC) + INTL Basis | Not Started
SAP DRC - Mexico | eDocument framework in S/4; submission via BTP to the PAC | eDocument and legal-change code ships in the stack; the Mexico deployment (21 Sep - 3 Oct) was built on FPS02. SER in-scope DRC note 3830404 (US). | Disable eDocument submission in copies (risk of test folios at the PAC) | Hold submissions during windows; resubmit from the eDocument cockpit | Create in XS4 (no submission); submit in QS4 9-12 Nov; UAT from 16 Nov | PwC Functional (DRC) + SAP BTP team | Not Started
SAP Build Work Zone Standard | Work Zone tenant; S/4 content exposure | Launchpad content (UI content FPS02 > FPS03, SAP_UI 758 SP06) is re-exposed after each upgrade. | Copies are not content providers | Re-expose and re-sync the content channel after each window | Embedded launchpad in XS4; Work Zone in DS4, QS4, SS4, PS4 | INTL Basis + PwC Technical | Not Started
SAP GRC Access Control 12.0 | Embedded in S/4 (GRCFND_A V8100, GRCPINW, UIGRAC01) | Upgraded inside the same SUM: AC 12.0 for S/4HANA SP29 > SP32; Fiori for AC 2.0 SP02 > SP03 (MP). | Copies keep GRC connectors to other systems: deactivate | No separate window | Post-steps and ARA in XS4; regression in QS4 9-11 Nov | INTL SAP Security | Not Started
SailPoint | SailPoint identity platform; SAP connector via RFC | SailPoint objects in S/4 are customer/partner transports; SU25 role changes can affect the connector user. | Do not aggregate or provision copies (unless defined as new applications) | Pause aggregation and provisioning for the target system | Objects active in XS4; aggregation and provisioning in QS4 9-11 Nov | INTL SAP Security + SailPoint | Not Started
Syniti (data migration) | Syniti platform; RFC to S/4; Mock3 on SS4-100 | Load programs and SAP APIs used by Syniti run on the new stack from SS4 (14 Nov) and PS4 (21 Nov). SER in-scope migration notes 3805046, 3791609, 3789840. | No Syniti connection to copies | No loads into a system in its window | Mock3 on FPS02 (no change); sample loads on SPS06 in QS4-100 9-11 Nov | PwC Data Migration + Syniti | Not Started
OpenText VIM 23.4 + ADA 23.4 | In S/4 (OTVIM* 02023_001); archive and capture outside S/4 | Partner add-on SPs move inside the stack: FND/INV SP03 > SP04, O2C/P2P SP01 > SP02; ADA stays at initial shipment (MP). The SER lists no OpenText components. | Disable archive, capture and e-mail connections in copies | Stop inbound capture during windows | VIM flow in XS4 without capture; end-to-end in QS4 9-12 Nov | PwC Functional (VIM) + INTL Basis + OpenText | Not Started
Thomson Reuters OneSource | OneSource tax engine; S/4 tax interface | Tax interface code in the stack; SER in-scope notes in OTC/STP stream focus. | Disconnect copies from OneSource | No impact beyond the window | QS4 9-12 Nov with TR onsite (w/c 9 Nov) | PwC Functional (OneSource) + TR | Not Started
SAP Ariba (CIG add-on) | Ariba Network via CIG | Ariba Cloud Integration for S/4HANA 1.0 moves 21 > 27 FPS (MP). | Disable CIG connectivity in copies | Queue outbound during windows | QS4 9-12 Nov (P1 STP) | PwC Functional (STP) | Not Started
Legacy interfaces | Non-SAP systems connected to QS4 / SS4 | Interface code on the S/4 side runs on the new stack. | Disable in copies | Notify interface owners of each window | QS4 9-12 Nov; SS4 UAT from 16 Nov | INTL Legacy teams + INTL Basis | Not Started

## Vendor Questions
Vendor questions and e-mail drafts
Send the e-mails on Mon 19 Oct; answers due Wed 28 Oct. Record answers in the yellow cells.
Vendor | ID | Question | Asked on | Answer | Answered on | Status
OpenText | OT-1 | Confirm VIM 23.4 (FND and INV SP04, O2C and P2P SP02, Fiori OTVIMFUI) and ADA 23.4 (initial shipment) are released for SAP S/4HANA 2023 SPS06 (S4CORE 108 SP06, SAP_BASIS / SAP_UI 758 SP06) on RISE Private Cloud. |  |  |  | Not Started
OpenText | OT-2 | Are there known issues, hotfixes or mandatory patches for these SPs on 2023 SPS06? |  |  |  | Not Started
OpenText | OT-3 | Which post-update steps are required after the SP move (configuration checks, BC sets, workflow or BRF+ regeneration, Fiori caches and catalogs)? |  |  |  | Not Started
OpenText | OT-4 | Do the SPs run conversion reports or data changes during import? Are they safe if SUM is restarted? |  |  |  | Not Started
OpenText | OT-5 | Any version dependency with components outside S/4 (capture, archive server, ArchiveLink)? |  |  |  | Not Started
OpenText | OT-6 | Which connections must be disabled after a homogeneous system copy (Sandbox and N+1 copies), and how are they re-registered? |  |  |  | Not Started
OpenText | OT-7 | Recommended regression scope after the SP update, and weekend support for 31 Oct, 7, 14 and 21 Nov. |  |  |  | Not Started
Thomson Reuters | TR-1 | Confirm the OneSource Indirect Tax integration in use is supported on SAP S/4HANA 2023 SPS06. |  |  |  | Not Started
Thomson Reuters | TR-2 | Is any SAP-side transport or configuration change needed for SPS06? |  |  |  | Not Started
Thomson Reuters | TR-3 | Can the onsite team (w/c 9 Nov) validate tax determination on QS4 client 200 (SPS06) during 9-12 Nov? |  |  |  | Not Started
Thomson Reuters | TR-4 | How should copied systems (Sandbox, N+1) be disconnected from OneSource? |  |  |  | Not Started
SailPoint | SP-1 | Confirm the SailPoint SAP connector and SailPoint-delivered SAP transports in use support SAP S/4HANA 2023 SPS06 (SAP_BASIS 758 SP06). |  |  |  | Not Started
SailPoint | SP-2 | Is a new transport version or connector configuration change needed? |  |  |  | Not Started
SailPoint | SP-3 | How should aggregation and provisioning be paused for a system during its upgrade window, and how are failed operations replayed? |  |  |  | Not Started
SailPoint | SP-4 | Recommended regression tests (aggregation, create, modify, lock, unlock, role assignment, password reset), and any dependency on GRC AC 12.0 SP32. |  |  |  | Not Started
SailPoint | SP-5 | Confirm copied systems will not be aggregated unless defined as new applications. |  |  |  | Not Started
Syniti | SY-1 | Mock3 runs on SS4 client 100 on FPS02 (19 Oct - 6 Nov); SS4 moves to SPS06 on 14 Nov and production on 21 Nov. Is any Syniti-side change needed? |  |  |  | Not Started
Syniti | SY-2 | Are the Syniti SAP-side components (RFC function modules or transports) compatible with SAP S/4HANA 2023 SPS06? Is a new version needed? |  |  |  | Not Started
Syniti | SY-3 | Which load methods are used per object (BAPI, IDoc, Migration Cockpit staging, custom)? Which objects should be revalidated on SPS06? |  |  |  | Not Started
Syniti | SY-4 | If the Migration Cockpit is used: do migration objects need an update after the stack change before cutover loads? |  |  |  | Not Started
Syniti | SY-5 | Can Syniti run sample loads on QS4 client 100 (SPS06) on 9-11 Nov to prove cutover readiness? |  |  |  | Not Started
Syniti | SY-6 | Confirm Syniti will not connect to copied systems (Sandbox XS4, N+1 DS5/QS5). |  |  |  | Not Started
E-mail drafts
OpenText |  | Subject: Project NorthStar - SAP S/4HANA 2023 SPS06 update: VIM 23.4 / ADA 23.4 confirmation
Hello OpenText team, International Motors (Project NorthStar) is updating SAP S/4HANA 2023 on RISE Private Cloud from FPS02 to SPS06 (Maintenance Plan 1002693650). The stack moves our OpenText components as follows: VIM 23.4 FND and INV SP03 to SP04, O2C and P2P SP01 to SP02; ADA 23.4 stays at initial shipment. Planned windows: Sandbox 24 Oct, Development 31 Oct, QA 7 Nov, pre-production 14 Nov, production 21 Nov 2026. Please answer the questions below by Wed 28 Oct 2026; the release confirmation for SPS06 and any required patches or post-update steps matter most. OT-1. Confirm VIM 23.4 (FND and INV SP04, O2C and P2P SP02, Fiori OTVIMFUI) and ADA 23.4 (initial shipment) are released for SAP S/4HANA 2023 SPS06 (S4CORE 108 SP06, SAP_BASIS / SAP_UI 758 SP06) on RISE Private Cloud. OT-2. Are there known issues, hotfixes or mandatory patches for these SPs on 2023 SPS06? OT-3. Which post-update steps are required after the SP move (configuration checks, BC sets, workflow or BRF+ regeneration, Fiori caches and catalogs)? OT-4. Do the SPs run conversion reports or data changes during import? Are they safe if SUM is restarted? OT-5. Any version dependency with components outside S/4 (capture, archive server, ArchiveLink)? OT-6. Which connections must be disabled after a homogeneous system copy (Sandbox and N+1 copies), and how are they re-registered? OT-7. Recommended regression scope after the SP update, and weekend support for 31 Oct, 7, 14 and 21 Nov. Thank you, Girish Ogirala SAP Basis, International Motors
Thomson Reuters |  | Subject: Project NorthStar - SAP S/4HANA 2023 SPS06 update: OneSource confirmation
Hello Thomson Reuters team, We are updating SAP S/4HANA 2023 from FPS02 to SPS06. QA (QS4) moves on 7 Nov, pre-production (SS4) on 14 Nov and production on 21 Nov 2026. Your onsite week starting 9 Nov falls in our QA regression (9-12 Nov) on SPS06. Please answer the questions below by Wed 28 Oct 2026. TR-1. Confirm the OneSource Indirect Tax integration in use is supported on SAP S/4HANA 2023 SPS06. TR-2. Is any SAP-side transport or configuration change needed for SPS06? TR-3. Can the onsite team (w/c 9 Nov) validate tax determination on QS4 client 200 (SPS06) during 9-12 Nov? TR-4. How should copied systems (Sandbox, N+1) be disconnected from OneSource? Thank you, Girish Ogirala
SailPoint |  | Subject: Project NorthStar - SAP S/4HANA 2023 SPS06 update: SailPoint connector confirmation
Hello SailPoint team, We are updating SAP S/4HANA 2023 from FPS02 to SPS06 (SAP_BASIS 758 SP06; GRC AC 12.0 SP32). Windows: Development 31 Oct, QA 7 Nov, pre-production 14 Nov, production 21 Nov 2026. Please answer the questions below by Wed 28 Oct 2026. SP-1. Confirm the SailPoint SAP connector and SailPoint-delivered SAP transports in use support SAP S/4HANA 2023 SPS06 (SAP_BASIS 758 SP06). SP-2. Is a new transport version or connector configuration change needed? SP-3. How should aggregation and provisioning be paused for a system during its upgrade window, and how are failed operations replayed? SP-4. Recommended regression tests (aggregation, create, modify, lock, unlock, role assignment, password reset), and any dependency on GRC AC 12.0 SP32. SP-5. Confirm copied systems will not be aggregated unless defined as new applications. Thank you, Girish Ogirala
Syniti |  | Subject: Project NorthStar - SAP S/4HANA 2023 SPS06 update: impact on Mock3 and cutover loads
Hello Syniti team, Mock Load 3 starts 19 Oct on SS4 client 100 and runs on FPS02 until 6 Nov. SS4 moves to SPS06 on 14 Nov and production on 21 Nov, so cutover loads (from 7 Dec) will run on SPS06. Please answer the questions below by Wed 28 Oct 2026. SY-1. Mock3 runs on SS4 client 100 on FPS02 (19 Oct - 6 Nov); SS4 moves to SPS06 on 14 Nov and production on 21 Nov. Is any Syniti-side change needed? SY-2. Are the Syniti SAP-side components (RFC function modules or transports) compatible with SAP S/4HANA 2023 SPS06? Is a new version needed? SY-3. Which load methods are used per object (BAPI, IDoc, Migration Cockpit staging, custom)? Which objects should be revalidated on SPS06? SY-4. If the Migration Cockpit is used: do migration objects need an update after the stack change before cutover loads? SY-5. Can Syniti run sample loads on QS4 client 100 (SPS06) on 9-11 Nov to prove cutover readiness? SY-6. Confirm Syniti will not connect to copied systems (Sandbox XS4, N+1 DS5/QS5). Thank you, Girish Ogirala

## Transport Windows
Transport windows and rules
Which transports may move while the landscape is on mixed levels.
Window | Dates | System levels | Rule
A | until Thu 29 Oct | All systems FPS02 | Normal DS4 > QS4 > SS4 (> PS4). DS5 exists from 28 Oct but is not used yet.
B | Fri 30 Oct - Sun 8 Nov | DS4 SPS06 (locked from 30 Oct); QS4, SS4, PS4 FPS02 | SIT2 week-6 and Mock3 fixes built in DS5 > QS4 / SS4 (FPS02 to FPS02) and re-applied in DS4. DS4 > QS4 imports held. QS4 imports end Thu 5 Nov.
C | Mon 9 - Sun 15 Nov | DS4, QS4 SPS06; SS4, PS4 FPS02 | DS4 > QS4 normal (both SPS06). UAT week-1 fixes for SS4 from DS5, re-applied in DS4. SS4 imports end Thu 12 Nov. PS4 held.
D | Mon 16 - Sun 22 Nov | DS4, QS4, SS4 SPS06; PS4 FPS02 until 21 Nov | Normal DS4 > QS4 > SS4. PS4 queue held until PS4 post-processing. DS5 frozen (Plan C only).
E | from Mon 23 Nov | Go-live line SPS06; DS5/QS5 FPS02 until 1 / 3 Dec | Normal flow to PS4. DS5/QS5 receive nothing until upgraded, then retrofit per N+1 design.
Rules
1. Transport only between systems on the same level; never from SPS06 into an FPS02 system (UG 3.1: transports between systems with different software levels may cause errors and inconsistencies).
2. Dual maintenance (UG 3.1): a fix made in DS5 for an FPS02 system is re-applied in DS4; the retrofit log is reconciled daily (task 2.10).
3. SUM reuses the DS4 SPDD and SPAU transports in QS4, SS4, PS4, DS5 and QS5 (phase ADJUSTPRP, UG 3.5). Keep the same target stack everywhere.
4. Imports into a system stop when its SUM uptime starts (repository locked); schedule the last import the day before.
5. Copies (XS4, DS5, QS5) never send data to connected systems unless a connection is deliberately rebuilt for testing.

## SAP Teams
How SAP ECS, MaxAttention and the BTP team support the upgrade
Relationship owner for all SAP teams: Girish Ogirala (INTL Basis).
SAP team | Role in this upgrade | Tasks | How engaged | When
SAP ECS | Runs the technical work on request (SRs) | System copies DS4>XS4, DS4>DS5, QS4>QS5; SUM runs on XS4, DS4, QS4, SS4, PS4, DS5, QS5; HANA/kernel per MP; backups; technical FES upgrade; SDMI users if requested; hands the SR back at SPDD and for ramp-down | SRs in SAP for Me; TSM for scheduling | Windows confirmed by Fri 23 Oct; copies and SUM per SR Tracker
SAP MaxAttention | Safeguards the plan and escalates | Review plan v4 and the runbook; review SI-check results and the side-effect note bundle; named weekend contacts; escalation of SR delays and incidents; performance comparison FPS02 vs SPS06 on SS4; PS4 window support | Engagement architect / TQM; incident escalation | Review by G0 (22 Oct); on call 24 Oct - 22 Nov
SAP BTP team | Keeps BTP services aligned with each S/4 window | Confirm no AFC, MBC, DRC or Work Zone action is needed for the stack; tenant maintenance dates vs windows; Cloud Connector and destinations; guidance to keep copies disconnected; DRC submission checks | BTP account team; BTP incidents | Checklist by G0; support on each Sunday check (1, 8, 15, 22 Nov)
SAP Support (incidents) | Product incidents during the upgrade | Incidents for SUM, application and note issues; priority per business impact; INTL Basis raises and tracks | SAP for Me incidents (INTL Basis) | As needed

## Guide Checklist
Upgrade Guide (UPGR_PE2023 v6.0) - every recommendation mapped
BPMN node = number in the NorthStar process diagram.
# | Guide section | Recommendation (UPGR_PE2023 v6.0) | NorthStar action | Task(s) | BPMN node | Status
UG-01 | 2.1 | Use the required documents: Simplification Item Catalog, SUM 2.0 guide, Maintenance Planner guide, and Notes 3307222, 3351047, 3348949, 2214409, 3279787, 2399707, 2502552, 3340515, 3340526, 3306766, 3336823, 2217489, 3346290, 3247591 | Reference list in this workbook; 2399707/2502552 implemented first | 0.02 | 1 | Not Started
UG-02 | 2.1 | SAP Readiness Check is relevant for release upgrades, not for FPS/SPS updates | Not required (FPS02 > SPS06 is an SPS update); SI-check and side-effect report used | H.4 | - | Complete
UG-03 | 2.1 | Technical notes via ECS (BASIC_1.5.04); application notes by customer or billable CAS (BASIC_1.5.03); a shared transport must be imported before the next system is upgraded | Note transports from DS4; imported before each SUM | 0.02, 2.08 | 5, C8 | Not Started
UG-04 | 2.2 | Follow the sequence Plan > Prepare > Realize > Follow-up | Phases P0-P7 and BPMN flow | all | all | Not Started
UG-05 | 3.1 | Update in transport order (Dev > QA > Prod) with the same software packages | XS4 > DS4 > QS4 > SS4 > PS4, one target stack | 0.05 | 10-22 | Not Started
UG-06 | 3.1 | Transport only between systems on the same level | Transport windows A-E | 0.12 | 4 | Not Started
UG-07 | 3.1 | Keep the development system; do not copy production to development | DS4 is upgraded in place; copies only go DS4 > XS4/DS5 and QS4 > QS5 | 1.01, 2.01, 3.01 | 10, 13, 16 | Not Started
UG-08 | 3.1 | Plan for the development freeze (dev lock) and inform developers | DS4 lock from Fri 30 Oct; cut-off 30 Oct 12:00 CT | 2.03, 2.04 | C3 | Not Started
UG-09 | 3.1 | Add a temporary Dev (and QA) copy for emergency fixes; dual maintenance with notification | DS5 and QS5 copies; dual-maintenance rule and retrofit log | 2.01, 3.01, 2.10 | 13, 15, 16 | Not Started
UG-10 | 3.2 | Check SAP GUI compatibility before downtime (Notes 147519, 26417, 178788) | GUI check | 0.18 | 6 | Not Started
UG-11 | 3.3 | FES technical upgrade by ECS; check Note 2217489; run the Fiori Upgrade Impact Analysis | MP shows Fiori UI FPS03 and FES 2023 SP02; impact analysis | 0.17 | 6, C7 | Not Started
UG-12 | 3.4 | Identify relevant simplification items early | SI-check in DS4 and QS4 week of 19 Oct | 0.03 | 1 | Not Started
UG-13 | 3.5 | Translations changed in SE63 are lost (Note 485741) | Check for SAP text changes in DS4 | 0.13 | 5 | Not Started
UG-14 | 3.5 | Adjust SPDD/SPAU first, then SPAU_ENH | Sequence in XS4 and DS4 | 1.05, 2.05 | C5, C8 | Not Started
UG-15 | 3.5 | A Z* package must exist before the update | Confirmed in DS4 | 0.13 | 5 | Not Started
UG-16 | 3.5 | Passive deletion of objects from manual note corrections (Note 2513585) | Objects listed and rescued in SPDD | 0.13 | 5, C5 | Not Started
UG-17 | 3.5 | ECS hands the SR back at SPDD; return it with the transport number (or buy TO_NWABAP_1.5.08) | SPDD transport into the DS4 SR; decision D-O5 | 2.05 | C5 | Not Started
UG-18 | 3.5 | Adjust in the first system; reuse SPDD and SPAU transports in later systems (ADJUSTPRP) with the same SP levels | DS4 transports reused in QS4, SS4, PS4, DS5, QS5 | 2.05, 3.05 | C5 | Not Started
UG-19 | 4.1 | Respect SP equivalence between source and target (Notes 2457423, 3307222) | Same release; MP validated the path | H.1 | 2 | Not Started
UG-20 | 4.2 | Create an MPID and attach it to the SR | MPID per system | 0.05 | 2, C1 | Not Started
UG-21 | 4.2 | Business functions always_on / always_off (Notes 2240359, 2240360) | Checked by MP for XS4; repeat per system | 0.05 | 2 | Not Started
UG-22 | 4.2 | Third-party add-ons: confirm with the vendor (Note 2861669); uninstall via BASIC 1.5.13A if needed (Note 2011192) | Vendor e-mails and questions | 0.11 | 3 | Not Started
UG-23 | 4.3 | System requirements (PAM); OS and HANA updates by separate SRs with separate downtime | Ask ECS about HANA 89.5 and kernel 916 | 0.06 | 9 | Not Started
UG-24 | 4.4 | SI-check: Notes 2399707 and 2502552 (TCI, Note 2187425); run /SDF/RC_START_CHECK early; fix RC 8/12; exempt RC 7 | DS4, QS4, XS4 before each SUM; version check 48 h before | 0.02, 0.03, 1.03 | 1, C2, C4 | Not Started
UG-25 | 4.5 | Custom code check with ATC or Custom Code Migration app; Simplification DB (Note 2241080); notes from 2436688; baseline | ATC in DS4 and XS4 | 0.14, 2.08 | 5 | Not Started
UG-26 | 4.6 | Java instances are the customer's responsibility (Note 2251604) | Confirm no separate Java instance (e.g. ADS) | 0.06 | 9 | Not Started
UG-27 | 4.7 | ODP jobs ODQ_CLEANUP / ODQ_DAEMON (Note 2677355) | Variant check | 0.16 | - | Not Started
UG-28 | 4.8 | Data Transition Validation (Note 3117879), optional | Decision D-O3 | - | C13 | Not Started
UG-29 | 5 | ECS triggers SUM 24 h before the start time; request earlier uptime in the SR | Uptime start written into each SR | 0.04 | C1, C3 | Not Started
UG-30 | 5 | Breakpoints: SPDD, dev lock, SI-checks | Named owners per weekend | 0.09 | C4, C5 | Not Started
UG-31 | 5 | Ramp-down before downtime: stop jobs, lock users, clear queues and update errors | Ramp-down tasks per system | 3.04, 4.02 | C6 | Not Started
UG-32 | 6.1 | SDMI: SDM_USER before, SDM_MON after; all SDMIs finished in all clients; downtime option must be in the SR | SDMI users; completion check; decision D-O1 | 0.15, 7.03 | 7, C9 | Not Started
UG-33 | 6.2 | Obsolete data handling with SODH (Note 3335020) after validation | After hypercare | 7.05 | 23 | Not Started
UG-34 | 6.3 | Fiori follow-ups: Notes 3336823, 2902673; /UI2/GET_APP_DESCR_REMOTE_ALL (BEC); cache invalidation; SICF /sap/public/bc/its; RS_ICF_SERV_MASS_PROCESSING; performance Note 2916959 | Every system after SUM | 1.07, 2.06, 3.06 | C10 | Not Started
UG-35 | 6.4 | SU25 steps 2a/2b, SU24, PFCG roles (Notes 1539556, 440231) | Every system; role transports from DS4 | 1.08, 2.07 | C11 | Not Started
UG-36 | 6.5 | Advanced Variant Configuration: Note 2987015 if used | Confirm whether AVC is used | 0.03 | C8 | Not Started
UG-37 | 6.6 | PP/DS report only when coming from 2021 or lower | Not applicable (2023 > 2023) | - | - | Complete
UG-38 | 6.7 | FS-PM follow-ups | Not applicable | - | - | Complete
UG-39 | 7.1 | Readiness Check is a planning tool; SI-check is mandatory and called by SUM | SI-check is the control point | 0.03 | 1 | Not Started
UG-40 | 2.1 | Additional notes: 2344014 (SPAU), 2836302 (TCI/digitally signed notes), 2351294 (downtime reduction), 2781530, 2834255 | Reviewed by PwC Technical with the SPAU plan | 1.05 | C8 | Not Started

## RACI
RACI
R = Responsible, A = Accountable, C = Consulted, I = Informed. INTL Basis = Girish Ogirala (lead) + 1 onsite + 2 offshore.
Activity | SAP ECS | SAP MaxAttention | SAP BTP team | INTL Basis | INTL SAP Security | INTL PMO | INTL Test Lead | INTL PO / IT | PwC Technical | PwC Functional | PwC Data Migration | Vendors
Service requests, ECS scheduling, incidents | R | C | I | A/R | I | C | I | I | I | I | I | I
System copies and isolation | R | I | C | A | C | I | I | I | I | C | C | I
SUM runs, HANA, kernel | R | C | I | A | I | I | I | I | C | I | I | I
SI-check and note 2502552 | C | C | I | A/R | I | I | I | I | C | R | I | I
SPDD, SPAU, note bundle, ATC | C | C | I | C | I | I | I | I | A/R | C | I | I
SU25, roles, GRC, SailPoint | I | I | I | C | A/R | I | I | I | C | C | I | C
Fiori, Work Zone, GUI | C | I | C | A/R | C | I | I | I | R | C | I | I
CFIN/SLT, GTS, BTP integrations | I | C | C | C | I | I | I | C | C | A/R | I | C
Partner add-ons (OpenText, TR, SailPoint, Syniti) | I | C | I | A/R | C | I | I | I | C | R | R | R
Sandbox and QS4 regression | I | I | I | C | C | I | A | C | R | R | C | C
UAT on SPS06 (SS4) | I | I | I | C | C | I | A | R | C | C | I | I
Data migration on SPS06 (Syniti) | I | I | I | C | I | I | C | I | I | C | A/R | R
Transport windows and dual maintenance | I | I | I | A/R | I | C | C | I | R | R | C | I
Gates and steering decisions | C | C | C | R | C | A | C | C | C | C | C | I

## Project Calendar
Project calendar (Plan on a Page, updated 9/21)
Context only: dates owned by the NorthStar PMO.
Event | System / client | Start | End | Note
SIT1 | QS4-100 | 2026-08-03 | 2026-09-27 | Complete per Plan on a Page
Mock Load 2 | QS4-200 | 2026-09-07 | 2026-10-11 | Master data, then transactional data
SIT2 | QS4-200 | 2026-09-28 | 2026-11-06 | Started 28 Sep as planned
Performance testing | SS4-100 | 2026-10-14 | 2026-11-06 | On FPS02
Mock Load 3 | SS4-100 | 2026-10-19 | 2026-11-06 | On FPS02
UAT | SS4-100 | 2026-11-09 | 2026-12-04 | Week 1 on FPS02, weeks 2-4 on SPS06
Go / No-Go | - | 2026-11-30 | 2026-12-04 | At UAT end
Cutover | PS4 | 2026-12-07 | 2026-12-31 | On SPS06
TR onsite (OneSource) | - | 2026-11-09 | 2026-11-13 | Validates OneSource on QS4 SPS06
Go-live | PS4 | 2027-01-01 | 2027-01-01

## Stream Test Focus
Stream test focus for the SPS06 re-run
Note numbers are from the side-effect report for MP 1002693650 (SER).
Stream | What to re-run | SER notes to watch
STP / Ariba (PwC) | PR -> PO -> Ariba Network via CIG add-on (ARBCI1 SP27), order confirmation, ASN, invoice; Manage Purchase Contracts; Taulia (TAUCI1) if used | 3727222, 3728027, 3563636, 3542666
OTC (PwC) | Order -> delivery -> billing, pricing, credit memo tax with OneSource, BP sync | 3678075, 3666390, 3759214
RTR (PwC) | GL close, FX valuation, allocations, AA depreciation, Margin Analysis, Material Ledger close | 3757119, 3777415 (HotNews), 3749911, 3751266
ITD (PwC) | GR/GI, inventory, deliveries, ML valuation, material master mass changes | 3777415, 3779425, 3528920
Central Finance (PwC) | SLT pause/resume, AIF monitor, replication of parked and reversal documents, mapping | 3794020, 3789234, 3793659, 3767655, 3756339
OpenText VIM (PwC) | Invoice capture -> DP document -> parking (FBV0) -> workflow approval -> posting; ArchiveLink images | 3680992, 3279714, 3777208
SAP AFC (PwC) | AFC (BTP) connection to S/4 via Cloud Connector; scheduled S/4 tasks run from AFC | Backend prerequisites per AFC documentation
SAP DRC (PwC) | Mexico eDocuments just deployed (21 Sep - 3 Oct): CFDI issue, cancel, payment complement; US Sales and Use Tax; CA/US/MX statutory reports | 3830404
SAP MBC (PwC) | F110 -> DMEE(X) payment file -> MBC; bank statement import and reprocessing; status messages | 3779613, 3614271, 3735645
OneSource Indirect Tax (PwC + TR) | Tax calculation SO/billing/credit memo, PO/MIRO, Mexico VAT cash basis (RFUMSV50); TR onsite w/c 12 Oct (Sandbox/statement) and w/c 9 Nov (UAT on SPS06) | 3678075, 3613556
Basis / Work Zone (INTL) | Launchpad and Work Zone content federation, tiles, custom apps, spool, qRFC | 3563542 (HotNews), 3534823, 3795313
Security / GRC (INTL) | SU25, SU24, role regression, SUIM, GRC AC 12 add-on | 3809657, 3782096, 3626764, 3590792
GTS (PwC) | Compliance screening and legal control on sales and purchasing documents; master data and document transfer to QG4; customs documents in use | No GTS notes in the SER
SailPoint (INTL Security) | Aggregation, create/modify/lock/unlock, role assignment, password reset | Vendor confirmation (SP-1 to SP-5)
Data migration / Syniti (PwC) | Sample loads per object on SPS06 (QS4-100) | 3805046, 3791609, 3789840

## SAP Notes (In-Scope)
Side-effect notes in scope: 135 notes (146 rows)
From the SER for MP 1002693650; full triage in SAP_Notes_Side_Effect_Register_SPS06.xlsx.
Side-effect note | Priority | Title | Component | Caused by note | Owner | Action
3563542 | 01 HotNews | RSPO1043 detects false inconsistencies and deletes spool requests | BC-CCM-PRN | 0002926979 | INTL Basis | SNOTE after upgrade (no SP assignment in report - check validity in SAP for Me)
3777415 | 01 HotNews | MBEW-KALN1 overwritten by OBEW-KALN1 | CO-PC-ACT | 0003641556 | PwC RTR / ITD | SNOTE after upgrade (fix ships in S4CORE SP07; target is SP06)
3279714 | 02 High | Commit Work not triggered by SWZ_AI_CREATE | BC-BMT-WFM | 0003169078 | PwC STP / VIM | SNOTE after upgrade (no SP assignment in report - check validity in SAP for Me)
3528920 | 02 High | Incorrect function module call due to SAP Note 3505510 | LO-MD-MM | 0003505510 | PwC ITD | SNOTE after upgrade (no SP assignment in report - check validity in SAP for Me)
3534823 | 02 High | ARFC_END_VB is not for update anymore | BC-MID-RFC-QT | 0003525039 | INTL Basis | SNOTE after upgrade (no SP assignment in report - check validity in SAP for Me)
3542666 | 02 High | F2229 - Material group missing | MM-FIO-PUR-REQ-PRF | 0003319706 | PwC STP | SNOTE after upgrade (no SP assignment in report - check validity in SAP for Me)
3563636 | 02 High | [F1048A] Create PO button doesn't launch Create PO application | MM-FIO-PUR-REQ-SOC | 0003539973 | PwC STP | SNOTE after upgrade (fix ships in UIS4HOP1 SP04; target is SP03)
3613556 | 02 High | RFUMSV50: tax transfer posted with FB01 is not updated in DEFTAX_ITEM | FI-GL-GL-F1 | 0003402197 | PwC RTR / OneSource | SNOTE after upgrade (no SP assignment in report - check validity in SAP for Me)
3614271 | 02 High | DMEEX - syntax error in LDMEE1CIT & LDMEE1I18 | CA-GTF-CSC-DME | 0003444594 | PwC STP / MBC | SNOTE after upgrade (no SP assignment in report - check validity in SAP for Me)
3662731 | 02 High | No temporary profitability segments in release S/4 HANA 1709 | CO-PA | 0003589823 | PwC RTR | SNOTE after upgrade (no SP assignment in report - check validity in SAP for Me)
3666390 | 02 High | Updates to Address Comment (ADRCT-REMARK) are not synchronized between the Business Partner, Supplier, and Customer master when remark is maintained in multiple languages | LO-MD-BP-VM | 0003581401 | PwC OTC / STP | SNOTE after upgrade (no SP assignment in report - check validity in SAP for Me)
3678075 | 02 High | Incorrect tax rate in credit memos for intercompany billing or currency change | SD-BIL-IV | 0003526407 | PwC OTC / OneSource | SNOTE after upgrade (no SP assignment in report - check validity in SAP for Me)
3680992 | 02 High | FBV0: Coding contains an invalid function module | FI-GL-GL-W | 0003612459 | PwC RTR / VIM | SNOTE after upgrade (no SP assignment in report - check validity in SAP for Me)
3727222 | 02 High | MEPO601 error when adding manually new item to PO in ME22N | MM-PUR-GF-PR | 0003499331 | PwC STP | SNOTE after upgrade (fix ships in S4CORE SP07; target is SP06)
3728027 | 02 High | Purchasing organization value is not filled for new partners created in contracts using Manage purchase contracts App | MM-FIO-PUR-SQ-CON | 0003622239 | PwC STP | SNOTE after upgrade (fix ships in S4CORE SP07; target is SP06)
3735645 | 02 High | Kurzzeitfehler ASSERTION_FAILED bei Interpretationsalgorithmus 421 | FI-BL-PT-BA | 0003681665 | PwC RTR / MBC | SNOTE after upgrade (fix ships in S4CORE SP07; target is SP06)
3749911 | 02 High | KE396 in MIR4 | CO-PA-ACT | 0003589823 | PwC RTR | SNOTE after upgrade (fix ships in S4CORE SP07; target is SP06)
3751266 | 02 High | KEPSL_DOC_POST_EXTERNAL DUMP CONVT_NO_NUMBER due to PLIKZ | CO-PA | 0003483652 | PwC RTR | SNOTE after upgrade (fix ships in S4CORE SP07; target is SP06)
3752228 | 02 High | Bank details not fully derived from IBAN when posting via accounting interface | FI-AP-AP-J | 0003715290 | PwC STP / CFIN | SNOTE after upgrade (fix ships in S4CORE SP07; target is SP06)
3757119 | 02 High | FAGL_FCV: Program termination GETWA_NOT_ASSIGNED / Selection list does not contain any data | FI-GL-GL-G | 0003558927 | PwC RTR | SNOTE after upgrade (no SP assignment in report - check validity in SAP for Me)
3759214 | 02 High | Classification data not replicated | LO-MD-BP-WS | 0003561399 | PwC OTC / STP | SNOTE after upgrade (fix ships in S4CORE SP07; target is SP06)
3759621 | 02 High | ALV HS-Grid: Dump MOVE_CAST_ERROR when right clicking on Hierseq Grid | BC-SRV-ALV | 0003719981 | INTL Basis | SNOTE after upgrade (fix ships in SAPBASIS SP07; target is SP06)
3767655 | 02 High | Serialization Web Service Message: Successor message is not executed automatically | CA-GTF-AIF | 0003751710 | PwC CFIN | SNOTE after upgrade (fix ships in SAPBASIS SP07; target is SP06)
3779425 | 02 High | UAPI: Wrong field symbol in MRP area update path after note 3621492 causes incorrect data | LO-MD-MM | 0003621492 | PwC ITD | SNOTE after upgrade (fix ships in S4CORE SP07; target is SP06)
3779613 | 02 High | F110: Extended individual payment fails | FI-AP-AP-B | 0003631409 | PwC STP / MBC | SNOTE after upgrade (fix ships in S4CORE SP07; target is SP06)
3782369 | 02 High | TABLE_INVALID_INDEX Runtime Error During Goods Receipt Posting via OData API in Advanced and Multistage Intercompany Process | LE-SHP-VCA | 0003682577 | PwC ITD / OTC | SNOTE after upgrade (no SP assignment in report - check validity in SAP for Me)
3793659 | 02 High | BAPI: AFLE mapping errors not returned | AC-INT | 0003613546 | PwC CFIN | SNOTE after upgrade (fix ships in S4CORE SP07; target is SP06)
3794020 | 02 High | Error reading document number during cFIN replication for posting of parked documents with BSTAT 'U' | FI-GL-GL | 0003596100 | PwC CFIN | SNOTE after upgrade (no SP assignment in report - check validity in SAP for Me)
3794020 | 02 High | Error reading document number during cFIN replication for posting of parked documents with BSTAT 'U' | FI-GL-GL | 0003607571 | PwC RTR | SNOTE after upgrade (no SP assignment in report - check validity in SAP for Me)
3794043 | 02 High | Deletion of an attachment that is available from 'Assign Document' not deleted | CA-DMS | 0003636183 | PwC STP / VIM | SNOTE after upgrade (no SP assignment in report - check validity in SAP for Me)
3806051 | 02 High | KE545 bei buchungskreisübergreifender Buchung | CO-PA-ACT | 0003562180 | PwC RTR | SNOTE after upgrade (no SP assignment in report - check validity in SAP for Me)
3809657 | 02 High | SU25: Fehlerhafte Ergebnisse in Schritt 2c | BC-SEC-AUT-TOO | 0003673078 | INTL Security | SNOTE after upgrade (fix ships in SAPBASIS SP07; target is SP06)
1001203 | 03 Medium | KEPC: Fehlermeldung KE361 | CO-PA | 0003613798 | PwC RTR | SNOTE after upgrade (fix ships in S4CORE SP07; target is SP06)
2525819 | 03 Medium | Accounting: Certificate expired for in-place Excel | FI-SL-IS-A | 0001992004 | PwC RTR | SNOTE after upgrade (no SP assignment in report - check validity in SAP for Me)
3325232 | 03 Medium | App Reprocess Bank Statement Items: Notification when more than 150 items are selected | FI-FIO-AR-PAY | 0003294845 | PwC RTR / MBC | SNOTE after upgrade (no SP assignment in report - check validity in SAP for Me)
3501073 | 03 Medium | SAPDBBRF: SYNTAX ERROR - The data object "<FIN_GLPOS>" does not... | FI-GL-GL-D | 0003497745 | PwC RTR | SNOTE after upgrade (no SP assignment in report - check validity in SAP for Me)
3502014 | 03 Medium | Syntax error due to inconsistent FIN_S_GLPOS | FI-GL-GL | 0003497745 | PwC RTR | SNOTE after upgrade (no SP assignment in report - check validity in SAP for Me)
3506575 | 03 Medium | ALV Grid - Subtotal text not displayed after SAP Note 3503436 | BC-SRV-ALV | 0003503436 | INTL Basis | SNOTE after upgrade (no SP assignment in report - check validity in SAP for Me)
3515210 | 03 Medium | Removal of method if_wd_dg_exexp_ext_ctrl~get_content_for_segment | BW-RUI-FPM | 0003494827 | PwC RTR | SNOTE after upgrade (no SP assignment in report - check validity in SAP for Me)
3525720 | 03 Medium | DIMP: Follow up note 3476680 | IS-A | 0003476680 | PwC ITD / OTC | SNOTE after upgrade (no SP assignment in report - check validity in SAP for Me)
3540815 | 03 Medium | RFAWVZ40N: Follow-up correction for Note 3526044 / Clearing of Customer/Vendor Invoices and Reversals | FI-GL-GL-G | 0003526044 | PwC RTR | SNOTE after upgrade (no SP assignment in report - check validity in SAP for Me)
3549111 | 03 Medium | DIMP: Follow up note 3519923 | IS-ADEC-SUB | 0003519923 | PwC ITD / OTC | SNOTE after upgrade (no SP assignment in report - check validity in SAP for Me)
3549715 | 03 Medium | App Support: Technical correction of unit test | CA-FLP-EXT-ASI | 0003530008 | INTL Basis | SNOTE after upgrade (no SP assignment in report - check validity in SAP for Me)
3549845 | 03 Medium | Quotation Currency does not get updated immediately | MM-FIO-PUR-SPQ | 0003547794 | PwC STP | SNOTE after upgrade (fix ships in UIS4HOP1 SP04; target is SP03)
3554417 | 03 Medium | Update of ABAP Daemon Configuration does not work correctly | BC-MID-DMN | 0003505500 | INTL Basis | SNOTE after upgrade (no SP assignment in report - check validity in SAP for Me)
3562966 | 03 Medium | Expand Display Hierarchy to level | BW-RUI-FPM | 0003552872 | PwC RTR | SNOTE after upgrade (no SP assignment in report - check validity in SAP for Me)
3576593 | 03 Medium | Runtime error during maintenance of classifications | CA-CL | 0003358066 | PwC ITD | SNOTE after upgrade (no SP assignment in report - check validity in SAP for Me)
3583023 | 03 Medium | Update of delivery date for multiple purchase order items not possible using Joule | MM-FIO-PUR-PO | 0003527180 | PwC STP | SNOTE after upgrade (no SP assignment in report - check validity in SAP for Me)
3583927 | 03 Medium | In program R_FINS_PLAN_TRANS_CO_ERP_2_S4H you get error "User &2 has an exclusive lock on data slice &1." | CO-FIO-OM-PL | 0003484101 | PwC RTR | SNOTE after upgrade (no SP assignment in report - check validity in SAP for Me)
3590792 | 03 Medium | Ergänzung zum Hinweis 3564568 | BC-SEC-USR-IS | 0003564568 | INTL Security | SNOTE after upgrade (no SP assignment in report - check validity in SAP for Me)
3595570 | 03 Medium | Succession note for Note 3429227 | CA-CL | 0003429227 | PwC ITD | SNOTE after upgrade (no SP assignment in report - check validity in SAP for Me)
3614027 | 03 Medium | F0711 F0712 Edit Line Items option is not working | FI-FIO-AP | 0003504850 | PwC OTC | SNOTE after upgrade (no SP assignment in report - check validity in SAP for Me)
3621344 | 03 Medium | ATC for DDLS I_ALLOCATIONCYCLEUPLOADTP | FIN-UA | 0003484215 | PwC RTR | SNOTE after upgrade (no SP assignment in report - check validity in SAP for Me)
3626764 | 03 Medium | SU01¦Copy User: Roles are not copied | BC-SEC-USR-ADM | 0003527801 | INTL Security | SNOTE after upgrade (no SP assignment in report - check validity in SAP for Me)
3642725 | 03 Medium | INA : Capabilities are not read and hence may face issues regarding these missing capabilities. | BW-BEX-OT-BICS-INA | 0003521219 | PwC RTR | SNOTE after upgrade (no SP assignment in report - check validity in SAP for Me)
3657542 | 03 Medium | Text Table fields are blank in SM30 during print | BC-CUS-TOL-TME | 0003627579 | INTL Basis | SNOTE after upgrade (no SP assignment in report - check validity in SAP for Me)
3657606 | 03 Medium | App Support: Chip ID invalid | CA-FLP-EXT-ASI | 0003649832 | INTL Basis | SNOTE after upgrade (no SP assignment in report - check validity in SAP for Me)
3666391 | 03 Medium | Unauthorized address display and runtime error SAPSQL_STMNT_TOO_LARGE in BP transaction | AP-MD-BP-EMP | 0003632949 | INTL Security | SNOTE after upgrade (no SP assignment in report - check validity in SAP for Me)
3669526 | 03 Medium | ALV: Missing buttons for added functions in SALV table | BC-SRV-ALV | 0003594156 | INTL Basis | SNOTE after upgrade (no SP assignment in report - check validity in SAP for Me)
3672941 | 03 Medium | MMPUR_SPROC/071: Joint Venture Accounting is not supported for Lean Services. | MM-PUR-PO-SVC | 0003645782 | PwC STP | SNOTE after upgrade (no SP assignment in report - check validity in SAP for Me)
3674295 | 03 Medium | RFAWVZ40: payment/clearing documents not considered correctly | FI-GL-GL-G | 0003708414 | PwC RTR | SNOTE after upgrade (fix ships in S4CORE SP07; target is SP06)
3689874 | 03 Medium | ALLOCATION: Error KC 018 | CO-PA | 0003529459 | PwC RTR | SNOTE after upgrade (fix ships in S4CORE SP07; target is SP06)
3691048 | 03 Medium | Short text of sender and reciver in Settlement follow-up documents after note 3389744 not always correct | CO-OM-OPA-F | 0003389744 | PwC RTR | SNOTE after upgrade (no SP assignment in report - check validity in SAP for Me)
3695248 | 03 Medium | FAGL_PROT: Message Statistics: Wrong Basis Release | FI-GL-GL-G | 0003486933 | PwC RTR | SNOTE after upgrade (no SP assignment in report - check validity in SAP for Me)
3717605 | 03 Medium | Enhanced Limit in PO/PR: Error Messages MMPUR_SPROC/072 + 073 not Required | MM-PUR-PO-SVC | 0003645782 | PwC STP | SNOTE after upgrade (no SP assignment in report - check validity in SAP for Me)
3723716 | 03 Medium | Error message FG605 "Program session restart" | FI-GL-IS | 0003588573 | PwC RTR | SNOTE after upgrade (no SP assignment in report - check validity in SAP for Me)
3730016 | 03 Medium | FAGLF101: Issues When Loading Saved Logs | FI-GL-GL-G | 0003673002 | PwC RTR | SNOTE after upgrade (fix ships in S4CORE SP07; target is SP06)
3737842 | 03 Medium | DIMP: Follow up note 3573879 | IS-ADEC-MPN | 0003573879 | PwC STP | SNOTE after upgrade (no SP assignment in report - check validity in SAP for Me)
3738502 | 03 Medium | CKM3N: Display issue in Beginning Inventory and Receipts categories | CO-PC-ACT | 0003691615 | PwC RTR / ITD | SNOTE after upgrade (fix ships in S4CORE SP07; target is SP06)
3738502 | 03 Medium | CKM3N: Display issue in Beginning Inventory and Receipts categories | CO-PC-ACT | 0003644834 | PwC RTR / ITD | SNOTE after upgrade (fix ships in S4CORE SP07; target is SP06)
3739961 | 03 Medium | BICS: Existing Bookmark Cannot Be Loaded Despite Being Present Part-2 | BW-BEX-OT-BICS-PROV | 0003696992 | PwC RTR | SNOTE after upgrade (fix ships in SAPBW SP07; target is SP06)
3739961 | 03 Medium | BICS: Existing Bookmark Cannot Be Loaded Despite Being Present Part-2 | BW-BEX-OT-BICS-PROV | 0003717286 | PwC RTR | SNOTE after upgrade (fix ships in SAPBW SP07; target is SP06)
3740305 | 03 Medium | Correction in CL_P_COMPANYCODEDETAILSPA - Field country is only from T001-land1 or T001N-land1 | FI-LOC-GEN | 0003605210 | PwC RTR | SNOTE after upgrade (fix ships in S4CORE SP07; target is SP06)
3745364 | 03 Medium | Illegal characters in InputField and InputTokenizer destroy html | BC-WD-ABA | 0003742755 | INTL Basis | SNOTE after upgrade (fix ships in SAPUI SP07; target is SP06)
3747285 | 03 Medium | SD Down Payment with Central Finance: System Dump in Invoice Print Preview | SD-BIL-IV-DP | 0003594536 | PwC OTC / CFIN | SNOTE after upgrade (fix ships in S4CORE SP07; target is SP06)
3747703 | 03 Medium | Purchase Contracts: Incorrect navigation to condition maintenance screen | MM-PUR-OA-CON | 0003620489 | PwC STP | SNOTE after upgrade (fix ships in S4CORE SP07; target is SP06)
3755725 | 03 Medium | No changeover to third phase of depreciation key at the end of useful life | FI-AA-AA-B | 0003583781 | PwC RTR | SNOTE after upgrade (fix ships in S4CORE SP07; target is SP06)
3755943 | 03 Medium | PERFORM_TOO_MANY_PARAMETERS Runtime Error in RCNCC920 | CO-PA | 0003589823 | PwC RTR | SNOTE after upgrade (fix ships in S4CORE SP07; target is SP06)
3756339 | 03 Medium | Central Finance: Central Market Segment Reporting Service Order Management (FI) | FI-CF-AC | 0003537332 | PwC CFIN | SNOTE after upgrade (fix ships in S4CORE SP07; target is SP06)
3759513 | 03 Medium | Parameters missing when navigating with selected hierarchy node | BW-RUI-FPM | 0003690998 | PwC RTR | SNOTE after upgrade (fix ships in SAPBW SP07; target is SP06)
3760190 | 03 Medium | Fehlermeldung FGV 005 (Es wurde keine Geschäftsjahresvariante angegeben) bei Materialbuchung | CO-PA-ACT | 0003593304 | PwC RTR | SNOTE after upgrade (fix ships in S4CORE SP07; target is SP06)
3765635 | 03 Medium | Real-time Overhead Posting Optimization | CO-OM-OPA-OH | 0003600765 | PwC RTR | SNOTE after upgrade (fix ships in S4CORE SP07; target is SP06)
3767916 | 03 Medium | Error F5336 for MM invoice with retention | FI-AP-AP-J | 0003528124 | PwC STP / CFIN | SNOTE after upgrade (no SP assignment in report - check validity in SAP for Me)
3769687 | 03 Medium | Outdated data returned when bypassing buffer for customer-BP assignment read | LO-MD-BP | 0003717181 | PwC OTC / STP | SNOTE after upgrade (fix ships in S4CORE SP07; target is SP06)
3770121 | 03 Medium | Performance issue with filter values in Manage Payments app | FIN-FSCM-PF | 0003765678 | PwC RTR / MBC | SNOTE after upgrade (fix ships in S4CORE SP07; target is SP06)
3770121 | 03 Medium | Performance issue with filter values in Manage Payments app | FIN-FSCM-PF | 0003769603 | PwC RTR / MBC | SNOTE after upgrade (fix ships in S4CORE SP07; target is SP06)
3771425 | 03 Medium | Deferred Tax Transfer: Filling LC Amount and Tax Base Amount When Posting Tax Transfer Document via FB05 | FI-GL-GL-F1 | 0003686849 | PwC RTR / OneSource | SNOTE after upgrade (fix ships in S4CORE SP07; target is SP06)
3771443 | 03 Medium | RLT not taken into account in sales order for discontinued material | SD-BF-AC | 0003566330 | PwC OTC | SNOTE after upgrade (no SP assignment in report - check validity in SAP for Me)
3773923 | 03 Medium | Report R_FAR_MEMOLINE_HEALTH_CHECK has low performance during processing a large number of records during the "Check & Sync" scenario | FI-FIO-AR-PAY | 0003722049 | PwC RTR / MBC | SNOTE after upgrade (fix ships in S4CORE SP07; target is SP06)
3775172 | 03 Medium | BAPI_PO_CHANGE: Item quantity cannot be changed when deletion indicator is set | MM-PUR-PO-BAPI | 0003569976 | PwC STP | SNOTE after upgrade (fix ships in S4CORE SP07; target is SP06)
3775293 | 03 Medium | Reprocess Bank Statement Items - G/L account is not derived correctly due to an unidentified transaction key on open items | FI-FIO-AR-PAY | 0003630931 | PwC RTR / MBC | SNOTE after upgrade (fix ships in S4CORE SP07; target is SP06)
3775777 | 03 Medium | Manage Purchase Contract Partner Deletion issue in draft | MM-FIO-PUR-SQ-CON | 0003500840 | PwC STP | SNOTE after upgrade (fix ships in S4CORE SP07; target is SP06)
3776134 | 03 Medium | ICR: Runtime error TYPELOAD_NEW_VERSION / LOAD_PROGRAM_INTF_MISMATCH | FI-GL-GL-G | 0003670615 | PwC RTR | SNOTE after upgrade (fix ships in S4CORE SP07; target is SP06)
3776693 | 03 Medium | API_PURCHASECONTRACT_PROCESS_SRV Version 2: Purchase Contract header data cleared and empty error details returned in batch changeset | MM-PUR-OA-API | 0003483918 | PwC STP | SNOTE after upgrade (fix ships in S4CORE SP07; target is SP06)
3776844 | 03 Medium | Unallowed delete statement in accounting interface trace in RAP context | AC-INT | 0003652980 | PwC CFIN | SNOTE after upgrade (fix ships in S4CORE SP07; target is SP06)
3777208 | 03 Medium | Revertion of SAP note 3762259 | CA-DMS | 0003762259 | PwC STP / VIM | SNOTE after upgrade (fix ships in SAPBASIS SP07; target is SP06)
3777911 | 03 Medium | wrong ATP result with special stock Q | SD-BF-AC | 0003697546 | PwC OTC | SNOTE after upgrade (fix ships in S4CORE SP07; target is SP06)
3777957 | 03 Medium | No auto split when calling BAPIs to create CO document | CO-OM-CCA-E | 0003482873 | PwC RTR | SNOTE after upgrade (no SP assignment in report - check validity in SAP for Me)
3778390 | 03 Medium | Error during split of schedule lines with FCFS using Forecast and Planning Delivery Schedule - Part 2 | SD-SLS | 0003750729 | PwC OTC | SNOTE after upgrade (fix ships in S4CORE SP07; target is SP06)
3779024 | 03 Medium | CVP EOP: Process switch DISABLE_PARTIAL_BLOCKING wrongly allow partial blocking of vendor company codes | LO-MD-BP-DP | 0003528521 | PwC OTC / STP | SNOTE after upgrade (fix ships in S4CORE SP07; target is SP06)
3779671 | 03 Medium | FSV: FAGL_FSV_TRANSPORT: Entries Not Written to Transport Request | FI-GL-GL-G | 0003668493 | PwC RTR | SNOTE after upgrade (fix ships in S4CORE SP07; target is SP06)
3781049 | 03 Medium | BICS: Exception while adding Bookmark to transport using report FPM_BICS_TRANSPORT_BOOKMARKS | BW-BEX-OT-BICS-PROV | 0003696992 | PwC RTR | SNOTE after upgrade (fix ships in SAPBW SP07; target is SP06)
3781348 | 03 Medium | F2547 - Verify General Journal Entries - Some Journal Entries in status Posted are duplicated | FI-FIO-GL-IS | 0003549709 | PwC RTR | SNOTE after upgrade (fix ships in S4CORE SP07; target is SP06)
3782096 | 03 Medium | SUPC/SU25: Simulation des Abmischvorgangs liefert falsche Ergebnisse | BC-SEC-AUT-PFC | 0003673078 | INTL Security | SNOTE after upgrade (fix ships in SAPBASIS SP07; target is SP06)
3782131 | 03 Medium | Manage Prices - Sales app: Key fields not set in the downloaded failed records excel | SD-MD-CM | 0003669800 | PwC OTC | SNOTE after upgrade (fix ships in S4CORE SP07; target is SP06)
3785315 | 03 Medium | KE25 detail screen shows initial values | CO-PA-IS | 0003572848 | PwC RTR | SNOTE after upgrade (fix ships in S4CORE SP07; target is SP06)
3785382 | 03 Medium | List of Totals Records is not refreshed correctly after changing layout | FIN-SEM-BCS-MD-WB | 0003716499 | INTL Basis | SNOTE after upgrade (no SP assignment in report - check validity in SAP for Me)
3785616 | 03 Medium | Dump during CO-PA extraction | CO-PA | 0003513327 | PwC RTR | SNOTE after upgrade (no SP assignment in report - check validity in SAP for Me)
3785970 | 03 Medium | Kontoauszug: Abbruch in SAPLBSPS wegen DATA_LENGTH_0 | FI-BL-PT-BA | 0003705668 | PwC RTR / MBC | SNOTE after upgrade (fix ships in S4CORE SP07; target is SP06)
3786196 | 03 Medium | WBS Element value disappears in UI | MM-FIO-PUR-REQ-SSP | 0003535740 | PwC STP | SNOTE after upgrade (no SP assignment in report - check validity in SAP for Me)
3787198 | 03 Medium | Validity of multi-level method not considered correctly | FI-AA-AA-B | 0003613486 | PwC RTR | SNOTE after upgrade (no SP assignment in report - check validity in SAP for Me)
3787980 | 03 Medium | CKMCCC: Wrong actual beginning inventory values | CO-PC-ACT | 0003512136 | PwC RTR / ITD | SNOTE after upgrade (fix ships in S4CORE SP07; target is SP06)
3789234 | 03 Medium | Error F5 727 raised for a cash ledger document posted additionally during clearing | FI-GL-GL-J | 0003577393 | PwC CFIN | SNOTE after upgrade (no SP assignment in report - check validity in SAP for Me)
3789840 | 03 Medium | Data Migration to S/4HANA: false positive FINS_RECON 763 for ledgers not used in Asset Accounting; inflated reconciliation total for true positives | FIN-MIG-AA | 0003753135 | PwC RTR / Data Migration | SNOTE after upgrade (fix ships in S4CORE SP07; target is SP06)
3791609 | 03 Medium | Data Migration to S/4HANA: false positive FINS_RECON 773 (LDGRP mismatch) for fully statistical ANEK documents | FIN-MIG-AA | 0003492815 | PwC RTR / Data Migration | SNOTE after upgrade (fix ships in S4CORE SP07; target is SP06)
3792215 | 03 Medium | Custom sorting of catalog lost after implementing note 3760261 | MM-FIO-PUR-REQ-SSP | 0003760261 | PwC STP | SNOTE after upgrade (fix ships in S4CORE SP07; target is SP06)
3792617 | 03 Medium | Parameter adjustment in BAdI FPM_BICS_NAVIGATION not applied by search UIBB | BW-RUI-FPM | 0003723229 | PwC RTR | SNOTE after upgrade (no SP assignment in report - check validity in SAP for Me)
3793529 | 03 Medium | IO304/IO261 during GR/GI for delivery with serialized HU | LE-SHP-GF-SR | 0003608289 | PwC ITD / OTC | SNOTE after upgrade (no SP assignment in report - check validity in SAP for Me)
3793800 | 03 Medium | A2A Sales Order - RATE_EXT -> CONVT_NO_NUMBER - Part 2 | SD-SLS-API | 0003587611 | PwC OTC | SNOTE after upgrade (fix ships in S4CORE SP07; target is SP06)
3795313 | 03 Medium | No SPAU alerts for SAPUI5 SMIM objects deleted via /UI5/MIME_CLEANUP report | CA-UI5-DLV | 0003599156 | INTL Basis | SNOTE after upgrade (fix ships in SAPUI SP07; target is SP06)
3797679 | 03 Medium | Unable to retreive both AL and GOS type attachments using API | CA-DMS | 0003546063 | PwC STP / VIM | SNOTE after upgrade (fix ships in S4CORE SP07; target is SP06)
3797710 | 03 Medium | CVAPI_DOC_MAINTAIN always returns error "Object does not exist" although corresponding object exists in the system | CA-DMS | 0003502891 | PwC STP / VIM | SNOTE after upgrade (no SP assignment in report - check validity in SAP for Me)
3799507 | 03 Medium | ATC / CHECKMAN Error in MM-PUR Application | MM-PUR-GF-PR | 0003713815 | PwC STP | SNOTE after upgrade (fix ships in S4CORE SP07; target is SP06)
3799507 | 03 Medium | ATC / CHECKMAN Error in MM-PUR Application | MM-PUR-GF-PR | 0003743039 | PwC STP | SNOTE after upgrade (fix ships in S4CORE SP07; target is SP06)
3802611 | 03 Medium | Hierarchy node selected from value help reported as wrong | BW-RUI-FPM | 0003712499 | PwC RTR | SNOTE after upgrade (fix ships in SAPBW SP07; target is SP06)
3805046 | 03 Medium | Cleanup of unused shadow DDIC objects | CA-LT-MIG | 0003706755 | PwC Data Migration | SNOTE after upgrade (fix ships in S4CORE SP07; target is SP06)
3806085 | 03 Medium | Error FAA_CFG_ACCESS 301 ('Depreciation key is not assigned') during asset transfer | FI-AA-AA-B | 0003549734 | PwC RTR | SNOTE after upgrade (no SP assignment in report - check validity in SAP for Me)
3809759 | 03 Medium | VL06: Freight Order Column Empty in Internal Transportation Management Integration | LE-SHP-GF | 0003546926 | PwC ITD / OTC | SNOTE after upgrade (fix ships in S4CORE SP07; target is SP06)
3809759 | 03 Medium | VL06: Freight Order Column Empty in Internal Transportation Management Integration | LE-SHP-GF | 0003757276 | PwC ITD / OTC | SNOTE after upgrade (fix ships in S4CORE SP07; target is SP06)
3809759 | 03 Medium | VL06: Freight Order Column Empty in Internal Transportation Management Integration | LE-SHP-GF | 0003685456 | PwC ITD / OTC | SNOTE after upgrade (fix ships in S4CORE SP07; target is SP06)
3809759 | 03 Medium | VL06: Freight Order Column Empty in Internal Transportation Management Integration | LE-SHP-GF | 0003608778 | PwC ITD / OTC | SNOTE after upgrade (fix ships in S4CORE SP07; target is SP06)
3809759 | 03 Medium | VL06: Freight Order Column Empty in Internal Transportation Management Integration | LE-SHP-GF | 0003622045 | PwC ITD / OTC | SNOTE after upgrade (fix ships in S4CORE SP07; target is SP06)
3810261 | 03 Medium | Value Help and Planning Sequence: Fix note 3676079 | BW-BEX-OT-BICS-INA | 0003676079 | PwC RTR | SNOTE after upgrade (fix ships in SAPBW SP07; target is SP06)
3830404 | 03 Medium | DRC U.S. - FormInstanceTaxItems Endpoint Call Fails Due to Wrong Parameter Format | FI-LOC-FI-US-SUT | 0003684090 | PwC DRC | SNOTE after upgrade (fix ships in S4CORE SP07; target is SP06)
3830831 | 03 Medium | Error message VL 632 with blank characters leads to dump CX_SY_REPLACE_INFINITE_LOOP | LE-SHP-GF | 0003663623 | PwC ITD / OTC | SNOTE after upgrade (fix ships in S4CORE SP07; target is SP06)
3533859 | 04 Low | CVI_BDT: Dynpro 0023 of function group CVI_FS_UI_CUSTOMER mistakenly created in ERP systems as downport from S4CORE | FS-BP | 0003501035 | PwC OTC / STP | SNOTE after upgrade (no SP assignment in report - check validity in SAP for Me)
3663413 | 04 Low | Webgui Data aging: virtual file system deleted on startup | BC-FES-WGU | 0003613566 | INTL Basis | SNOTE after upgrade (no SP assignment in report - check validity in SAP for Me)
3684513 | 04 Low | Remove Deprecated SAP__* entity from Odata service | IS-LS-ICS-OPS-DEL | 0003457369 | INTL Basis | SNOTE after upgrade (no SP assignment in report - check validity in SAP for Me)
3749544 | 04 Low | Support program for deletion of CO-PA characteristics[2] | CO-PA-ST | 0003605401 | PwC RTR | SNOTE after upgrade (fix ships in S4CORE SP07; target is SP06)
3764577 | 04 Low | API Release: Enhanced change evaluation for CDS view annotations in API compatibility ATC check | BC-SRV-APS-EXT-REL | 0003745539 | PwC Technical | SNOTE after upgrade (fix ships in SAPBASIS SP07; target is SP06)
3764577 | 04 Low | API Release: Enhanced change evaluation for CDS view annotations in API compatibility ATC check | BC-SRV-APS-EXT-REL | 0003749331 | PwC Technical | SNOTE after upgrade (fix ships in SAPBASIS SP07; target is SP06)
3770825 | 04 Low | API Release: Enhanced change evaluation for DDLS in API compatibility ATC check | BC-DWB-DIC | 0003745539 | PwC Technical | SNOTE after upgrade (fix ships in SAPBASIS SP07; target is SP06)
3770825 | 04 Low | API Release: Enhanced change evaluation for DDLS in API compatibility ATC check | BC-DWB-DIC | 0003749331 | PwC Technical | SNOTE after upgrade (fix ships in SAPBASIS SP07; target is SP06)
3781224 | 04 Low | CVI_CIF: KNA1 data not saved when maintained through complex interface with current state | CA-FS-CVI | 0003617764 | PwC OTC / STP | SNOTE after upgrade (fix ships in S4CORE SP07; target is SP06)
3806214 | 04 Low | Custom Business Configurations app (F4579): Short dump when search field and filter is used together | BC-CUS-TOL-MBC | 0003741477 | INTL Basis | SNOTE after upgrade (fix ships in SAPBASIS SP07; target is SP06)
3831697 | 04 Low | F4485 schreibt keine Nachrichten zum Storno ins Protokoll | FI-FIO-AR | 0003724924 | PwC OTC | SNOTE after upgrade (no SP assignment in report - check validity in SAP for Me)

## Roles
Roles used in this plan
Allocation follows INTL guidance: PwC functional and technical; INTL Basis owns Basis and the SAP relationships; INTL Security collaborates.
Code | Role | Who | Scope
INTL-BAS | INTL Basis | Girish Ogirala (lead) + 1 onsite + 2 offshore | Technical owner of the upgrade; SRs, copies, post-processing, transports, weekend coordination
INTL-SEC | INTL SAP Security | Security team (collaborates with Basis) | SU25/SU24, PFCG roles, GRC AC post-steps, SailPoint and SDMI users
INTL-PMO | INTL PMO | Project NorthStar PMO | Plan, gates, steering, communications
INTL-TST | INTL Test Lead | NorthStar test management | Regression scope, qTest/ADO tracking, UAT coordination
INTL-PO | INTL PO / IT Leads | Business product owners and IT leads | UAT execution and business sign-off
PwC-TEC | PwC Technical | PwC technical team | SPDD/SPAU, notes, custom code, ATC, Fiori custom apps, RICEFW unit tests
PwC-FUN | PwC Functional | PwC functional streams | SI-check application items, regression testing, integration flows
PwC-DM | PwC Data Migration | PwC data migration (Syniti) | Mock loads, Syniti alignment, migration validation on SPS06
SAP-ECS | SAP ECS | SAP Enterprise Cloud Services (via SRs) | System copies, SUM execution, HANA/kernel, backups, technical FES upgrade
SAP-MAX | SAP MaxAttention | SAP MaxAttention engagement team | Plan safeguarding, issue escalation, weekend/go-live support
SAP-BTP | SAP BTP team | SAP BTP team (from SAP) | AFC, MBC, DRC, Work Zone tenants, Cloud Connector guidance
VENDOR | Partner vendors | OpenText, Thomson Reuters, SailPoint, Syniti | Compatibility statements and partner-specific steps

## Read Me
Read me - how this workbook works
CONFIDENTIAL AND PROPRIETARY TO INTERNATIONAL ¦ Plan v4.0 (18 Oct 2026)
Daily update (3 steps)
1. Exec Summary | Set "As of" to today. Check Overall status, the headline and the three key messages. Update team alignment and leadership asks.
2. Schedule | Set Status on each task and gate row (drop-down). Phase rows, % complete, Milestones and the Detail Plan follow automatically. Change Start/Finish only when a date really moves.
3. Dashboard | Open NorthStar_SPS06_Upgrade_Dashboard.html, choose "Update data" and pick this file (or drop it on the page). The file is read in your browser; nothing is uploaded.
Tabs
Schedule | The plan in MS Project style: one line per step, verb first, with the team that performs it. Click the [-] buttons on the left to collapse to phases.
Exec Summary | What leaders see first on the dashboard: status, headline, key messages, team alignment, asks.
Milestones | Gates G0-G5 with their exit criteria, upgrade weekends and project dates.
Detail Plan | Reference detail behind each Schedule row (what exactly, deliverable, sources, notes). Column B links to the Schedule.
Other tabs | Systems, SR Tracker, RAID, Sandbox Test Plan, Integrations, Vendor Questions (with e-mail drafts), Transport Windows, SAP Teams, Guide Checklist, RACI, Project Calendar, Stream Test Focus, SAP Notes (In-Scope), Roles.
Do not rename | Sheet names and column headers: the dashboard finds data by these names. Insert new Schedule rows inside a phase so the phase roll-up includes them, and give them Type Task or Milestone.
Yellow cells | Cells you are expected to edit.
Status values
Not Started | Gray - Not started yet
On Track | Green - In progress and on plan
Complete | Green - Done and evidenced
At Risk | Yellow - In progress, may miss its date - action needed
Blocked | Red - Cannot proceed - escalation needed
Overdue | Calculated: Finish before "As of" and Status not Complete. The Finish date turns red; the dashboard counts it.
Teams
INTL Basis | INTL Basis: Girish Ogirala (lead) + 1 onsite + 2 offshore. Technical owner of the upgrade; SRs, copies, post-processing, transports, weekend coordination
INTL Security | INTL SAP Security: Security team (collaborates with Basis). SU25/SU24, PFCG roles, GRC AC post-steps, SailPoint and SDMI users
INTL PMO | INTL PMO: Project NorthStar PMO. Plan, gates, steering, communications
INTL Testing | INTL Test Lead: NorthStar test management. Regression scope, qTest/ADO tracking, UAT coordination
Business (UAT) | INTL PO / IT Leads: Business product owners and IT leads. UAT execution and business sign-off
PwC Tech | PwC Technical: PwC technical team. SPDD/SPAU, notes, custom code, ATC, Fiori custom apps, RICEFW unit tests
PwC Functional | PwC Functional: PwC functional streams. SI-check application items, regression testing, integration flows
PwC Data Migration | PwC Data Migration: PwC data migration (Syniti). Mock loads, Syniti alignment, migration validation on SPS06
SAP ECS | SAP ECS: SAP Enterprise Cloud Services (via SRs). System copies, SUM execution, HANA/kernel, backups, technical FES upgrade
SAP MaxAttention | SAP MaxAttention: SAP MaxAttention engagement team. Plan safeguarding, issue escalation, weekend/go-live support
SAP BTP | SAP BTP team: SAP BTP team (from SAP). AFC, MBC, DRC, Work Zone tenants, Cloud Connector guidance
Vendors | Partner vendors: OpenText, Thomson Reuters, SailPoint, Syniti. Compatibility statements and partner-specific steps
Sources
SR | SAP for Me SR 31018471 log (XS4 update), as uploaded
MP | Maintenance Plan 1002693650 (plan PDF, stack file, download list)
UG | Upgrade Guide for SAP S/4HANA Cloud Private Edition 2023, version 6.0 (UPGR_PE2023.pdf); section numbers quoted
SER | Side-effect report for MP 1002693650 (uploaded export) - note numbers quoted
POAP | Project NorthStar Plan on a Page (updated 9/21) and project dates given by INTL
USER | Decisions and facts stated by Girish Ogirala (INTL Basis)
Fallback plans
Plan B | Plan B (ECS cannot meet a window, or G1 fails): shift the chain by one week - XS4 31 Oct, DS4 7 Nov (after SIT2, so DS5 is not needed for SIT2 fixes), QS4 14 Nov, SS4 21 Nov, PS4 28 Nov (Thanksgiving weekend). G5 moves to Wed 2 Dec, inside the Go/No-Go week; UAT weeks 1-2 run on FPS02 and weeks 3-4 on SPS06.
Plan C | Plan C (G3 fails): SS4 and PS4 stay on FPS02 and go live on FPS02. DS5 and QS5 (FPS02 copies) become the delivery line for fixes to SS4 and PS4; DS4 and QS4 stay on SPS06 as the post-go-live upgrade line. Remaining systems are upgraded after hypercare.
Time zone | Dates and times are US Central (the SR log uses America/Chicago). ECS windows are agreed in UTC.

## Lists (hidden)
Status | Colour | Role code | Workstream | Phase
Not Started | Gray | INTL-BAS | GOV | P0
On Track | Green | INTL-SEC | TEC | P1
Complete | Green | INTL-PMO | CODE | P2
At Risk | Yellow | INTL-TST | SEC | P3
Blocked | Red | INTL-PO | INT | P4
|  | PwC-TEC | FIO | P5
|  | PwC-FUN | TST | P6
|  | PwC-DM | DM | P7
SAP-ECS
SAP-MAX
SAP-BTP
VENDOR