## Read Me
Project NorthStar ¦ S/4HANA 2023 FPS02 -> SPS06 Upgrade Plan - OPTION: with Tricentis test automation
Updated 6 Oct 2026 ¦ Project dates from the Plan on a Page (updated 9/21) ¦ Inputs: Maintenance Planner 1002693650 software catalog + side-effect report
How to use
Integrated Timeline: the Plan on a Page (weeks W1-W25) with the SPS06 upgrade swimlanes underneath. Copy the upgrade rows into the master plan to embed it.
Detailed Plan: task-level plan with owners, dependencies and an automatic Gantt (edit Start/End and the bars move).
Plan Update: what changed between the 5-March Testing Overview and the 9/21 Plan on a Page, and what it does to the upgrade.
Gates, Systems & Transports, Test Strategy, Test Automation & TMS, Stream Test Focus, Compatibility, RACI, RAID, SAP Notes (In-Scope): supporting tabs.
Strategy in one line
Upgrade at phase boundaries: prove on Sandbox, the idle N+1 Dev and QS5 (automated Tricentis pack, FPS02 baseline vs SPS06) in October; upgrade QS4 on 24-25 Oct so SIT2 weeks 5-6 run on SPS06 with a re-run of passed P1 scripts; upgrade SS4 + DS4 on 6-8 Nov between Mock3 / performance testing and UAT so all of UAT runs on SPS06; upgrade PRD on 13-15 Nov, before Go/No-Go and cutover.
Key facts
FPS vs SPS: S/4HANA 2023 had three feature packs (FPS01-FPS03); from SP04 SAP ships support packs (SPS). Target = SPS06 (S4CORE 108 SP06). The jump from FPS02 crosses FPS03, so full regression applies.
Side-effect notes: 870 pairs triaged -> 135 in-scope notes, all to be implemented with SNOTE after the upgrade (none are contained in SPS06). See SAP Notes (In-Scope) tab and the separate register workbook.
Assumptions
Dates from the Plan on a Page (updated 9/21): SIT2 28 Sep - 6 Nov (QS4/200); Mock2 Tx data to 11 Oct (QS4/200); performance testing about 14 Oct - 6 Nov and Mock3 19 Oct - 6 Nov (SS4/100); UAT 9 Nov - 4 Dec (SS4/100); cutover 7 - 31 Dec (PRD); go-live 1 Jan 2027.
Go/No-Go is placed at the end of UAT (30 Nov - 4 Dec). Dress rehearsal and hypercare dates are to be confirmed and are not invented here.
DRC = SAP Document and Reporting Compliance deployment for Mexico (21 Sep - 3 Oct, complete). TR onsite = Thomson Reuters on site for OneSource integration (w/c 12 Oct, 9 Nov, 7 Dec); not an upgrade constraint, used for OneSource validation.
Legacy systems stay connected to QS4 until SIT2 ends (6 Nov) and are repointed to SS4 before UAT starts (9 Nov) - repoint date to be confirmed.
N+1 is the upgrade line: N+1 Dev is upgraded first, then QS5 (N+1 QA); both are idle until N+1 activation (Mon 2 Nov). The N+1 Dev SID is to be confirmed (task 0.3).
SAP ECS executes SUM (RISE PCE); INTL Basis coordinates; PwC Technical performs SPDD/SPAU. Downtime per system is confirmed from the Sandbox run.
Central Finance runs in the same S/4HANA system; SLT replication is paused around each target upgrade.
PRD exists on FPS02 and has no business data until cutover (7 Dec).
Countries US, CA, MX; English only. S/4HCM, IS-OIL, IS-UT, IS-PRA, IS-PS-CA, IBP are not in test scope (catalog "No").
Test automation (option): Tricentis Tosca is available (qTest is already in use with ADO) and scripts exist from the Jun-Jul Automation Scripting track. QS5-100 is the automation client until 30 Oct; afterwards automation runs in QS4-200 and as smoke in SS4-100. No automation in PRD.
Contingency
Plan B (ECS lead time or Sandbox issue): shift the chain by 1 week. Sandbox 20 Oct, N+1 Dev 26-27 Oct, QS5 28-29 Oct, QS4 31 Oct - 1 Nov (still inside SIT2, week 6 only on SPS06), P1 re-run 2-11 Nov, G3 12 Nov, SS4+DS4 13-15 Nov (UAT week 1 on FPS02, about 1 day UAT pause), PRD 20-22 Nov. Still closes before Go/No-Go (30 Nov).
Automation fallback: if the QS5-100 copy or agents are not ready by 15 Oct, capture the FPS02 automated baseline in QS4-200 during SIT2 (19-23 Oct) and run the SPS06 pack in QS4-200 from 26 Oct. Gate dates do not change.
Plan C (G3 fails): SS4, DS4 and PRD stay on FPS02; UAT and go-live run on FPS02. QS4, N+1 Dev and QS5 stay on SPS06 as the post-go-live upgrade line (QS4 can be restored from the 23 Oct ECS backup if required, losing SIT2 data since). Remaining tiers are upgraded after hypercare.

## Integrated Timeline
PROJECT NORTHSTAR: PLAN ON A PAGE (9/21) + SPS06 UPGRADE OVERLAY - option with automation
|  | AUG |  |  |  |  | SEP |  |  |  | OCT |  |  |  | NOV |  |  |  |  | DEC |  |  |  | JAN
|  | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13 | W14 | W15 | W16 | W17 | W18 | W19 | W20 | W21 | W22 | W23 | W24 | W25
Workstream | System | 2026-08-03 | 2026-08-10 | 2026-08-17 | 2026-08-24 | 2026-08-31 | 2026-09-07 | 2026-09-14 | 2026-09-21 | 2026-09-28 | 2026-10-05 | 2026-10-12 | 2026-10-19 | 2026-10-26 | 2026-11-02 | 2026-11-09 | 2026-11-16 | 2026-11-23 | 2026-11-30 | 2026-12-07 | 2026-12-14 | 2026-12-21 | 2026-12-28 | 2027-01-04 | 2027-01-11 | 2027-01-18
SIT1 - OTC | QS4 100 | 2026-08-03: Test Execution; 2026-09-14: Extended Testing
SIT1 - All other WS | QS4 100 | 2026-09-14: Defects Remediation
Mock Load 2 | QS4 200 | 2026-09-07: Master Data; 2026-09-28: Tx Data
OneSource |  | 2026-09-07: OS Build and Unit Test
Test Planning & Execution |  | 2026-09-14: TC scope, upload, stitching
Volume & Complexity Plan |  | 2026-09-14: Plan aligned & published
SIT2 | QS4 200 | 2026-09-28: Test Execution
Mock Load 3 | SS4 100 | 2026-10-19: Mock Load 3
Performance Testing | SS4 100 | 2026-10-12: SAP Performance Testing
UAT | SS4 100 | 2026-11-09: UAT
Go / No-Go (at UAT end) |  | 2026-11-30: Go/No-Go
Cutover | PROD | 2026-12-07: Cutover
DRC (Mexico) / TR onsite |  | 2026-09-21: DRC MX deploy; 2026-10-12: TR; 2026-11-09: TR; 2026-12-07: TR
Go-live | PROD | 2026-12-28: GO-LIVE 1 Jan
S/4HANA 2023 FPS02 -> SPS06 UPGRADE OVERLAY ¦ Sandbox -> N+1 Dev -> QS5 -> QS4/200 (inside SIT2) -> SS4 + DS4 (before UAT) -> PRD ¦ SAP ECS executes SUM
Sandbox (basic validation) | SBX | 2026-10-12: UPG 13-14 Oct; smoke; G1
N+1 Dev (dev integrity) | N+1 | 2026-10-12: Sync with DS4; 2026-10-19: UPG 19-20 Oct; SPDD/SPAU; 2026-10-26: ATC + unit tests; DS4 retrofit
QS5 100 (N+1 QA, automation) | QS5 | 2026-10-05: Copy QS4-200 10-11 Oct; 2026-10-12: Harden + FPS02 baseline; 2026-10-19: UPG 21-22 Oct; auto run; 2026-10-26: Auto runs; cut-over 30 Oct
QS4 100/200 (inside SIT2) | QS4 | 2026-10-19: FPS02 baseline 23 Oct; UPG 24-25 Oct; 2026-10-26: SIT2 wks 5-6 on SPS06 + P1 re-run (automated nightly)
SS4 pre-prod + DS4 | SS4 | 2026-11-02: UPG 6-8 Nov; 2026-11-09: All of UAT on SPS06; perf delta 9-13 Nov; TR onsite
PRD | PRD | 2026-11-09: Import hold; UPG 13-15 Nov; 2026-11-16: Tech verify; 2026-12-07: Cutover on SPS06
INTL Basis / SAP ECS |  | 2026-10-05: ECS SRs + rules; 2026-10-12: Post-steps each tier, Work Zone re-sync, interfaces; 2026-11-16: SPS06 side-effect watch
INTL Security |  | 2026-10-12: SU25 dry run; 2026-10-19: SU25 in N+1; 2026-10-26: Role regression + GRC; 2026-11-09: SS4/PRD roles
PwC Technical |  | 2026-10-05: Notes check; 2026-10-12: SPAU proto; 2026-10-19: SPDD/SPAU, notes, ATC, tests; 2026-11-02: UPG defect fixes
PwC Functional streams |  | 2026-10-05: Modules + vendor checks; 2026-10-12: SBX smoke; 2026-10-26: P1 re-run QS4/200; 2026-11-09: Support UAT
INTL + PwC Test Leads |  | 2026-10-05: Regression set in qTest; 2026-10-19: FPS02 baseline; 2026-10-26: Track UPG-SPS06 defects; 2026-11-09: Perf delta SS4
Tricentis automation (INTL) |  | 2026-10-05: Scope + coverage; 2026-10-12: Agents, users, scripting; 2026-10-19: SPS06 run QS5; 2026-10-26: Nightly runs QS4-200; 2026-11-09: SS4 smoke 9 Nov; 2026-12-14: Pack to N+1
PwC CFIN |  | 2026-10-05: SLT runbook; 2026-10-19: SLT pause 23 / resume 26 Oct; 2026-11-02: SLT pause/resume SS4
PMO & gates (INTL) |  | 2026-10-05: G0 9 Oct; 2026-10-12: G1 16 Oct; 2026-10-19: G2 23 Oct; 2026-11-02: G3 5 Nov; 2026-11-09: G4 12 Nov; 2026-11-16: G5 20 Nov; 2026-11-30: Go/No-Go
Legend: grey = complete (before 6 Oct) ¦ dark blue = project phase ¦ light blue = DRC / TR onsite ¦ orange = system upgrade window (SAP ECS) ¦ light orange = upgrade work ¦ charcoal = gate / go-live. Weekly granularity: bars cover whole weeks; exact dates in the bar text.
Plan B (ECS lead time or Sandbox issue): shift the chain by 1 week. Sandbox 20 Oct, N+1 Dev 26-27 Oct, QS5 28-29 Oct, QS4 31 Oct - 1 Nov (still inside SIT2, week 6 only on SPS06), P1 re-run 2-11 Nov, G3 12 Nov, SS4+DS4 13-15 Nov (UAT week 1 on FPS02, about 1 day UAT pause), PRD 20-22 Nov. Still closes before Go/No-Go (30 Nov).
Automation fallback: if the QS5-100 copy or agents are not ready by 15 Oct, capture the FPS02 automated baseline in QS4-200 during SIT2 (19-23 Oct) and run the SPS06 pack in QS4-200 from 26 Oct. Gate dates do not change.
Plan C (G3 fails): SS4, DS4 and PRD stay on FPS02; UAT and go-live run on FPS02. QS4, N+1 Dev and QS5 stay on SPS06 as the post-go-live upgrade line (QS4 can be restored from the 23 Oct ECS backup if required, losing SIT2 data since). Remaining tiers are upgraded after hypercare.

## Plan Update
What changed: 5-March Testing Overview -> Plan on a Page (9/21)
Impact on the SPS06 upgrade
Item | 5-March plan | Plan on a Page (9/21) | Impact on the upgrade
SIT2 (QS4/200) | 28 Sep - 11 Oct, defects to 25 Oct | 28 Sep - 6 Nov | QS4 upgrade (24-25 Oct) now falls inside SIT2: weeks 5-6 run on SPS06
Mock Load 2 (QS4/200) | to 13 Sep (+ defects to 4 Oct) | Master data 7-27 Sep; Tx data 28 Sep - 11 Oct | Complete before the QS4 window
Performance testing (SS4/100) | not shown | about 14 Oct - 6 Nov | Runs on FPS02: add a performance delta check on SPS06 (9-13 Nov)
Mock Load 3 (SS4/100) | 5 - 25 Oct | 19 Oct - 6 Nov | Ends the day the SS4 window opens: reconciliation sign-off by Fri 6 Nov 12:00
UAT (SS4/100) | 26 Oct - 22 Nov | 9 Nov - 4 Dec | All of UAT runs on SPS06; no UAT pause needed
Go / No-Go | 23 Nov - 6 Dec | end of UAT (30 Nov - 4 Dec) | G5 (20 Nov) feeds it with the upgrade sign-off
Cutover (PRD) | 14 - 27 Dec | 7 - 31 Dec | PRD upgraded 13-15 Nov, before cutover
Go-live | w/c 4 Jan 2027 | 1 Jan 2027 | Dress rehearsal and hypercare dates to be confirmed
DRC Mexico / TR onsite | - | DRC MX deploy 21 Sep - 3 Oct; TR onsite w/c 12 Oct, 9 Nov, 7 Dec | No constraint; TR week 9 Nov validates OneSource on SPS06 in UAT

## Detailed Plan
Detailed Upgrade Plan
Bars are conditional formatting driven by Start/End. Week columns start Monday.
ID | Phase | Task | System / client | Start | End | Work days | Org | Responsible | Depends on | Deliverable / exit | Status | 2026-10-05 | 2026-10-12 | 2026-10-19 | 2026-10-26 | 2026-11-02 | 2026-11-09 | 2026-11-16 | 2026-11-23 | 2026-11-30 | 2026-12-07 | 2026-12-14 | 2026-12-21 | 2026-12-28 | 2027-01-04
0.1 | 0 Mobilize | Upgrade kick-off; baseline this plan against the Plan on a Page (9/21) | - | 2026-10-07 | 2026-10-07 |  | INTL | PMO | - | Plan baselined; owners named | Not started
0.2 | 0 Mobilize | Raise SAP ECS service requests for every upgrade window (Sandbox, N+1 Dev, QS5, QS4, SS4+DS4, PRD) incl. HANA revision + kernel, plus client export QS4-200 -> QS5-100 | All | 2026-10-07 | 2026-10-07 |  | INTL | Basis | 0.3 | ECS confirms dates and downtime in writing | Not started
0.3 | 0 Mobilize | Confirm N+1 SIDs and transport routes N+1 Dev -> QS5 and N+1 Dev -> QS4/SS4/PRD for upgrade adjustment transports | N+1 | 2026-10-07 | 2026-10-08 |  | INTL | Basis | - | Landscape map signed off | Not started
0.4 | 0 Mobilize | Confirm Maintenance Planner transaction 1002693650 (stack.xml) is used unchanged for every system | All | 2026-10-07 | 2026-10-08 |  | INTL | Basis | - | Same stack in all tiers | Not started
0.5 | 0 Mobilize | Validate the 135 in-scope side-effect notes in SAP for Me; streams confirm Yes/No on the 47 conditional module groups | - | 2026-10-07 | 2026-10-09 |  | PwC | Technical + stream leads | - | Final note bundle list | Not started
0.6 | 0 Mobilize | Vendor / service confirmations: OpenText VIM, Thomson Reuters OneSource (use TR onsite week of 12 Oct), Taulia (if used), AFC, DRC, MBC, Work Zone | - | 2026-10-07 | 2026-10-16 |  | INTL + PwC | Basis + stream leads | - | Written confirmations filed (Compatibility tab) | Not started
0.7 | 0 Mobilize | Define the SPS06 regression set in qTest: SIT2 P1 scripts per stream to re-run after the QS4 upgrade; record FPS02 results by 23 Oct | - | 2026-10-07 | 2026-10-16 |  | INTL + PwC | INTL Test Lead + PwC Test Lead | - | Tagged regression set with owners | Not started
0.8 | 0 Mobilize | Publish transport rules (windows A-D), defect tag UPG-SPS06 in ADO/qTest, comms calendar | - | 2026-10-07 | 2026-10-09 |  | INTL | PMO + Basis | 0.3 | Rules published | Not started
0.9 | 0 Mobilize | CFIN runbook: pause/resume SLT replication and AIF checks around each target upgrade | QS4/SS4 | 2026-10-07 | 2026-10-16 |  | PwC + INTL | CFIN + Basis | - | Runbook approved | Not started
0.10 | 0 Mobilize | Tricentis scope: confirm Tosca (SAP GUI + Fiori engines), DEX agents, LiveCompare (optional); map existing scripts to the P1 set (automated coverage %) | - | 2026-10-07 | 2026-10-09 |  | INTL | INTL Test Lead (automation) | - | Automation scope and coverage baseline | Not started
0.11 | 0 Mobilize | TMS design for automation: extended transport control DS4.110 -> existing QS4 clients + QS5.100 (same import order as QS4.200) until N+1 activation; cut-over rule for 2 Nov | QS4, QS5 | 2026-10-07 | 2026-10-09 |  | INTL | Basis | 0.3 | TMS change approved | Not started
G0 | Gate | G0 Mobilized: ECS dates confirmed, landscape map signed | - | 2026-10-09 | 2026-10-09 |  | INTL | PMO (Steering) | 0.2,0.3 | Go for Sandbox | Not started
A.1 | 1A QS5-100 automation | Client export QS4-200 (SCC8) and import into QS5-100 (SCC7) while both are on FPS02 | QS4 -> QS5 | 2026-10-10 | 2026-10-11 |  | SAP ECS + INTL | ECS / Basis | 0.2, 0.11 | QS5-100 = QS4-200 config, master and test data | Not started
A.2 | 1A QS5-100 automation | Post-copy hardening: BDLS, SM59, IDoc ports/partners, SOAMANAGER ports, SCOT; disable or stub Ariba CIG, MBC, DRC/PAC, SLT/CFIN, AIF outbound | QS5-100 | 2026-10-12 | 2026-10-13 |  | INTL + PwC | Basis + CFIN | A.1 | No outbound to real endpoints (checklist signed) | Not started
A.3 | 1A QS5-100 automation | Enable SAP GUI scripting (sapgui/user_scripting, user_scripting_per_user) on QS5, QS4, SS4 only; S_SCR in automation role only; never PRD | QS5, QS4, SS4 | 2026-10-12 | 2026-10-13 |  | INTL | Basis + Security | 0.2 | Scripting active for automation users only | Not started
A.4 | 1A QS5-100 automation | Automation persona users with production-like roles; SECPOL password policy for automation users; credentials in Tosca vault | QS5, QS4, SS4 | 2026-10-12 | 2026-10-14 |  | INTL | Security | A.3 | Users and roles ready | Not started
A.5 | 1A QS5-100 automation | Tosca DEX agents (SAP GUI + browser) with network path to RISE QS5/QS4/SS4; Tosca -> qTest results, qTest -> ADO defects (UPG-SPS06) | - | 2026-10-12 | 2026-10-14 |  | INTL | INTL Test Lead (automation) | 0.10 | Agents execute a hello-world SAP test | Not started
A.6 | 1A QS5-100 automation | Harden P1 automated scenarios; Tosca test data (TDS); environment as Tosca test configuration parameter (QS5 / QS4 / SS4) | QS5-100 | 2026-10-12 | 2026-10-20 |  | INTL + PwC | INTL automation + PwC functional | A.5 | Stable P1 automated pack | Not started
A.7 | 1A QS5-100 automation | FPS02 baseline automated run in QS5-100 (expected results before the upgrade) | QS5-100 | 2026-10-15 | 2026-10-20 |  | INTL | INTL automation | A.2, A.6 | Baseline results in qTest | Not started
A.8 | 1A QS5-100 automation | Optional LiveCompare impact analysis: Sandbox (SPS06) vs QS4 (FPS02), SIT2 usage as proxy for production usage | Sandbox, QS4 | 2026-10-15 | 2026-10-20 |  | INTL | INTL Test Lead + Basis | 1.1 | Most-at-risk list drives test priority | Not started
1.1 | 1 Sandbox | Backup + SUM run: HANA 2.0 SPS08 rev 89.5, kernel 916, SPAM 0095, SPS06 stack | Sandbox | 2026-10-13 | 2026-10-14 |  | SAP ECS | ECS | G0 | Upgrade log, runtime and downtime measured | Not started
1.2 | 1 Sandbox | Technical post-checks: SICK, SM21, ST22, SGEN, STMS, SM59, SMICM, /UI2/INVALIDATE_GLOBAL_CACHES, /UI5/APP_INDEX_CALCULATE | Sandbox | 2026-10-15 | 2026-10-15 |  | INTL | Basis | 1.1 | Checklist signed | Not started
1.3 | 1 Sandbox | SPDD/SPAU prototype and note bundle trial (HotNews 3563542, 3777415 first) | Sandbox | 2026-10-15 | 2026-10-16 |  | PwC | Technical | 1.1 | SPAU worklist + effort for Dev | Not started
1.4 | 1 Sandbox | SU25 dry run after notes 3809657 / 3782096 | Sandbox | 2026-10-15 | 2026-10-16 |  | INTL | Security | 1.3 | Role delta list | Not started
1.5 | 1 Sandbox | "Nothing broken" smoke: key T-codes, Fiori launchpad and Work Zone tiles, RFC/IDoc/AIF ping (0.5 day per stream); OneSource smoke with TR if connected in Sandbox | Sandbox | 2026-10-15 | 2026-10-16 |  | PwC | Stream leads | 1.2 | Smoke checklist passed | Not started
G1 | Gate | G1 Sandbox sign-off; downtime per system confirmed with ECS | - | 2026-10-16 | 2026-10-16 |  | INTL | PMO (Steering) | 1.1-1.5 | Go for N+1 Dev | Not started
2.0 | 2 N+1 Dev / QS5 | Sync N+1 Dev with all DS4 transports released since its copy (same SP level, before upgrade) | N+1 Dev | 2026-10-12 | 2026-10-16 |  | INTL | Basis | 0.3 | N+1 Dev = DS4 object state | Not started
2.1 | 2 N+1 Dev / QS5 | SUM run on N+1 Dev with SPDD during SUM | N+1 Dev | 2026-10-19 | 2026-10-20 |  | SAP ECS + PwC | ECS / Technical | G1, 2.0 | N+1 Dev on SPS06 | Not started
2.2 | 2 N+1 Dev / QS5 | SPAU + note bundle (SNOTE) recorded in transports for reuse in QS5, QS4, SS4, DS4, PRD | N+1 Dev | 2026-10-20 | 2026-10-22 |  | PwC | Technical | 2.1 | Released SPDD/SPAU/note transports | Not started
2.3 | 2 N+1 Dev / QS5 | SU25 steps 2a-2d, SU24 and role adjustments in transports | N+1 Dev | 2026-10-20 | 2026-10-22 |  | INTL | Security | 2.1 | Role transports released | Not started
2.4 | 2 N+1 Dev / QS5 | ATC custom-code run and RICEFW unit tests (interfaces, enhancements, forms, workflows, custom Fiori) | N+1 Dev | 2026-10-21 | 2026-10-30 |  | PwC | Technical | 2.2 | Unit-test evidence; zero priority-1 ATC findings | Not started
2.5 | 2 N+1 Dev / QS5 | Retrofit: import new DS4 transports into N+1 Dev weekly (FPS02 -> SPS06 direction only) | N+1 Dev | 2026-10-19 | 2026-11-06 |  | INTL | Basis | 2.1 | Retrofit log | Not started
2.6 | 2 N+1 Dev / QS5 | SUM run on QS5 (N+1 QA) importing SPDD; SPAU, note and role transports imported after SUM | QS5 | 2026-10-21 | 2026-10-22 |  | SAP ECS + INTL | ECS / Basis | 2.1, A.7 | QS5 on SPS06 before N+1 activation (2 Nov) | Not started
2.7 | 2 N+1 Dev / QS5 | Automated regression run 1 on SPS06 in QS5-100; compare with FPS02 baseline; triage differences | QS5-100 | 2026-10-22 | 2026-10-23 |  | INTL + PwC | INTL automation + PwC functional | 2.6 | Upgrade-caused differences logged (UPG-SPS06) | Not started
G2 | Gate | G2 Dev ready: adjustment transports released, no blocking unit-test failure, automated P1 run on SPS06 in QS5-100 without upgrade blockers | - | 2026-10-23 | 2026-10-23 |  | INTL | PMO (Steering) | 2.2,2.3,2.7 | Go for QS4 | Not started
3.0 | 3 QS4 (inside SIT2) | SIT2 checkpoint: record FPS02 pass/fail per script in qTest by Fri 23 Oct (baseline for defect attribution) | QS4/200 | 2026-10-19 | 2026-10-23 |  | INTL + PwC | INTL Test Lead + PwC Test Lead | 0.7 | FPS02 SIT2 baseline frozen | Not started
3.1 | 3 QS4 (inside SIT2) | Pause SLT replication into QS4; drain AIF / qRFC queues; SIT2 pause notice for the weekend | QS4 | 2026-10-23 | 2026-10-23 |  | PwC + INTL | CFIN + Basis + PMO | 0.9 | Queues empty; testers informed | Not started
3.2 | 3 QS4 (inside SIT2) | SUM run on QS4 (clients 100/200) importing SPDD/SPAU/note transports from N+1 Dev | QS4 | 2026-10-24 | 2026-10-25 |  | SAP ECS + INTL | ECS / Basis | G2, 3.1 | QS4 on SPS06 | Not started
3.3 | 3 QS4 (inside SIT2) | Post-checks, role transports, Work Zone content re-sync, legacy interface reconnect and ping | QS4 | 2026-10-26 | 2026-10-26 |  | INTL | Basis + Security + Legacy teams | 3.2 | SIT2 resumes Mon 26 Oct PM | Not started
3.4 | 3 QS4 (inside SIT2) | Resume SLT replication; reconcile CFIN (AIF, mapping, replication of parked docs) | QS4/200 | 2026-10-26 | 2026-10-26 |  | PwC | CFIN | 3.3 | Replication healthy | Not started
3.5 | 3 QS4 (inside SIT2) | SIT2 weeks 5-6 continue on SPS06 (remaining scripts) - every new run also validates the upgrade | QS4/200 | 2026-10-26 | 2026-11-06 |  | INTL + PwC | SIT2 testers | 3.3 | SIT2 exit as planned (6 Nov) | Not started
3.6 | 3 QS4 (inside SIT2) | Automated P1 pack in QS4-200 (night of 26 Oct), then nightly after each fix drop; manual P1 re-runs only for scenarios not automated | QS4/200 | 2026-10-26 | 2026-11-05 |  | INTL + PwC | INTL automation + PwC functional | 3.4 | P1 pass >= 95%, no open Sev1/Sev2 | Not started
3.6a | 3 QS4 (inside SIT2) | QS5-100 cut-over: stop DS4 -> QS5 deliveries (Fri 30 Oct); QS5 joins N+1 line on 2 Nov; automation continues in QS4-200 | QS5 | 2026-10-30 | 2026-10-30 |  | INTL | Basis + INTL automation | 0.11 | QS5 receives N+1 Dev transports only from 2 Nov | Not started
3.7 | 3 QS4 (inside SIT2) | Security regression incl. negative tests, GRC AC 12 checks, Work Zone role collections | QS4/200 | 2026-10-27 | 2026-11-03 |  | INTL | Security | 3.3 | Role test evidence | Not started
3.8 | 3 QS4 (inside SIT2) | Migration Cockpit mini-validation on SPS06 (sample load per object) | QS4/100 | 2026-10-27 | 2026-10-30 |  | PwC | Data Migration | 3.3 | Objects load on SPS06 | Not started
3.9 | 3 QS4 (inside SIT2) | Batch performance spot checks vs FPS02 runs (payment run, FX valuation, settlement) | QS4/200 | 2026-10-28 | 2026-11-04 |  | INTL | INTL Test Lead | 3.3 | No material degradation | Not started
3.10 | 3 QS4 (inside SIT2) | Triage SIT2 defects against the FPS02 baseline; fix and retest UPG-SPS06 defects | QS4 | 2026-10-26 | 2026-11-05 |  | PwC | Functional + Technical | 3.0 | Defect log closed or accepted | Not started
G3 | Gate | G3 Upgrade decision for SS4 + DS4 (6-8 Nov) and PRD (13-15 Nov), or Plan C | - | 2026-11-05 | 2026-11-05 |  | INTL | Steering (PMO) | 3.5-3.10 | Go / Plan C | Not started
4.0 | 4 SS4 + DS4 | Mock3 reconciliation and performance test sign-off by Fri 6 Nov 12:00; transport freeze to SS4 | SS4 | 2026-11-06 | 2026-11-06 |  | INTL + PwC | PMO + Data Migration + INTL Test Lead | G3 | Mock3 and perf test closed; else window starts Sat 7 Nov | Not started
4.1 | 4 SS4 + DS4 | Pause SLT replication into SS4 (if CFIN source connected) | SS4 | 2026-11-06 | 2026-11-06 |  | PwC | CFIN | 4.0 | Queues empty | Not started
4.2 | 4 SS4 + DS4 | SUM run on SS4 (pre-prod) and DS4 (go-live Dev) reusing adjustment transports | SS4, DS4 | 2026-11-06 | 2026-11-08 |  | SAP ECS + INTL | ECS / Basis | 4.0 | SS4 and DS4 on SPS06 | Not started
4.3 | 4 SS4 + DS4 | Post-checks, role transports, Work Zone re-sync, legacy interfaces (repointed for UAT) ping, resume SLT | SS4, DS4 | 2026-11-09 | 2026-11-09 |  | INTL + PwC | Basis + Security + Legacy + CFIN | 4.2 | UAT starts on SPS06 Mon 9 Nov | Not started
4.3a | 4 SS4 + DS4 | Automated smoke pack on SS4-100 before UAT testers start (read-mostly scenarios) | SS4/100 | 2026-11-09 | 2026-11-09 |  | INTL | INTL automation | 4.3, A.3 | Smoke green before business testers start | Not started
4.4 | 4 SS4 + DS4 | UAT on SPS06 (whole UAT = second round in pre-prod); TR onsite week validates OneSource tax on SPS06 | SS4/100 | 2026-11-09 | 2026-12-04 |  | INTL | PO/IT leads + business testers (PwC supports) | 4.3 | UAT exit | Not started
4.5 | 4 SS4 + DS4 | Performance delta check on SPS06: re-run key scenarios from the FPS02 performance test | SS4/100 | 2026-11-09 | 2026-11-13 |  | INTL | INTL Test Lead (performance) | 4.3 | No material degradation vs FPS02 results | Not started
G4 | Gate | G4 SS4 stable on SPS06: go for PRD | - | 2026-11-12 | 2026-11-12 |  | INTL | Steering (PMO) | 4.3,4.4,4.5 | Go for PRD | Not started
5.0 | 5 PRD | Hold PRD transport imports (queue) while PRD is still FPS02 | PRD | 2026-11-09 | 2026-11-15 |  | INTL | Basis | 4.2 | Import queue held | Not started
5.1 | 5 PRD | SUM run on PRD (pre-go-live, no business data) | PRD | 2026-11-13 | 2026-11-15 |  | SAP ECS | ECS | G4 | PRD on SPS06 | Not started
5.2 | 5 PRD | Post-checks, import queued transports, role transports, Work Zone production content, Cloud Connector / BTP destinations | PRD | 2026-11-16 | 2026-11-17 |  | INTL | Basis + Security | 5.1 | Technical verification signed | Not started
G5 | Gate | G5 Upgrade closed: PRD verified, UAT running clean on SPS06; feeds Go/No-Go (30 Nov - 4 Dec) | - | 2026-11-20 | 2026-11-20 |  | INTL | Steering (PMO) | 4.4,5.2 | Upgrade closed for go-live | Not started
6.1 | 6 Stabilize | SPS06 side-effect watch: re-run side-effect report weekly to go-live (extend monthly through hypercare once dated) | All | 2026-11-16 | 2027-01-01 |  | INTL + PwC | Basis + Technical | G5 | Watch log | Not started
6.2 | 6 Stabilize | Cutover runs on SPS06 (Plan on a Page 7-31 Dec); add SPS06 checks to the cutover checklist; dress rehearsal date TBC | PRD | 2026-12-07 | 2026-12-31 |  | INTL + PwC | Cutover lead | G5 | Cutover checklist incl. SPS06 items | Not started
6.3 | 6 Stabilize | Maintenance freeze: no further stack change from Go/No-Go until end of hypercare (TBC) | All | 2026-11-30 | 2027-01-01 |  | INTL | PMO | - | Freeze in change calendar | Not started
6.4 | 6 Stabilize | Hand the automated regression pack to the N+1 line (QS5) for future releases and the next stack update | QS5 | 2026-12-14 | 2026-12-31 |  | INTL | INTL Test Lead | G5 | Regression asset owned by N+1 | Not started

## Gates
Decision Gates
Gate | Date | Name | Exit criteria | Decision owner
G0 | Fri 9 Oct | Mobilized | ECS dates and downtime confirmed in writing; N+1 SIDs and routes signed off; stack confirmed | Steering (INTL PMO)
G1 | Fri 16 Oct | Sandbox sign-off | Upgrade clean; smoke passed; SPAU worklist sized; downtime measured; vendor confirmations received or tracked; QS5-100 copied, hardened and automation-ready | Steering
G2 | Fri 23 Oct | Dev ready | SPDD/SPAU, note bundle and role transports released from N+1 Dev; no blocking unit-test failure; ATC priority-1 findings closed; automated P1 pack on SPS06 in QS5-100 without upgrade blockers | Steering
G3 | Thu 5 Nov | Upgrade decision | P1 re-run in QS4/200 pass >= 95%; zero open Sev1/Sev2 UPG-SPS06 defects; SIT2 weeks 5-6 without upgrade blockers; CFIN healthy; security passed; migration loads on SPS06 | Steering (go-live line decision)
G4 | Thu 12 Nov | PRD go | SS4 technical checks passed; UAT running on SPS06 without upgrade blockers; performance delta acceptable; legacy E2E OK | Steering
G5 | Fri 20 Nov | Upgrade closed | PRD technical verification signed; UAT clean on SPS06 for two weeks; known issues and watch list handed to Go/No-Go (30 Nov - 4 Dec) | Steering -> Go/No-Go board

## Systems & Transports
System Calendar and Transport Rules
Tier | SID | Purpose in this upgrade | Upgrade window | Impact | Transport rule
Sandbox | (SID tbc) | Basic validation: nothing broken | 13-14 Oct (Tue-Wed) | Sandbox users only | Not in transport path
N+1 Dev | (SID tbc) | Dev integrity: SPDD/SPAU, notes, unit tests | 19-20 Oct (Mon-Tue) | None (idle until N+1 activation 2 Nov) | Source of upgrade adjustment transports; retrofit from DS4
QS5 100 | QS5 | N+1 QA: automated regression client until 30 Oct, then N+1 QA | 21-22 Oct (Wed-Thu) | None for project testers | Receives DS4 transports with QS4.200 until 30 Oct; N+1 Dev only from 2 Nov
QS4 100/200 | QS4 | SIT2 weeks 5-6 on SPS06 + P1 re-run of passed SIT2 scripts | 24-25 Oct (weekend, inside SIT2) | SIT2 pauses Sat-Sun; resumes Mon 26 Oct PM | Receives DS4 (FPS02) transports: lower -> higher only
SS4 100 | SS4 | Pre-prod: all of UAT on SPS06 | 6-8 Nov (Fri eve-Sun) | Between Mock3 / performance test end (6 Nov) and UAT start (9 Nov): no UAT pause; Mock3 data preserved | Freeze from Fri 6 Nov 12:00
DS4 110 | DS4 | Go-live Dev aligned to SPS06 | 6-8 Nov (with SS4) | Dev downtime over the weekend | After this, DS4 -> QS4 -> SS4 all SPS06
PRD | PS4 (tbc) | Production before cutover | 13-15 Nov (Fri eve-Sun) | No business data until cutover (7 Dec) | Import hold 9-15 Nov, then release queue
Landscape-balance windows (SAP Note 1090842: lower -> higher SP is the recommended direction)
Window | Dates | Landscape state | Rule
A | now - 23 Oct | Go-live line on FPS02; N+1 Dev SPS06 from 20 Oct; QS5 SPS06 from 22 Oct | Normal DS4 -> QS4 -> SS4 flow; from 12 Oct the same DS4 transports also go to QS5.100. Nothing from N+1 Dev into the go-live line except adjustment transports imported by SUM.
B | 24 Oct - 8 Nov | QS4 SPS06; DS4, SS4, PRD FPS02 | SIT2 fixes flow DS4 -> QS4 -> SS4 (FPS02-origin objects, lower -> higher). No SPS06-origin objects to SS4/PRD.
C | 9 - 15 Nov | DS4, QS4, SS4 SPS06; PRD FPS02 | Normal flow to SS4 (UAT fixes). PRD imports held in queue until PRD is upgraded.
D | 16 Nov onwards | All tiers SPS06 | Normal flow. N+1 (active 2 Nov) delivers N+1 Dev -> QS5 only; DS4 changes reach QS5 by retrofit into N+1 Dev.

## Test Strategy
Test Strategy per Tier
Tier | Objective | Scope | Who | Exit
Sandbox | Prove the stack installs and nothing is broken | Technical checklist; key T-codes; launchpad and Work Zone tiles; RFC/IDoc/AIF ping; SU25 dry run | INTL Basis, INTL Security, PwC stream leads (0.5 day each) | G1 16 Oct
N+1 Dev | Ensure the upgrade does not break custom developments | SPDD/SPAU; note bundle; ATC; RICEFW unit tests; custom Fiori apps; SU25/SU24 | PwC Technical, INTL Security | G2 23 Oct
QS5 client 100 (automation) | Early automated signal before QS4 is touched | Tosca P1 pack: FPS02 baseline (15-20 Oct), SPS06 run (22-23 Oct), difference triage | INTL automation; PwC functional for expected results | G2 23 Oct
QS4 client 200 (inside SIT2) | Full regression of all upgraded components | Automated P1 pack nightly; manual re-runs only where not automated; security negative tests; batch performance spot checks; migration check (client 100) | PwC Functional, SIT2 testers, INTL automation; INTL Test Lead tracks | G3 5 Nov
SS4 (pre-prod) | Second round: all of UAT on SPS06 | Automated smoke 9 Nov; UAT 9 Nov - 4 Dec on SPS06; performance delta check 9-13 Nov; OneSource with TR onsite (w/c 9 Nov); legacy interface E2E | INTL PO/IT leads, business testers; PwC supports | G4 12 Nov, G5 20 Nov
PRD | Technical verification only (no data before cutover) | Technical checklist; queued transports; role transports; Work Zone production content; no automation in PRD; cutover on SPS06 | INTL Basis, Security; cutover team | G5 20 Nov

## Test Automation & TMS
Test Automation with Tricentis and Transport Management QS4-200 / QS5-100
Tosca executes, qTest records (already linked to ADO), LiveCompare optional for impact analysis
1. How the plan changes with automation
Area | Without automation (main plan) | With Tricentis automation
First evidence on SPS06 | SIT2 weeks 5-6 in QS4/200 from 26 Oct | Automated P1 pack on SPS06 in QS5-100 on 22-23 Oct, compared with an FPS02 baseline, before QS4 is touched
G2 gate | Thu 22 Oct, based on unit tests | Fri 23 Oct, adds automated SPS06 evidence from QS5-100
Regression in QS4/200 | Manual re-run of passed SIT2 P1 scripts alongside SIT2 | Automated pack nightly after every fix drop; testers focus on SIT2 scripts and scenarios not automated
UAT start on SS4 (9 Nov) | Manual technical smoke on Mon 9 Nov morning | Automated smoke pack on Mon 9 Nov morning; testers start once it is green
Test priority | Stream judgement plus side-effect notes | Optional LiveCompare most-at-risk list and test gaps drive what runs first
After go-live | Manual scripts only | Automated pack handed to the N+1 line for future releases and the next stack update
Unchanged | - | Gate dates G0, G1, G3, G4, G5; upgrade windows for Sandbox, N+1 Dev, QS5, QS4, SS4 + DS4, PRD; business-run UAT on SPS06
2. QS5-100 (N+1 QA) automation readiness
Item | What has to be in place | Owner | Due
Tricentis scope | Tosca with SAP GUI and Fiori engines, DEX agents, qTest (in use), LiveCompare (optional); existing scripts mapped to the P1 set | INTL Test Lead | Fri 9 Oct
QS5-100 baseline | Client export QS4-200 (SCC8) and import into QS5-100 (SCC7) on 10-11 Oct, both on FPS02; disk sizing confirmed by ECS | INTL Basis / ECS | Sun 11 Oct
Post-copy hardening | BDLS; SM59; IDoc ports and partner profiles; SOAMANAGER logical ports; SCOT; disable or stub Ariba CIG, MBC, DRC/PAC, SLT/CFIN, AIF outbound | INTL Basis + PwC CFIN | Tue 13 Oct
Client settings | QS5-100 locked for Customizing and repository changes (SCC4); changes arrive by transport only | INTL Basis | Tue 13 Oct
SAP GUI scripting | sapgui/user_scripting = TRUE and sapgui/user_scripting_per_user = TRUE on QS5, QS4, SS4 (never PRD); S_SCR only in the automation role | INTL Basis + Security | Tue 13 Oct
Automation users | Persona users per stream with production-like roles from role transports; SECPOL policy so passwords do not expire mid-run; credentials in the Tosca vault | INTL Security | Wed 14 Oct
Agents and network | Windows DEX agents with SAP GUI and browser; network path to RISE QS5/QS4/SS4; SAP Logon entries; overnight execution window | INTL Test Lead + infrastructure | Wed 14 Oct
Integrations | Tosca results to qTest; qTest defects to ADO with tag UPG-SPS06 (ADO-qTest link already exists) | INTL Test Lead | Wed 14 Oct
Fiori and Work Zone | Fiori apps tested on the embedded launchpad in QS5; Work Zone tile tests run in QS4 and SS4, which are already connected to Work Zone | INTL automation | Tue 20 Oct
Test data | Data from the copied client (Mock2 load); Tosca TDS for consumable data; number ranges checked; data refresh rule between runs | INTL automation + PwC functional | Tue 20 Oct
Baseline | FPS02 automated baseline in QS5-100 stored in qTest as expected results | INTL automation | Tue 20 Oct
3. Transport management between QS4-200 (SIT2) and QS5-100 (automation)
Phase | Dates | Route | Rule
T0 | now - 11 Oct | QS5 not in any route | QS5-100 is filled by client export/import from QS4-200 on 10-11 Oct (both FPS02).
T1 | 12 - 30 Oct | DS4.110 -> target group {existing QS4 clients + QS5.100} | Extended transport control delivers each released DS4 request to QS4 and QS5.100; import into QS5.100 in the same sequence as QS4.200. From 22 Oct QS5 is SPS06 and DS4 is FPS02: lower -> higher only, the recommended direction (SAP Note 1090842).
T1a | 19 - 22 Oct | N+1 Dev -> QS5 | SPDD, SPAU, note and role transports from N+1 Dev are imported into QS5 with its upgrade, as for every other tier.
T2 | 30 Oct (Fri) | Cut-over | Remove QS5.100 from the DS4 target group; clear the remaining QS5 queue. Automation for the go-live line continues in QS4-200 (and smoke in SS4-100).
T3 | from 2 Nov | N+1 Dev -> QS5 only | QS5 is the N+1 QA. DS4 changes reach QS5 only by retrofit into N+1 Dev, then the normal N+1 route. Nothing ever flows from QS5 or QS4 back into DS4.
4. Transport rules
- No direct changes in QS4-200 or QS5-100 (client settings locked); everything arrives by transport.
- Never transport from a QA client to another QA client: QS4-200 is not a transport source. Alignment comes from the shared DS4 route plus the one-time client copy.
- Weekly consistency check: compare QS4 and QS5 import history (STMS) until cut-over; any gap is re-imported in order.
- Tosca SAP GUI and Fiori testing works through the UI and needs no ABAP add-on in S/4 (confirm optional components with Tricentis). Test cases carry the target system as a test configuration parameter.

## Stream Test Focus
Stream Test Focus and Related SAP Notes
Note numbers come from the Maintenance Planner side-effect report; validate each in SAP for Me
Stream (owner) | Regression focus (QS4/200 P1 re-run and UAT on SPS06) | Related side-effect notes
STP / Ariba (PwC) | PR -> PO -> Ariba Network via CIG add-on (ARBCI1 SP27), order confirmation, ASN, invoice; Manage Purchase Contracts; Taulia (TAUCI1) if used | 3727222, 3728027, 3563636, 3542666
OTC (PwC) | Order -> delivery -> billing, pricing, credit memo tax with OneSource, BP sync | 3678075, 3666390, 3759214
RTR (PwC) | GL close, FX valuation, allocations, AA depreciation, Margin Analysis, Material Ledger close | 3757119, 3777415 (HotNews), 3749911, 3751266
ITD (PwC) | GR/GI, inventory, deliveries, ML valuation, material master mass changes | 3777415, 3779425, 3528920
Central Finance (PwC) | SLT pause/resume, AIF monitor, replication of parked and reversal documents, mapping | 3794020, 3789234, 3793659, 3767655, 3756339
OpenText VIM (PwC) | Invoice capture -> DP document -> parking (FBV0) -> workflow approval -> posting; ArchiveLink images | 3680992, 3279714, 3777208
SAP AFC (PwC) | AFC (BTP) connection to S/4 via Cloud Connector; scheduled S/4 tasks run from AFC | Backend prerequisites per AFC documentation
SAP DRC (PwC) | Mexico eDocuments just deployed (21 Sep - 3 Oct): CFDI issue, cancel, payment complement; US Sales and Use Tax; CA/US/MX statutory reports | 3830404
SAP MBC (PwC) | F110 -> DMEE(X) payment file -> MBC; bank statement import and reprocessing; status messages | 3779613, 3614271, 3735645
OneSource Indirect Tax (PwC + TR) | Tax calculation SO/billing/credit memo, PO/MIRO, Mexico VAT cash basis (RFUMSV50); TR onsite w/c 12 Oct (Sandbox/statement) and w/c 9 Nov (UAT on SPS06) | 3678075, 3613556
Basis / Work Zone (INTL) | Launchpad and Work Zone content federation, tiles, custom apps, spool, qRFC | 3563542 (HotNews), 3534823, 3795313
Security / GRC (INTL) | SU25, SU24, role regression, SUIM, GRC AC 12 add-on | 3809657, 3782096, 3626764, 3590792

## Compatibility
Compatibility Register
Public sources and your Maintenance Planner files; vendor items need written confirmation
Component / topic | Finding and action | Source | Status | Owner
S/4HANA 2023 SPS06 (S4CORE 108 SP06) | FPS02 -> SPS06 crosses FPS03, the last 2023 feature pack, so new and changed features arrive in addition to corrections. Plan full regression, not SPS-level smoke. | SAP news (FPS03, 26 Feb 2025); SAP Release Cycles page | Covered by this plan | PwC + INTL Test Lead
Side-effect notes (Maintenance Planner 1002693650) | 135 in-scope notes need SNOTE after upgrade (fix ships in SP07 or has no SP); 2 HotNews | Your SER file; register workbook | Validate in SAP for Me (task 0.5) | PwC Technical
SAP HANA 2.0 SPS08 rev 89.5 | SPS08 is supported for S/4HANA 2023 (SPS07 rev 76 is the recommended minimum). Check revision restrictions in SAP Note 2655761 and HANA strategy SAP Note 2378962. | SAP Community install blog (2023 FPS02); SAP Notes 2655761, 2378962 | ECS to confirm | INTL Basis / ECS
Kernel 916 with SAP_BASIS 758 | S/4HANA 2023 ships with kernel 7.93; kernel 916 is supported as the downward-compatible kernel (via SUM) per SAP Kernel news. | SAP Kernel: Important News (help.sap.com) | ECS to confirm | INTL Basis / ECS
Transports across SP levels | Higher-SP -> lower-SP transports are risky; lower -> higher is the recommended direction; Customizing across levels not supported (SAP Note 1090842). Drives transport windows A-D. | SAP Note 1090842 | Rules published (task 0.8) | INTL Basis / PMO
SAP_UI 758 SP06 / BTP Work Zone Standard | SAP_UI 758 carries SAPUI5 1.120 (long-term maintenance). After each upgrade: invalidate caches, recalculate app index, re-sync Work Zone content channel, test tiles and custom apps. | SAP Fiori FES 2023 community blog; register note 3795313 | Test in Sandbox (1.2/1.5) | INTL Basis
Ariba CIG add-on (ARBCI1 10S SP27, ARBCI2 SP13, S4CI1 SP3) | Add-on upgraded within the stack; follow SAP upgrade guide for existing add-on installations; re-test CIG flows. | help.sap.com: managed gateway for spend management upgrade guide | Regression P1 | PwC STP / Ariba
Taulia add-on (TAUCI1 10S SP7) | Delivered in the stack; confirm whether Taulia is used, else no test. | Software catalog | Confirm usage | PwC STP
OpenText VIM 2023 (OTVIM* 02023_001, SP2/SP4) | Partner add-on; not covered by SAP side-effect report. Obtain OpenText confirmation that installed SPs support S/4HANA 2023 SPS06. | OpenText support (vendor confirmation required) | Open - INTL to raise ticket | INTL Basis + PwC VIM
Thomson Reuters OneSource Indirect Tax | Partner connector outside the SAP stack; get TR support statement for S/4HANA 2023 SPS06 during the TR onsite week of 12 Oct; TR onsite w/c 9 Nov coincides with UAT on SPS06. | Thomson Reuters (vendor confirmation required); Plan on a Page TR onsite weeks | Open - TR onsite 12 Oct | PwC OneSource
SAP AFC (BTP) | SaaS; S/4 backend connection (Cloud Connector, RFC/OData) must be re-tested after each upgrade; re-check backend prerequisite notes in AFC documentation. | SAP AFC documentation (supported systems) | Regression P1 | PwC AFC
SAP DRC (Mexico deployed 21 Sep - 3 Oct) | eDocument framework and legal changes ship in the stack; the new Mexico DRC deployment was built on FPS02, so re-test Mexico CFDI flows on SPS06; US SUT note 3830404. | Your SER file; Plan on a Page; DRC documentation | Regression P1 | PwC DRC
SAP MBC (BTP) | S/4 connector re-test: payment files out, bank statements in, status messages; notes 3779613, 3614271, 3735645. | Your SER file | Regression P1 | PwC MBC
Central Finance (same system) + SLT | Pause SLT replication during each target upgrade; confirm DMIS on SLT server/source supports target SPS06; run CFIN note checks after upgrade. | SAP CFIN guidance (validate DMIS compatibility in SAP for Me) | Runbook (0.9) | PwC CFIN + INTL Basis
GRC AC 12 (GRCFND_A V8100 SP32, GRCPINW SP32, UIGRAC01) | Upgraded within the stack; security regression covers ARA/EAM/role provisioning paths used. | Software catalog | Regression (3.7) | INTL Security
Tricentis qTest | Already integrated with ADO; tracks the SIT2 baseline, the P1 re-runs and UPG-SPS06 defects plus automated results | Your Testing Overview (ADO integration with qTest) | In place | INTL Test Lead
Tricentis Tosca (SAP GUI + Fiori) | SAP GUI engine needs server-side scripting (sapgui/user_scripting); restrict with user_scripting_per_user + S_SCR; Tricentis recommends Dev/QA only. Rescan modules for UI changes after SPS06 (SAPUI5 1.120 patch). | Tricentis Tosca docs; SAP GUI Scripting Security Guide | Set up in A.3-A.5 | INTL Basis + INTL Test Lead
Tricentis LiveCompare (optional) | Compares current system with the SAP update, ranks most-at-risk objects using usage data and flags test gaps. Pre-go-live, use QS4 SIT2 usage as proxy. Confirm RFC/SAP-side prerequisites with Tricentis. | Tricentis LiveCompare docs (Smart Impact Analysis) | Decide in 0.10 | INTL Test Lead
Client copy QS4-200 -> QS5-100 | Source and target must be on the same release; copy while both are on FPS02 (10-11 Oct), then upgrade QS5. | SAP client copy documentation / SAP Learning | ECS service request (0.2) | INTL Basis / ECS
RISE roles & responsibilities | ECS executes the technical update on request; customer owns SPDD/SPAU, testing and scheduling incl. stated lead times. | RISE PCE Roles & Responsibilities (SAP) | Confirm with ECS TSM | INTL Basis / PMO

## RACI
RACI
R = responsible, A = accountable, C = consulted, I = informed
Activity | SAP ECS | INTL Basis | INTL Security | INTL PMO | INTL Test Lead | INTL PO / IT Leads | INTL Legacy Teams | PwC Technical | PwC Functional | PwC Test Lead
ECS service requests and scheduling | C | R | I | A | I | I | I | I | I | I
Technical upgrade (SUM, HANA, kernel) | R | A | I | I | I | I | I | C | I | I
SPDD / SPAU and note bundle | I | A | I | I | I | I | I | R | C | I
SU25 / role adjustments, GRC | I | C | A/R | I | I | I | I | C | C | I
Post-processing, Work Zone re-sync | C | A/R | C | I | I | I | I | C | I | I
Interface reconnect and ping | I | A | I | I | C | I | R | C | C | I
Regression set and SIT2 baseline (qTest) | I | I | C | I | A | C | I | C | R | R
QS4/200 P1 re-run inside SIT2 | I | C | R | I | A | I | C | R | R | R
UAT on SPS06 (SS4) | I | C | C | I | A | R | R | C | C | C
Performance delta check (SS4) | C | C | I | I | A/R | I | I | C | C | I
Defect fix (UPG-SPS06) | C | R | R | I | C | I | C | R | R | I
CFIN replication pause / resume | I | R | I | I | I | I | I | C | A/R | I
Vendor compatibility confirmations | C | A/R | I | C | I | I | I | C | R | I
Automation readiness (QS5-100, agents, scripting) | C | R | R | I | A | I | I | I | C | C
Automated regression runs and triage | I | I | I | I | A/R | I | I | C | R | C
Transport routes DS4 -> QS4 + QS5 | C | A/R | I | C | C | I | I | I | I | I
Gates and steering decisions | C | C | C | A/R | C | C | I | C | C | C

## RAID
Risks and Mitigations
ID | Risk | Rating | Mitigation | Owner
R1 | ECS cannot schedule Sandbox by 13-14 Oct (lead time; requests go in 7 Oct) | High | Raise all service requests Wed 7 Oct with dates; escalate via ECS TSM; Plan B shifts chain +1 week and still closes before Go/No-Go | INTL Basis
R2 | QS4 regression overlaps SIT2 execution in the same client and team | High | Re-run only P1 scripts that passed on FPS02; SIT2 weeks 5-6 count as upgrade evidence; PwC functional and SIT2 testers split by stream | INTL Test Lead / PwC Test Lead
R3 | Defects in SIT2 weeks 5-6 cannot be attributed (functional vs upgrade) | Medium | FPS02 SIT2 baseline frozen in qTest by 23 Oct; tag UPG-SPS06; compare with SS4 (FPS02 until 6 Nov) | INTL Test Lead
R4 | Performance test (about 14 Oct - 6 Nov) runs on FPS02, production runs SPS06 with kernel 916 and HANA SPS08 | Medium | Performance delta check of key scenarios on SS4 SPS06 (9-13 Nov) is a G4 criterion | INTL Test Lead
R5 | Partner add-ons unconfirmed (OpenText VIM, OneSource, Taulia) | High | Vendor confirmations are a G1 criterion (TR statement during onsite week of 12 Oct); regression P1 for each; hold SS4/PRD at G3 if open | INTL Basis
R6 | Mock3 ends 6 Nov, the day the SS4 window opens | Medium | Mock3 reconciliation sign-off by Fri 6 Nov 12:00; otherwise the SS4 window starts Sat 7 Nov (UAT still starts 9 Nov) | PwC Data Migration / PMO
R7 | Transport imbalance between tiers | Medium | Windows A-D; PRD import hold 9-15 Nov; SUM reuses adjustment transports | INTL Basis
R8 | Mock3 runs on FPS02 but cutover runs on SPS06 | Medium | Migration Cockpit mini-validation on QS4/100 after upgrade; dress rehearsal (TBC) on SPS06 | PwC Data Migration
R9 | New Mexico DRC deployment (built on FPS02) affected by SPS06 legal changes | Medium | Mexico CFDI flows in the P1 re-run (QS4) and in UAT on SPS06 | PwC DRC
R10 | SPAU / note bundle larger than expected | Medium | Sandbox prototype sizes it a week early; HotNews and High priority notes first | PwC Technical
R11 | CFIN replication backlog or errors after target upgrade | Medium | Pause/resume runbook; drain queues before; reconcile after | PwC CFIN
R12 | New side effects published after SPS06 goes in | Low | Weekly side-effect watch to go-live, monthly through hypercare (TBC) | INTL Basis / PwC Technical
R13 | Automated coverage lower than assumed or scripts brittle after UI changes | Medium | Coverage measured by 9 Oct; automate only stable P1 scenarios; manual P1 remains the safety net; module rescans in A.6 | INTL Test Lead
R14 | QS5-100 copy sends messages to real endpoints | High | Post-copy hardening checklist (A.2) before any execution; outbound stubbed or disabled | INTL Basis
R15 | QS5-100 drifts from QS4-200 configuration | Medium | Same DS4 transports in the same order; weekly import-history comparison; cut-over on 30 Oct | INTL Basis

## SAP Notes (In-Scope)
In-Scope Side-Effect Notes (135) - implement with SNOTE after upgrade
Full triage of all 870 pairs: SAP_Notes_Side_Effect_Register_SPS06.xlsx
Solution note | Priority | Title | Fix ships in | Owner | Component(s) | Cause note(s)
3563542 | 01 HotNews | RSPO1043 detects false inconsistencies and deletes spool requests | - | INTL Basis | BC-CCM-PRN | 2926979
3777415 | 01 HotNews | MBEW-KALN1 overwritten by OBEW-KALN1 | S4CORE SP07 | PwC RTR / ITD | CO-PC-ML-MP | 3641556
3759621 | 02 High | ALV HS-Grid: Dump MOVE_CAST_ERROR when right clicking on Hierseq Grid | SAPBASIS SP07 | INTL Basis | BC-SRV-ALV | 3719981
3534823 | 02 High | ARFC_END_VB is not for update anymore | - | INTL Basis | BC-MID-RFC-QT | 3525039
3809657 | 02 High | SU25: Fehlerhafte Ergebnisse in Schritt 2c | SAPBASIS SP07 | INTL Security | BC-SEC-AUT-TOO | 3673078
3767655 | 02 High | Serialization Web Service Message: Successor message is not executed automatically | SAPBASIS SP07 | PwC CFIN | BC-SRV-AIF | 3751710
3793659 | 02 High | BAPI: AFLE mapping errors not returned | S4CORE SP07 | PwC CFIN | AC-INT | 3613546
3794020 | 02 High | Error reading document number during cFIN replication for posting of parked documents with BSTAT 'U' | - | PwC CFIN; PwC RTR | FI-GL-GL; FI-GL-GL-J | 3596100; 3607571
3779425 | 02 High | UAPI: Wrong field symbol in MRP area update path after note 3621492 causes incorrect data | S4CORE SP07 | PwC ITD | LO-MD-MM | 3621492
3528920 | 02 High | Incorrect function module call due to SAP Note 3505510 | - | PwC ITD | LO-MD-MM | 3505510
3782369 | 02 High | TABLE_INVALID_INDEX Runtime Error During Goods Receipt Posting via OData API in Advanced and Multistage Intercompany Process | - | PwC ITD / OTC | LE-SHP-VCA | 3682577
3678075 | 02 High | Incorrect tax rate in credit memos for intercompany billing or currency change | - | PwC OTC / OneSource | SD-BF-TX | 3526407
3759214 | 02 High | Classification data not replicated | S4CORE SP07 | PwC OTC / STP | LO-MD-BP-WS | 3561399
3666390 | 02 High | Updates to Address Comment (ADRCT-REMARK) are not synchronized between the Business Partner, Supplier, and Customer master when remark is maintained in multiple languages | - | PwC OTC / STP | LO-MD-BP-SYN | 3581401
3662731 | 02 High | No temporary profitability segments in release S/4 HANA 1709 | - | PwC RTR | CO-PA | 3589823
3749911 | 02 High | KE396 in MIR4 | S4CORE SP07 | PwC RTR | CO-PA | 3589823
3751266 | 02 High | KEPSL_DOC_POST_EXTERNAL DUMP CONVT_NO_NUMBER due to PLIKZ | S4CORE SP07 | PwC RTR | CO-PA-ACT | 3483652
3757119 | 02 High | FAGL_FCV: Program termination GETWA_NOT_ASSIGNED / Selection list does not contain any data | - | PwC RTR | FI-GL-GL-G | 3558927
3806051 | 02 High | KE545 bei buchungskreisübergreifender Buchung | - | PwC RTR | CO-PA | 3562180
3735645 | 02 High | Kurzzeitfehler ASSERTION_FAILED bei Interpretationsalgorithmus 421 | S4CORE SP07 | PwC RTR / MBC | FIN-FSCM-PF | 3681665
3613556 | 02 High | RFUMSV50: tax transfer posted with FB01 is not updated in DEFTAX_ITEM | - | PwC RTR / OneSource | FI-GL-GL-F1 | 3402197
3680992 | 02 High | FBV0: Coding contains an invalid function module | - | PwC RTR / VIM | FI-GL-GL-W | 3612459
3727222 | 02 High | MEPO601 error when adding manually new item to PO in ME22N | S4CORE SP07 | PwC STP | MM-PUR-GF-PR | 3499331
3728027 | 02 High | Purchasing organization value is not filled for new partners created in contracts using Manage purchase contracts App | S4CORE SP07 | PwC STP | MM-FIO-PUR-SQ-CON | 3622239
3563636 | 02 High | [F1048A] Create PO button doesn't launch Create PO application | UIS4HOP1 SP04 | PwC STP | MM-FIO-PUR-REQ-SOC | 3539973
3542666 | 02 High | F2229 - Material group missing | - | PwC STP | MM-FIO-PUR-REQ-PRF | 3319706
3752228 | 02 High | Bank details not fully derived from IBAN when posting via accounting interface | S4CORE SP07 | PwC STP / CFIN | FI-AP-AP-J | 3715290
3614271 | 02 High | DMEEX - syntax error in LDMEE1CIT & LDMEE1I18 | - | PwC STP / MBC | CA-GTF-CSC-DME | 3444594
3779613 | 02 High | F110: Extended individual payment fails | S4CORE SP07 | PwC STP / MBC | FI-AP-AP-B | 3631409
3794043 | 02 High | Deletion of an attachment that is available from 'Assign Document' not deleted | - | PwC STP / VIM | CA-DMS | 3636183
3279714 | 02 High | Commit Work not triggered by SWZ_AI_CREATE | - | PwC STP / VIM | BC-BMT-WFM | 3169078
3745364 | 03 Medium | Illegal characters in InputField and InputTokenizer destroy html | SAPUI SP07 | INTL Basis | BC-WD-ABA | 3742755
3506575 | 03 Medium | ALV Grid - Subtotal text not displayed after SAP Note 3503436 | - | INTL Basis | BC-SRV-ALV | 3503436
3554417 | 03 Medium | Update of ABAP Daemon Configuration does not work correctly | - | INTL Basis | BC-MID-DMN | 3505500
3657542 | 03 Medium | Text Table fields are blank in SM30 during print | - | INTL Basis | BC-CUS-TOL-TME | 3627579
3657606 | 03 Medium | App Support: Chip ID invalid | - | INTL Basis | CA-FLP-EXT-ASI | 3649832
3549715 | 03 Medium | App Support: Technical correction of unit test | - | INTL Basis | CA-FLP-EXT-ASI | 3530008
3669526 | 03 Medium | ALV: Missing buttons for added functions in SALV table | - | INTL Basis | BC-SRV-ALV | 3594156
3785382 | 03 Medium | List of Totals Records is not refreshed correctly after changing layout | - | INTL Basis | BC-SRV-ALV | 3716499
3795313 | 03 Medium | No SPAU alerts for SAPUI5 SMIM objects deleted via /UI5/MIME_CLEANUP report | SAPUI SP07 | INTL Basis | CA-UI5-ABA-SAR | 3599156
3590792 | 03 Medium | Ergänzung zum Hinweis 3564568 | - | INTL Security | BC-SEC-USR-IS | 3564568
3626764 | 03 Medium | SU01¦Copy User: Roles are not copied | - | INTL Security | BC-SEC-USR-ADM | 3527801
3666391 | 03 Medium | Unauthorized address display and runtime error SAPSQL_STMNT_TOO_LARGE in BP transaction | - | INTL Security | AP-MD-BP-EMP | 3632949
3782096 | 03 Medium | SUPC/SU25: Simulation des Abmischvorgangs liefert falsche Ergebnisse | SAPBASIS SP07 | INTL Security | BC-SEC-AUT-TOO | 3673078
3789234 | 03 Medium | Error F5 727 raised for a cash ledger document posted additionally during clearing | - | PwC CFIN | FI-GL-GL-J | 3577393
3756339 | 03 Medium | Central Finance: Central Market Segment Reporting Service Order Management (FI) | S4CORE SP07 | PwC CFIN | FI-CF-AC | 3537332
3776844 | 03 Medium | Unallowed delete statement in accounting interface trace in RAP context | S4CORE SP07 | PwC CFIN | AC-INT | 3652980
3830404 | 03 Medium | DRC U.S. - FormInstanceTaxItems Endpoint Call Fails Due to Wrong Parameter Format | S4CORE SP07 | PwC DRC | FI-LOC-FI-US-SUT | 3684090
3805046 | 03 Medium | Cleanup of unused shadow DDIC objects | S4CORE SP07 | PwC Data Migration | CA-LT-MIG | 3706755
3576593 | 03 Medium | Runtime error during maintenance of classifications | - | PwC ITD | CA-CL-CL | 3358066
3595570 | 03 Medium | Succession note for Note 3429227 | - | PwC ITD | CA-CL | 3429227
3525720 | 03 Medium | DIMP: Follow up note 3476680 | - | PwC ITD / OTC | LE-SHP-GF-EDI | 3476680
3549111 | 03 Medium | DIMP: Follow up note 3519923 | - | PwC ITD / OTC | LE-SHP-DL | 3519923
3793529 | 03 Medium | IO304/IO261 during GR/GI for delivery with serialized HU | - | PwC ITD / OTC | LE-SHP-GF-SR | 3608289
3809759 | 03 Medium | VL06: Freight Order Column Empty in Internal Transportation Management Integration | S4CORE SP07 | PwC ITD / OTC | LE-SHP-DL; LE-SHP-DL-RM; LE-SHP-GF | 3546926; 3608778; 3622045; 3685456; 3757276
3830831 | 03 Medium | Error message VL 632 with blank characters leads to dump CX_SY_REPLACE_INFINITE_LOOP | S4CORE SP07 | PwC ITD / OTC | LE-SHP-DL | 3663623
3614027 | 03 Medium | F0711 F0712 Edit Line Items option is not working | - | PwC OTC | FI-FIO-AR | 3504850
3793800 | 03 Medium | A2A Sales Order - RATE_EXT -> CONVT_NO_NUMBER - Part 2 | S4CORE SP07 | PwC OTC | SD-SLS-API | 3587611
3782131 | 03 Medium | Manage Prices - Sales app: Key fields not set in the downloaded failed records excel | S4CORE SP07 | PwC OTC | SD-MD-CM | 3669800
3771443 | 03 Medium | RLT not taken into account in sales order for discontinued material | - | PwC OTC | SD-BF-AC | 3566330
3777911 | 03 Medium | wrong ATP result with special stock Q | S4CORE SP07 | PwC OTC | SD-BF-AC | 3697546
3778390 | 03 Medium | Error during split of schedule lines with FCFS using Forecast and Planning Delivery Schedule - Part 2 | S4CORE SP07 | PwC OTC | SD-SLS | 3750729
3747285 | 03 Medium | SD Down Payment with Central Finance: System Dump in Invoice Print Preview | S4CORE SP07 | PwC OTC / CFIN | SD-BIL-IV-DP | 3594536
3769687 | 03 Medium | Outdated data returned when bypassing buffer for customer-BP assignment read | S4CORE SP07 | PwC OTC / STP | LO-MD-BP | 3717181
3779024 | 03 Medium | CVP EOP: Process switch DISABLE_PARTIAL_BLOCKING wrongly allow partial blocking of vendor company codes | S4CORE SP07 | PwC OTC / STP | LO-MD-BP-DP | 3528521
3502014 | 03 Medium | Syntax error due to inconsistent FIN_S_GLPOS | - | PwC RTR | FI-GL-IS | 3497745
3755943 | 03 Medium | PERFORM_TOO_MANY_PARAMETERS Runtime Error in RCNCC920 | S4CORE SP07 | PwC RTR | CO-PA | 3589823
3723716 | 03 Medium | Error message FG605 "Program session restart" | - | PwC RTR | FI-GL-GL | 3588573
3755725 | 03 Medium | No changeover to third phase of depreciation key at the end of useful life | S4CORE SP07 | PwC RTR | FI-AA-AA-B | 3583781
3730016 | 03 Medium | FAGLF101: Issues When Loading Saved Logs | S4CORE SP07 | PwC RTR | FI-GL-GL-G | 3673002
3515210 | 03 Medium | Removal of method if_wd_dg_exexp_ext_ctrl~get_content_for_segment | - | PwC RTR | BW-RUI-FPM | 3494827
3739961 | 03 Medium | BICS: Existing Bookmark Cannot Be Loaded Despite Being Present Part-2 | SAPBW SP07 | PwC RTR | BW-BEX-OT-BICS-INA; BW-BEX-OT-BICS-PROV | 3696992; 3717286
3740305 | 03 Medium | Correction in CL_P_COMPANYCODEDETAILSPA - Field country is only from T001-land1 or T001N-land1 | S4CORE SP07 | PwC RTR | FI-LOC-GEN | 3605210
3501073 | 03 Medium | SAPDBBRF: SYNTAX ERROR - The data object "<FIN_GLPOS>" does not... | - | PwC RTR | FI-GL-IS | 3497745
3689874 | 03 Medium | ALLOCATION: Error KC 018 | S4CORE SP07 | PwC RTR | CO-PA | 3529459
3691048 | 03 Medium | Short text of sender and reciver in Settlement follow-up documents after note 3389744 not always correct | - | PwC RTR | CO-OM-OPA-F | 3389744
3583927 | 03 Medium | In program R_FINS_PLAN_TRANS_CO_ERP_2_S4H you get error "User &2 has an exclusive lock on data slice &1." | - | PwC RTR | CO-FIO-OM-PL | 3484101
3562966 | 03 Medium | Expand Display Hierarchy to level | - | PwC RTR | BW-RUI-FPM | 3552872
3621344 | 03 Medium | ATC for DDLS I_ALLOCATIONCYCLEUPLOADTP | - | PwC RTR | FIN-UA | 3484215
3642725 | 03 Medium | INA : Capabilities are not read and hence may face issues regarding these missing capabilities. | - | PwC RTR | BW-BEX-OT-BICS-INA | 3521219
3674295 | 03 Medium | RFAWVZ40: payment/clearing documents not considered correctly | S4CORE SP07 | PwC RTR | FI-GL-GL-G | 3708414
3540815 | 03 Medium | RFAWVZ40N: Follow-up correction for Note 3526044 / Clearing of Customer/Vendor Invoices and Reversals | - | PwC RTR | FI-GL-GL-G | 3526044
3695248 | 03 Medium | FAGL_PROT: Message Statistics: Wrong Basis Release | - | PwC RTR | FI-GL | 3486933
3760190 | 03 Medium | Fehlermeldung FGV 005 (Es wurde keine Geschäftsjahresvariante angegeben) bei Materialbuchung | S4CORE SP07 | PwC RTR | CO-PA-ACT | 3593304
1001203 | 03 Medium | KEPC: Fehlermeldung KE361 | S4CORE SP07 | PwC RTR | CO-PA | 3613798
3759513 | 03 Medium | Parameters missing when navigating with selected hierarchy node | SAPBW SP07 | PwC RTR | BW-RUI-FPM | 3690998
3785616 | 03 Medium | Dump during CO-PA extraction | - | PwC RTR | CO-PA | 3513327
3787198 | 03 Medium | Validity of multi-level method not considered correctly | - | PwC RTR | FI-AA-AA-B | 3613486
3792617 | 03 Medium | Parameter adjustment in BAdI FPM_BICS_NAVIGATION not applied by search UIBB | - | PwC RTR | BW-RUI-FPM | 3723229
3802611 | 03 Medium | Hierarchy node selected from value help reported as wrong | SAPBW SP07 | PwC RTR | BW-RUI-FPM | 3712499
3806085 | 03 Medium | Error FAA_CFG_ACCESS 301 ('Depreciation key is not assigned') during asset transfer | - | PwC RTR | FI-AA-AA-B | 3549734
3810261 | 03 Medium | Value Help and Planning Sequence: Fix note 3676079 | SAPBW SP07 | PwC RTR | BW-BEX-OT-BICS-INA | 3676079
3785315 | 03 Medium | KE25 detail screen shows initial values | S4CORE SP07 | PwC RTR | CO-PA | 3572848
2525819 | 03 Medium | Accounting: Certificate expired for in-place Excel | - | PwC RTR | FI-SL-IS-A | 1992004
3765635 | 03 Medium | Real-time Overhead Posting Optimization | S4CORE SP07 | PwC RTR | CO-OM-OPA-OH | 3600765
3776134 | 03 Medium | ICR: Runtime error TYPELOAD_NEW_VERSION / LOAD_PROGRAM_INTF_MISMATCH | S4CORE SP07 | PwC RTR | FI-GL-GL-G | 3670615
3781348 | 03 Medium | F2547 - Verify General Journal Entries - Some Journal Entries in status Posted are duplicated | S4CORE SP07 | PwC RTR | FI-FIO-GL | 3549709
3777957 | 03 Medium | No auto split when calling BAPIs to create CO document | - | PwC RTR | CO-OM-CCA-E | 3482873
3779671 | 03 Medium | FSV: FAGL_FSV_TRANSPORT: Entries Not Written to Transport Request | S4CORE SP07 | PwC RTR | FI-GL-GL-G | 3668493
3781049 | 03 Medium | BICS: Exception while adding Bookmark to transport using report FPM_BICS_TRANSPORT_BOOKMARKS | SAPBW SP07 | PwC RTR | BW-BEX-OT-BICS-INA | 3696992
3789840 | 03 Medium | Data Migration to S/4HANA: false positive FINS_RECON 763 for ledgers not used in Asset Accounting; inflated reconciliation total for true positives | S4CORE SP07 | PwC RTR / Data Migration | FIN-MIG-AA | 3753135
3791609 | 03 Medium | Data Migration to S/4HANA: false positive FINS_RECON 773 (LDGRP mismatch) for fully statistical ANEK documents | S4CORE SP07 | PwC RTR / Data Migration | FIN-MIG-AA | 3492815
3738502 | 03 Medium | CKM3N: Display issue in Beginning Inventory and Receipts categories | S4CORE SP07 | PwC RTR / ITD | CO-PC-ACT | 3644834; 3691615
3787980 | 03 Medium | CKMCCC: Wrong actual beginning inventory values | S4CORE SP07 | PwC RTR / ITD | CO-PC-ACT | 3512136
3325232 | 03 Medium | App Reprocess Bank Statement Items: Notification when more than 150 items are selected | - | PwC RTR / MBC | FI-FIO-AR-PAY | 3294845
3785970 | 03 Medium | Kontoauszug: Abbruch in SAPLBSPS wegen DATA_LENGTH_0 | S4CORE SP07 | PwC RTR / MBC | FI-BL-PT-BA | 3705668
3770121 | 03 Medium | Performance issue with filter values in Manage Payments app | S4CORE SP07 | PwC RTR / MBC | FIN-FSCM-PF | 3765678; 3769603
3775293 | 03 Medium | Reprocess Bank Statement Items - G/L account is not derived correctly due to an unidentified transaction key on open items | S4CORE SP07 | PwC RTR / MBC | FI-FIO-AR-PAY | 3630931
3773923 | 03 Medium | Report R_FAR_MEMOLINE_HEALTH_CHECK has low performance during processing a large number of records during the "Check & Sync" scenario | S4CORE SP07 | PwC RTR / MBC | FI-FIO-AR-PAY | 3722049
3771425 | 03 Medium | Deferred Tax Transfer: Filling LC Amount and Tax Base Amount When Posting Tax Transfer Document via FB05 | S4CORE SP07 | PwC RTR / OneSource | FI-GL-GL-F1 | 3686849
3737842 | 03 Medium | DIMP: Follow up note 3573879 | - | PwC STP | MM-PUR-GF-ATP | 3573879
3717605 | 03 Medium | Enhanced Limit in PO/PR: Error Messages MMPUR_SPROC/072 + 073 not Required | - | PwC STP | MM-PUR-PO | 3645782
3747703 | 03 Medium | Purchase Contracts: Incorrect navigation to condition maintenance screen | S4CORE SP07 | PwC STP | MM-PUR-OA-CON | 3620489
3583023 | 03 Medium | Update of delivery date for multiple purchase order items not possible using Joule | - | PwC STP | MM-FIO-PUR-PO | 3527180
3549845 | 03 Medium | Quotation Currency does not get updated immediately | UIS4HOP1 SP04 | PwC STP | MM-FIO-PUR-SPQ | 3547794
3672941 | 03 Medium | MMPUR_SPROC/071: Joint Venture Accounting is not supported for Lean Services. | - | PwC STP | MM-PUR-PO | 3645782
3786196 | 03 Medium | WBS Element value disappears in UI | - | PwC STP | MM-FIO-PUR-REQ-SSP | 3535740
3792215 | 03 Medium | Custom sorting of catalog lost after implementing note 3760261 | S4CORE SP07 | PwC STP | MM-FIO-PUR-REQ-SSP | 3760261
3799507 | 03 Medium | ATC / CHECKMAN Error in MM-PUR Application | S4CORE SP07 | PwC STP | MM-FIO-PUR-REQ-SSP; MM-PUR-REQ | 3713815; 3743039
3775172 | 03 Medium | BAPI_PO_CHANGE: Item quantity cannot be changed when deletion indicator is set | S4CORE SP07 | PwC STP | MM-PUR-PO-BAPI | 3569976
3775777 | 03 Medium | Manage Purchase Contract Partner Deletion issue in draft | S4CORE SP07 | PwC STP | MM-FIO-PUR-SQ-CON | 3500840
3776693 | 03 Medium | API_PURCHASECONTRACT_PROCESS_SRV Version 2: Purchase Contract header data cleared and empty error details returned in batch changeset | S4CORE SP07 | PwC STP | MM-FIO-PUR-SQ-CON | 3483918
3767916 | 03 Medium | Error F5336 for MM invoice with retention | - | PwC STP / CFIN | FI-AP-AP-J | 3528124
3797679 | 03 Medium | Unable to retreive both AL and GOS type attachments using API | S4CORE SP07 | PwC STP / VIM | CA-DMS | 3546063
3797710 | 03 Medium | CVAPI_DOC_MAINTAIN always returns error "Object does not exist" although corresponding object exists in the system | - | PwC STP / VIM | CA-DMS | 3502891
3777208 | 03 Medium | Revertion of SAP note 3762259 | SAPBASIS SP07 | PwC STP / VIM | PLM-FIO-DMS | 3762259
3684513 | 04 Low | Remove Deprecated SAP__* entity from Odata service | - | INTL Basis | OPU-GW-COR | 3457369
3663413 | 04 Low | Webgui Data aging: virtual file system deleted on startup | - | INTL Basis | BC-FES-ITS | 3613566
3806214 | 04 Low | Custom Business Configurations app (F4579): Short dump when search field and filter is used together | SAPBASIS SP07 | INTL Basis | BC-CUS-TOL-MBC | 3741477
3831697 | 04 Low | F4485 schreibt keine Nachrichten zum Storno ins Protokoll | - | PwC OTC | FI-FIO-AR | 3724924
3781224 | 04 Low | CVI_CIF: KNA1 data not saved when maintained through complex interface with current state | S4CORE SP07 | PwC OTC / STP | CA-FS-CVI | 3617764
3533859 | 04 Low | CVI_BDT: Dynpro 0023 of function group CVI_FS_UI_CUSTOMER mistakenly created in ERP systems as downport from S4CORE | - | PwC OTC / STP | CA-FS-CVI | 3501035
3749544 | 04 Low | Support program for deletion of CO-PA characteristics[2] | S4CORE SP07 | PwC RTR | CO-PA-ST | 3605401
3764577 | 04 Low | API Release: Enhanced change evaluation for CDS view annotations in API compatibility ATC check | SAPBASIS SP07 | PwC Technical | BC-SRV-APS-EXT-REL | 3745539; 3749331
3770825 | 04 Low | API Release: Enhanced change evaluation for DDLS in API compatibility ATC check | SAPBASIS SP07 | PwC Technical | BC-SRV-APS-EXT-REL | 3745539; 3749331