## Slide 1
INTERNATIONAL
INTERNATIONAL.COM
CONFIDENTIAL AND PROPRIETARY TO INTERNATIONAL
S/4HANA 2023 SPS06 UPGRADE STRATEGY
OPTION: with Tricentis test automation
FPS02 to SPS06 inside SIT2, before UAT | aligned to the Plan on a Page (9/21)
Sandbox, N+1 Dev, QS5, QS4, SS4, PRD | Project NorthStar | October 2026

## Slide 2
1
EXECUTIVE SUMMARY
One upgrade, six tiers, six gates; all tiers on SPS06 by 15 Nov, before Go/No-Go (30 Nov - 4 Dec) and cutover (7 Dec)
1
What: S/4HANA 2023 FPS02 to SPS06 (S4CORE 108 SP02 to SP06)
With SAP HANA 2.0 SPS08 rev 89.5, kernel 916, Ariba CIG, OpenText VIM, GRC and MDG add-on SPs. SAP ECS executes; INTL and PwC adjust and test.
2
Why before go-live: go live on the stack we will run
The jump crosses FPS03 (last feature pack) plus SPS04 to SPS06 corrections and legal changes. Doing it now avoids an upgrade during hypercare.
3
How: QS4 inside SIT2, SS4 before UAT, PRD before cutover
QS4 24-25 Oct (SIT2 weeks 5-6 on SPS06), SS4 + DS4 6-8 Nov (all of UAT on SPS06), PRD 13-15 Nov. A Tricentis pack proves SPS06 in QS5-100 first.
4
Ask: approve the plan and gates; raise ECS requests by Wed 7 Oct
ECS scheduling lead time is the critical path. Plan B (+1 week) still closes before Go/No-Go.
Notes: Decision slide. Project dates follow the Plan on a Page updated 9/21. The only hard dependency this week is raising the SAP ECS service requests by Wednesday 7 October.

## Slide 3
2
WHAT CHANGED IN THE PROJECT PLAN
5-March Testing Overview vs Plan on a Page (9/21), and what it means for the upgrade
Item | 5-March plan | Plan on a Page (9/21) | Impact on the upgrade
SIT2 (QS4/200) | 28 Sep - 11 Oct, defects to 25 Oct | 28 Sep - 6 Nov | QS4 upgrade (24-25 Oct) now falls inside SIT2: weeks 5-6 run on SPS06
Mock Load 2 (QS4/200) | to 13 Sep (+ defects to 4 Oct) | Master data 7-27 Sep; Tx data 28 Sep - 11 Oct | Complete before the QS4 window
Performance testing (SS4/100) | not shown | about 14 Oct - 6 Nov | Runs on FPS02: add a performance delta check on SPS06 (9-13 Nov)
Mock Load 3 (SS4/100) | 5 - 25 Oct | 19 Oct - 6 Nov | Ends the day the SS4 window opens: reconciliation sign-off by Fri 6 Nov 12:00
UAT (SS4/100) | 26 Oct - 22 Nov | 9 Nov - 4 Dec | All of UAT runs on SPS06; no UAT pause needed
Go / No-Go | 23 Nov - 6 Dec | end of UAT (30 Nov - 4 Dec) | G5 (20 Nov) feeds it with the upgrade sign-off
Cutover (PRD) | 14 - 27 Dec | 7 - 31 Dec | PRD upgraded 13-15 Nov, before cutover
Go-live | w/c 4 Jan 2027 | 1 Jan 2027 | Dress rehearsal and hypercare dates to be confirmed
DRC Mexico / TR onsite | - | DRC MX deploy 21 Sep - 3 Oct; TR onsite w/c 12 Oct, 9 Nov, 7 Dec | No constraint; TR week 9 Nov validates OneSource on SPS06 in UAT

## Slide 4
3
WHAT IS CHANGING
Technical stack from Maintenance Planner transaction 1002693650 (software catalog, 2 Oct 2026)
Component | Today | Target
SAP S/4HANA (S4CORE, S4FND, S4CEXT 108) | SP02 (FPS02) | SP06 (SPS06)
SAP_BASIS, SAP_UI, SAP_BW, SAP_GWFND 758 | SP02 | SP06 (SAPUI5 1.120)
SAP HANA database 2.0 | per ECS | SPS08 rev 89.5
Kernel | per ECS | 916 (downward-compatible)
Ariba CIG add-on ARBCI1 10S / Taulia TAUCI1 | SP21 / SP02 | SP27 / SP07
OpenText VIM 2023: BAS, INV / O2C, P2P | SP3 / SP1 | SP4 / SP2
GRC AC 12 (GRCFND_A V8100, GRCPINW) | SP29 | SP32
MDG, EA-PS, FI-CAX (808); UIS4HOP1 900 | SP02 | SP06; SP03
Tools: SUM 2.0 / SPAM | - | SP26 PL5 / 0095
Today levels are derived from the lowest SP in the download basket.
FPS vs SPS (S/4HANA 2023)
01
FPS01
Feb 2024
02
FPS02
today
03
FPS03
last feature pack, Feb 2025
04
SPS04
corrections + legal
05
SPS05
corrections + legal
06
SPS06
target
Crossing FPS03 brings new and changed features, so we run full regression, not SPS-level smoke.
Notes: SP number equals stack number (FPS02 = SP02, SPS06 = SP06). After three feature packs SAP ships support package stacks. Sources: SAP news FPS03 (26 Feb 2025), SAP Release Cycles page, Upgrade Guide PCE 2023.

## Slide 5
4
GUIDING PRINCIPLES
Four rules that let the upgrade run alongside SIT2, Mock3, performance testing and UAT
1
Phase boundaries
QS4 between SIT2 weeks 4 and 5; SS4 between Mock3 and UAT
2
N+1 proves it first
Idle N+1 Dev and QS5 absorb SPDD/SPAU and the note bundle
3
Reuse and automate
SIT2 scripts in qTest; P1 pack automated in Tricentis Tosca
4
Gate driven
Six gates, each with a defined Plan B
How it works: SIT2 runs 28 Sep to 6 Nov, so QS4 is upgraded on 24-25 Oct and SIT2 weeks 5-6 test the new stack. SS4 is upgraded on 6-8 Nov, in the gap between Mock3 / performance testing and UAT, so all of UAT runs on SPS06. PRD follows on 13-15 Nov while it holds no business data.

## Slide 6
5
THE UPGRADE PATH
Each tier has one job; depth of testing increases as we move right
Sandbox
13-14 Oct
Nothing is broken
Technical checks, smoke per stream, SU25 dry run, downtime measured
N+1 Dev
19-20 Oct
Developments intact
SPDD/SPAU, 135 notes, ATC, RICEFW unit tests, role transports
QS5 100
21-22 Oct
Automated signal
Tosca P1 pack: FPS02 baseline vs SPS06 run, before QS4 is touched
QS4 100/200
24-25 Oct
Inside SIT2
SIT2 weeks 5-6 on SPS06; automated P1 pack nightly; security
SS4 + DS4
6-8 Nov
All of UAT
UAT 9 Nov - 4 Dec on SPS06; performance delta check; TR onsite
PRD
13-15 Nov
Technical verify
No data until cutover (7 Dec); cutover on SPS06
How it works: SAP ECS runs SUM in every tier. SPDD/SPAU, note and role transports are built once in N+1 Dev and reused in QS5, QS4, SS4, DS4 and PRD, so each tier gets the identical adjustment set. QS5-100 is a copy of QS4-200 used only for automation until 30 Oct.

## Slide 7
6
INTEGRATED TIMELINE
Upgrade overlay on the Plan on a Page (updated 9/21); Go/No-Go placed at UAT end; dress rehearsal and hypercare TBC
21
28
5
12
19
26
2
9
16
23
30
7
14
21
28
4
11
Sep
Oct
Nov
Dec
Jan
SIT2 (QS4/200)
SIT2 test execution
Mock loads
M2 Tx (QS4)
Mock3 (SS4)
Performance test (SS4)
SAP performance testing
UAT (SS4/100)
UAT
Go/No-Go, cutover
G/NG
Cutover (PRD)
DRC MX / TR onsite
DRC MX
TR
TR
TR
SPS06 UPGRADE
Sandbox 13-14 Oct
N+1 Dev 19-20 Oct
sync
unit test
QS5-100 21-22 Oct
baseline
auto runs
QS4 24-25 Oct
SIT2 + auto P1
SS4 + DS4 6-8 Nov
all of UAT on SPS06
PRD 13-15 Nov
cutover on SPS06
Gates
G0
G1
G2
G3
G4
G5
Today
Go-live 1 Jan
Project phase (Plan on a Page)
DRC Mexico / TR onsite
Upgrade window (SAP ECS)
Upgrade validation / testing
Notes: Week columns start Monday. Orange windows: Sandbox 13-14 Oct, N+1 Dev 19-20 Oct, QS5 21-22 Oct, QS4 24-25 Oct, SS4 and DS4 6-8 Nov, PRD 13-15 Nov. Performance testing start read from the Plan on a Page as about 14 Oct.

## Slide 8
7
KEEPING THE LANDSCAPE BALANCED
Transport windows follow SAP Note 1090842: lower SP to higher SP is the recommended direction
Window | Dates | Landscape state | Transport rule
A | now to 23 Oct | Go-live line on FPS02; N+1 Dev SPS06 from 20 Oct, QS5 from 22 Oct | Normal DS4 > QS4 > SS4 flow, also delivered to QS5.100 from 12 Oct. Nothing from N+1 Dev except adjustment transports
B | 24 Oct to 8 Nov | QS4 on SPS06; DS4, SS4, PRD on FPS02 | SIT2 fixes flow DS4 > QS4 > SS4 (FPS02-origin objects only). No SPS06-origin objects to SS4 or PRD
C | 9 to 15 Nov | DS4, QS4, SS4 on SPS06; PRD on FPS02 | UAT fixes flow normally to SS4. PRD imports held in the queue until PRD is upgraded
D | from 16 Nov | All tiers on SPS06 | Normal flow. N+1 (active 2 Nov) delivers N+1 Dev > QS5 only; DS4 changes reach QS5 by retrofit
How it works: N+1 Dev is upgraded first while it is idle, so the go-live Dev (DS4) keeps feeding SIT2 fixes on FPS02. DS4 is upgraded with SS4 on 6-8 Nov, so UAT fixes are built on SPS06 for an SPS06 SS4. Retrofit DS4 changes into N+1 Dev weekly until then.

## Slide 9
8
TEST STRATEGY PER TIER
Manual SIT2 continues; automation adds a QS5 signal and nightly re-runs
Tier | Objective | Scope | Who | Exit
Sandbox | Prove the stack installs and nothing is broken | Technical checklist; key T-codes; launchpad and Work Zone tiles; RFC/IDoc/AIF ping; SU25 dry run | INTL Basis, INTL Security, PwC stream leads (0.5 day each) | G1 16 Oct
N+1 Dev | Ensure the upgrade does not break custom developments | SPDD/SPAU; note bundle; ATC; RICEFW unit tests; custom Fiori apps; SU25/SU24 | PwC Technical, INTL Security | G2 23 Oct
QS5 client 100 (automation) | Early automated signal before QS4 is touched | Tosca P1 pack: FPS02 baseline (15-20 Oct), SPS06 run (22-23 Oct), difference triage | INTL automation; PwC functional for expected results | G2 23 Oct
QS4 client 200 (inside SIT2) | Full regression of all upgraded components | Automated P1 pack nightly; manual re-runs only where not automated; security negative tests; batch performance spot checks; migration check (client 100) | PwC Functional, SIT2 testers, INTL automation; INTL Test Lead tracks | G3 5 Nov
SS4 (pre-prod) | Second round: all of UAT on SPS06 | Automated smoke 9 Nov; UAT 9 Nov - 4 Dec on SPS06; performance delta check 9-13 Nov; OneSource with TR onsite (w/c 9 Nov); legacy interface E2E | INTL PO/IT leads, business testers; PwC supports | G4 12 Nov, G5 20 Nov
PRD | Technical verification only (no data before cutover) | Technical checklist; queued transports; role transports; Work Zone production content; no automation in PRD; cutover on SPS06 | INTL Basis, Security; cutover team | G5 20 Nov
Exit G3: P1 re-run pass rate at least 95%, zero open Sev1/Sev2 UPG-SPS06 defects, SIT2 weeks 5-6 without upgrade blockers, CFIN healthy, security passed, migration loads on SPS06.

## Slide 10
9
TEST AUTOMATION WITH TRICENTIS
Option: qTest is already in place with ADO, Tosca executes, LiveCompare is optional
Area | Main plan (manual) | With Tricentis automation
First evidence on SPS06 | SIT2 weeks 5-6 in QS4/200 from 26 Oct | Automated P1 pack on SPS06 in QS5-100 on 22-23 Oct, compared with an FPS02 baseline, before QS4 is touched
G2 gate | Thu 22 Oct, based on unit tests | Fri 23 Oct, adds automated SPS06 evidence from QS5-100
Regression in QS4/200 | Manual re-run of passed SIT2 P1 scripts alongside SIT2 | Automated pack nightly after every fix drop; testers focus on SIT2 scripts and scenarios not automated
UAT start on SS4 (9 Nov) | Manual technical smoke on Mon 9 Nov morning | Automated smoke pack on Mon 9 Nov morning; testers start once it is green
Test priority | Stream judgement plus side-effect notes | Optional LiveCompare most-at-risk list and test gaps drive what runs first
After go-live | Manual scripts only | Automated pack handed to the N+1 line for future releases and the next stack update
What does not change: gate dates G0, G1, G3, G4, G5; every upgrade window; business-run UAT on SPS06. Automation adds evidence and cycles, it does not replace SIT2 or UAT. Coverage depends on the scripts from the Jun-Jul Automation Scripting track; only stable P1 scenarios are automated in this window.

## Slide 11
10
QS5-100 AUTOMATION READINESS
What the N+1 QA client needs before the FPS02 baseline run on 15 Oct
Item | What has to be in place | Owner | Due
QS5-100 baseline | Client export QS4-200 (SCC8) and import into QS5-100 (SCC7) on 10-11 Oct, both on FPS02; disk sizing confirmed by ECS | INTL Basis / ECS | Sun 11 Oct
Post-copy hardening | BDLS; SM59; IDoc ports and partner profiles; SOAMANAGER logical ports; SCOT; disable or stub Ariba CIG, MBC, DRC/PAC, SLT/CFIN, AIF outbound | INTL Basis + PwC CFIN | Tue 13 Oct
Client settings | QS5-100 locked for Customizing and repository changes (SCC4); changes arrive by transport only | INTL Basis | Tue 13 Oct
SAP GUI scripting | sapgui/user_scripting = TRUE and sapgui/user_scripting_per_user = TRUE on QS5, QS4, SS4 (never PRD); S_SCR only in the automation role | INTL Basis + Security | Tue 13 Oct
Automation users | Persona users per stream with production-like roles from role transports; SECPOL policy so passwords do not expire mid-run; credentials in the Tosca vault | INTL Security | Wed 14 Oct
Agents and network | Windows DEX agents with SAP GUI and browser; network path to RISE QS5/QS4/SS4; SAP Logon entries; overnight execution window | INTL Test Lead + infrastructure | Wed 14 Oct
Integrations | Tosca results to qTest; qTest defects to ADO with tag UPG-SPS06 (ADO-qTest link already exists) | INTL Test Lead | Wed 14 Oct
Fiori and Work Zone | Fiori apps tested on the embedded launchpad in QS5; Work Zone tile tests run in QS4 and SS4, which are already connected to Work Zone | INTL automation | Tue 20 Oct
Test data | Data from the copied client (Mock2 load); Tosca TDS for consumable data; number ranges checked; data refresh rule between runs | INTL automation + PwC functional | Tue 20 Oct

## Slide 12
11
TRANSPORT MANAGEMENT: QS4-200 AND QS5-100
Keep the automation client identical to SIT2 until N+1 takes QS5 over on 2 Nov
DS4 110
go-live Dev
QS4 200
SIT2
QS5 100
automation client
N+1 Dev
upgrade line
SS4 / PRD
go-live line
same DS4 transports, same order (12-30 Oct)
adjustment transports 19-22 Oct; all N+1 from 2 Nov
client copy once, 10-11 Oct (both FPS02)
Phase | Dates | Route | Rule
T0 | to 11 Oct | QS5 not in any route | QS5-100 filled once by client export/import from QS4-200
T1 | 12 to 30 Oct | DS4 > existing QS4 clients + QS5.100 | Extended transport control; import into QS5.100 in QS4.200 order; lower SP to higher SP only (SAP Note 1090842)
T2 | Fri 30 Oct | Cut-over | Remove QS5.100 from the DS4 target group; automation continues in QS4-200 and as smoke in SS4-100
T3 | from 2 Nov | N+1 Dev > QS5 only | DS4 changes reach QS5 by retrofit into N+1 Dev; nothing flows from QS4 or QS5 back into DS4
QS4-200 is never a transport source. No direct changes in QS4-200 or QS5-100. Weekly import-history comparison until cut-over. Tosca tests through the UI with no ABAP add-on (confirm optional components with Tricentis); the target system is a test configuration parameter.

## Slide 13
12
STREAM REGRESSION FOCUS
Every in-scope solution, with the side-effect notes from your Maintenance Planner report that touch it
Stream | Regression focus (QS4/200 P1 re-run and UAT on SPS06) | Side-effect notes
STP / Ariba | PR -> PO -> Ariba Network via CIG add-on (ARBCI1 SP27), order confirmation, ASN, invoice; Manage Purchase Contracts; Taulia (TAUCI1) if used | 3727222, 3728027, 3563636, 3542666
OTC | Order -> delivery -> billing, pricing, credit memo tax with OneSource, BP sync | 3678075, 3666390, 3759214
RTR | GL close, FX valuation, allocations, AA depreciation, Margin Analysis, Material Ledger close | 3757119, 3777415, 3749911, 3751266
ITD | GR/GI, inventory, deliveries, ML valuation, material master mass changes | 3777415, 3779425, 3528920
Central Finance | SLT pause/resume, AIF monitor, replication of parked and reversal documents, mapping | 3794020, 3789234, 3793659, 3767655, 3756339
OpenText VIM | Invoice capture -> DP document -> parking (FBV0) -> workflow approval -> posting; ArchiveLink images | 3680992, 3279714, 3777208
SAP AFC | AFC (BTP) connection to S/4 via Cloud Connector; scheduled S/4 tasks run from AFC | Backend prerequisites per AFC documentation
SAP DRC | Mexico eDocuments just deployed (21 Sep - 3 Oct): CFDI issue, cancel, payment complement; US Sales and Use Tax; CA/US/MX statutory reports | 3830404
SAP MBC | F110 -> DMEE(X) payment file -> MBC; bank statement import and reprocessing; status messages | 3779613, 3614271, 3735645
OneSource Indirect Tax | Tax calculation SO/billing/credit memo, PO/MIRO, Mexico VAT cash basis (RFUMSV50); TR onsite w/c 12 Oct (Sandbox/statement) and w/c 9 Nov (UAT on SPS06) | 3678075, 3613556
Basis / Work Zone | Launchpad and Work Zone content federation, tiles, custom apps, spool, qRFC | 3563542, 3534823, 3795313
Security / GRC | SU25, SU24, role regression, SUIM, GRC AC 12 add-on | 3809657, 3782096, 3626764, 3590792

## Slide 14
13
SIDE-EFFECT NOTES TRIAGE
Maintenance Planner side-effect report filtered to US, CA, MX, English and the NorthStar streams
870
cause to solution pairs in your report
135
in-scope notes to implement
178
conditional: depends on module use
535
out of scope (300 are S/4HCM payroll)
None of the 135 fixes ship inside SPS06 (they arrive in SP07 or have no SP), so all go in by SNOTE as one note bundle built in N+1 Dev.
Note | Priority | Why it matters | Owner
3563542 | HotNews | Spool consistency job RSPO1043 can delete valid spool requests: apply before the job runs | INTL Basis
3777415 | HotNews | Material Ledger: MBEW-KALN1 overwritten by OBEW-KALN1 | PwC RTR / ITD
3809657, 3782096 | High / Medium | SU25 step 2c returns wrong results: apply before role adjustment | INTL Security
3794020 | High | CFIN replication of parked documents fails reading the document number | PwC CFIN
3779613, 3614271 | High | F110 extended individual payment; DMEEX syntax error in payment formats | PwC STP / MBC
Notes: Full register with all 870 rows: SAP_Notes_Side_Effect_Register_SPS06.xlsx. Every note is validated in SAP for Me before implementation.

## Slide 15
14
COMPATIBILITY AND THIRD PARTIES
What SAP's side-effect report does not cover, and what we must confirm in writing
Component | Finding / action | Status
HANA 2.0 SPS08 rev 89.5 | Supported for S/4HANA 2023 (SPS07 rev 76 recommended minimum); check SAP Notes 2655761 and 2378962 | ECS confirm
Kernel 916 | Downward-compatible kernel for 2023 (ships with 7.93), per SAP Kernel news | ECS confirm
Work Zone Standard | SAP_UI 758 carries SAPUI5 1.120; after each tier: invalidate caches, app index, re-sync content channel | Sandbox test
OpenText VIM 2023 SP4 | Partner add-on outside SAP report: written OpenText support statement for 2023 SPS06 | Open: INTL ticket
OneSource Indirect Tax | TR support statement during TR onsite w/c 12 Oct; TR onsite w/c 9 Nov tests OneSource in UAT on SPS06 | Open: TR onsite
DRC Mexico (new) | Deployed 21 Sep - 3 Oct on FPS02: re-test Mexico CFDI flows on SPS06 (QS4 re-run and UAT) | Regression P1
Ariba CIG, AFC, MBC | In stack or BTP: follow add-on upgrade guide; re-test S/4 connections per tier | Regression P1
Central Finance + SLT | Pause replication per target upgrade; confirm DMIS on SLT/source supports 2023 SPS06 | Runbook
Tricentis Tosca | SAP GUI scripting on QS5, QS4, SS4 only (per-user via S_SCR); module rescans for SAPUI5 1.120 changes | Set up 12-14 Oct
Vendor confirmations are a G1 entry criterion. Unconfirmed items stop SS4 and PRD at G3.

## Slide 16
15
WHO DOES WHAT
R responsible, A accountable, C consulted, I informed. INTL Test Lead column includes the INTL automation team
Activity | SAP ECS | INTL Basis | INTL Security | INTL PMO | INTL Test Lead | INTL PO / IT | INTL Legacy | PwC Technical | PwC Functional | PwC Test Lead
ECS service requests and scheduling | C | R | I | A | I | I | I | I | I | I
Technical upgrade (SUM, HANA, kernel) | R | A | I | I | I | I | I | C | I | I
SPDD / SPAU and note bundle | I | A | I | I | I | I | I | R | C | I
SU25 / role adjustments, GRC | I | C | A/R | I | I | I | I | C | C | I
Post-processing, Work Zone re-sync | C | A/R | C | I | I | I | I | C | I | I
Interface reconnect and ping | I | A | I | I | C | I | R | C | C | I
Regression set and SIT2 baseline (qTest) | I | I | C | I | A | C | I | C | R | R
QS4/200 P1 re-run inside SIT2 | I | C | R | I | A | I | C | R | R | R
UAT on SPS06 (SS4) | I | C | C | I | A | R | R | C | C | C
Performance delta check (SS4) | C | C | I | I | A/R | I | I | C | C | I
Defect fix (UPG-SPS06) | C | R | R | I | C | I | C | R | R | I
CFIN replication pause / resume | I | R | I | I | I | I | I | C | A/R | I
Vendor compatibility confirmations | C | A/R | I | C | I | I | I | C | R | I
Automation readiness (QS5-100, agents, scripting) | C | R | R | I | A | I | I | I | C | C
Automated regression runs and triage | I | I | I | I | A/R | I | I | C | R | C
Transport routes DS4 -> QS4 + QS5 | C | A/R | I | C | C | I | I | I | I | I
Gates and steering decisions | C | C | C | A/R | C | C | I | C | C | C

## Slide 17
16
DECISION GATES
Each gate is a short steering decision chaired by INTL PMO
Gate | Date | Decision | Exit criteria
G0 | Fri 9 Oct | Mobilized | ECS dates and downtime confirmed in writing; N+1 SIDs and routes signed off; stack confirmed
G1 | Fri 16 Oct | Sandbox sign-off | Upgrade clean; smoke passed; SPAU worklist sized; downtime measured; vendor confirmations received or tracked; QS5-100 copied, hardened and automation-ready
G2 | Fri 23 Oct | Dev ready | SPDD/SPAU, note bundle and role transports released from N+1 Dev; no blocking unit-test failure; ATC priority-1 findings closed; automated P1 pack on SPS06 in QS5-100 without upgrade blockers
G3 | Thu 5 Nov | Upgrade decision | P1 re-run in QS4/200 pass >= 95%; zero open Sev1/Sev2 UPG-SPS06 defects; SIT2 weeks 5-6 without upgrade blockers; CFIN healthy; security passed; migration loads on SPS06
G4 | Thu 12 Nov | PRD go | SS4 technical checks passed; UAT running on SPS06 without upgrade blockers; performance delta acceptable; legacy E2E OK
G5 | Fri 20 Nov | Upgrade closed | PRD technical verification signed; UAT clean on SPS06 for two weeks; known issues and watch list handed to Go/No-Go (30 Nov - 4 Dec)
Plan B (ECS lead time): shift one week; QS4 31 Oct - 1 Nov (still inside SIT2), SS4 13-15 Nov (UAT week 1 on FPS02), PRD 20-22 Nov, still before Go/No-Go. Plan C (G3 fails): SS4, DS4 and PRD stay FPS02 for UAT and go-live; QS4, N+1 Dev and QS5 stay SPS06 as the post-go-live line.

## Slide 18
17
KEY RISKS AND MITIGATIONS
Top risks; full RAID (15 items) in the plan workbook
Risk | Rating | Mitigation | Owner
ECS cannot schedule Sandbox by 13-14 Oct (lead time; requests go in 7 Oct) | High | Raise all service requests Wed 7 Oct with dates; escalate via ECS TSM; Plan B shifts chain +1 week and still closes before Go/No-Go | INTL Basis
QS4 regression overlaps SIT2 execution in the same client and team | High | Re-run only P1 scripts that passed on FPS02; SIT2 weeks 5-6 count as upgrade evidence; PwC functional and SIT2 testers split by stream | INTL Test Lead / PwC Test Lead
Defects in SIT2 weeks 5-6 cannot be attributed (functional vs upgrade) | Medium | FPS02 SIT2 baseline frozen in qTest by 23 Oct; tag UPG-SPS06; compare with SS4 (FPS02 until 6 Nov) | INTL Test Lead
Performance test (about 14 Oct - 6 Nov) runs on FPS02, production runs SPS06 with kernel 916 and HANA SPS08 | Medium | Performance delta check of key scenarios on SS4 SPS06 (9-13 Nov) is a G4 criterion | INTL Test Lead
Partner add-ons unconfirmed (OpenText VIM, OneSource, Taulia) | High | Vendor confirmations are a G1 criterion (TR statement during onsite week of 12 Oct); regression P1 for each; hold SS4/PRD at G3 if open | INTL Basis
QS5-100 copy sends messages to real endpoints | High | Post-copy hardening checklist (A.2) before any execution; outbound stubbed or disabled | INTL Basis
Mock3 ends 6 Nov, the day the SS4 window opens | Medium | Mock3 reconciliation sign-off by Fri 6 Nov 12:00; otherwise the SS4 window starts Sat 7 Nov (UAT still starts 9 Nov) | PwC Data Migration / PMO
New Mexico DRC deployment (built on FPS02) affected by SPS06 legal changes | Medium | Mexico CFDI flows in the P1 re-run (QS4) and in UAT on SPS06 | PwC DRC
Automated coverage lower than assumed or scripts brittle after UI changes | Medium | Coverage measured by 9 Oct; automate only stable P1 scenarios; manual P1 remains the safety net; module rescans in A.6 | INTL Test Lead

## Slide 19
18
NEXT TEN DAYS
What has to happen before the Sandbox window on 13 Oct
1
Wed 7 Oct: approve plan and gates; raise all SAP ECS service requests
INTL PMO and Basis. Every tier incl. QS5, plus the QS4-200 to QS5-100 client copy; HANA revision, kernel and downtime window per tier.
2
Fri 9 Oct (G0): routes and scope locked
N+1 SIDs and the DS4 > QS4 + QS5.100 target group approved; note bundle validated; Tricentis scope and coverage known.
3
Sat 10 to Wed 14 Oct: QS5-100 automation-ready
Client copy, post-copy hardening, GUI scripting, automation users, Tosca agents and qTest link (Basis, Security, Test Lead).
4
Fri 16 Oct (G1): Sandbox signed off
Vendor confirmations filed (OpenText, Thomson Reuters); FPS02 automated baseline in QS5-100 under way.