## Read Me
Project NorthStar ¦ Performance Assurance Workbook
Companion to the Performance Assurance Strategy deck. Draft, October 2026.
Purpose | One place to plan, staff, scope and track the NorthStar performance test workstream from mobilization (Oct 5, 2026) through the first month-end close after business go-live.
Key dates | UAT Oct 26 to Nov 20. Cutover from Nov 23. Tech go-live Dec 15, 2026. Business go-live Jan 1, 2027. Performance go / no-go gate Dec 4.
Environment fact | Pre-prod is sized at about 50% of PRD (per VP IT). Confirm the exact configuration with SAP ECS and enter it on the Scaling Model tab.
Plan | Phased plan with weekly Gantt. Edit Start, End, Status and % Complete. Bars and milestones redraw automatically.
RACI | R, A, C, I by role for every plan activity. The check column flags any row without exactly one A.
Scenario Catalog | Tier 1 (35) and example Tier 2 scenarios with risk scoring, KPIs and owners. Scores 1 to 5; Suggested Tier is calculated.
Workload Model | Turns daily volumes into peak-hour design load, pre-prod step targets and virtual users. Yellow cells are inputs.
Scaling Model | Pre-prod versus PRD configuration, the capacity ratio, and PRD projections by metric class (A, B, C).
KPI Library | Proposed default thresholds by metric class and where each is measured.
Interface Inventory | Template for the 168 BTP interfaces with risk score and suggested tier.
Batch Inventory | Template for Control-M, SAP, DataStage and SOA jobs on the critical path.
Env Readiness | Entry checklist for pre-prod before cycle 1 (target Nov 2).
Risks and Decisions | Risk log with scoring and the decision log for leadership.
Team | Roles, FTE, source and FTE-weeks.
Cell legend | Yellow fill with blue text = input you are expected to edit. Black text = formula or fixed content. Do not overwrite formula cells.
Role codes | VP = VP IT and steering ¦ IPL = International performance test lead ¦ PPM = PwC performance test manager ¦ PET = performance engineering team ¦ TDE = test data engineer ¦ BAS = Basis and HANA ¦ ECS = SAP ECS (RISE) ¦ BTP = BTP integration team ¦ ABAP = ABAP fix team ¦ DSC = DataStage and Control-M ¦ SME = functional SMEs ¦ LEG = legacy and SaaS owners ¦ SEC = security and GRC ¦ CUT = cutover lead
Assumptions | Volumes, peak profiles and KPI thresholds are proposals until mined and signed (target Oct 14 and Oct 23). Example values are marked as examples.

## Plan
Performance Assurance Plan ¦ Oct 5, 2026 to Feb 12, 2027
Edit Start, End, Status, % Complete. Gantt bars are conditional formats driven by Start and End.
Gantt start (Monday) | 2026-10-05 |  |  |  | Today | 2026-10-01
ID | Phase | Activity | R | A | Start | End | Workdays | Type | Status | % Complete | 2026-10-05 | 2026-10-12 | 2026-10-19 | 2026-10-26 | 2026-11-02 | 2026-11-09 | 2026-11-16 | 2026-11-23 | 2026-11-30 | 2026-12-07 | 2026-12-14 | 2026-12-21 | 2026-12-28 | 2027-01-04 | 2027-01-11 | 2027-01-18 | 2027-01-25 | 2027-02-01 | 2027-02-08
0 | Phase 0 Mobilize
0.1 | Mobilize | Name International performance test lead and PwC performance manager | VP | VP | 2026-10-05 | 2026-10-06 | 2 | Task | Not started | 0%
0.2 | Mobilize | Present strategy; obtain steering approval and funding | IPL | VP | 2026-10-06 | 2026-10-09 | 4 | Task | Not started | 0%
0.3 | Mobilize | Raise PwC change request for the performance workstream | PPM | VP | 2026-10-05 | 2026-10-14 | 8 | Task | Not started | 0%
0.4 | Mobilize | Contract specialist performance engineers and test data engineer | IPL | VP | 2026-10-07 | 2026-10-16 | 8 | Task | Not started | 0%
0.5 | Mobilize | ECS tickets: pre-prod and PRD config sheet, refresh plan, snapshots, upsize quote | BAS | IPL | 2026-10-05 | 2026-10-16 | 10 | Task | Not started | 0%
0.6 | Mobilize | Request SAP Going-Live Check (confirm Enterprise Support entitlement) | BAS | IPL | 2026-10-05 | 2026-10-09 | 5 | Task | Not started | 0%
0.7 | Mobilize | Agree pre-prod slot plan with cutover lead for Nov 2 to Dec 4 | IPL | VP | 2026-10-07 | 2026-10-09 | 3 | Task | Not started | 0%
0.8 | Mobilize | Legacy and SaaS owners decide: scale test instance or accept stub | LEG | IPL | 2026-10-07 | 2026-10-16 | 8 | Task | Not started | 0%
M0 | Mobilize | Steering approval, workstream launched | IPL | VP | 2026-10-09 | 2026-10-09 | 1 | Milestone | Not started | 0%
1 | Phase 1 Shift-left baselines (SIT2)
1.1 | Shift-left | Enable telemetry in SIT2: ST03N and STAD retention, SQLM, HANA expensive statements, IS trace | BAS | IPL | 2026-10-05 | 2026-10-09 | 5 | Task | Not started | 0%
1.2 | Shift-left | Analyze Mock-2 runtimes: CFIN JE posting rate, load durations, job runtimes | BAS | PPM | 2026-10-05 | 2026-10-16 | 10 | Task | Not started | 0%
1.3 | Shift-left | Single-user baselines of Tier 1 transactions during SIT2 | PET | PPM | 2026-10-12 | 2026-10-23 | 10 | Task | Not started | 0%
1.4 | Shift-left | Interface latency baselines: OneSource, DRC and PAC, Pega, Ariba | BTP | PPM | 2026-10-12 | 2026-10-23 | 10 | Task | Not started | 0%
1.5 | Shift-left | Expensive SQL and custom code review: VIM, CFIN and AIF, VSM, enhancements | ABAP | PPM | 2026-10-12 | 2026-10-30 | 15 | Task | Not started | 0%
1.6 | Shift-left | Technical hotspot checks: number ranges, IS limits, Cloud Connector, HANA parameters | BAS | IPL | 2026-10-12 | 2026-10-23 | 10 | Task | Not started | 0%
2 | Phase 2 Design and build
2.1 | Design and build | Collect inventory: 168 interfaces, RICEFW, Fiori and T-code usage, Control-M export | PPM | IPL | 2026-10-05 | 2026-10-09 | 5 | Task | Not started | 0%
2.2 | Design and build | AI-assisted classification and draft risk scores | PET | IPL | 2026-10-07 | 2026-10-14 | 6 | Task | Not started | 0%
2.3 | Design and build | Tier 1 sign-off workshop | IPL | IPL | 2026-10-15 | 2026-10-16 | 2 | Task | Not started | 0%
M2a | Design and build | Tier 1 scope signed | IPL | IPL | 2026-10-16 | 2026-10-16 | 1 | Milestone | Not started | 0%
2.4 | Design and build | Mine legacy volumes and build the workload model | TDE | PPM | 2026-10-07 | 2026-10-21 | 11 | Task | Not started | 0%
2.5 | Design and build | KPI and acceptance criteria sign-off by process owners | PPM | IPL | 2026-10-19 | 2026-10-23 | 5 | Task | Not started | 0%
2.6 | Design and build | NeoLoad infrastructure: controller, generators, network path to RISE, auth for perf users | PET | PPM | 2026-10-12 | 2026-10-23 | 10 | Task | Not started | 0%
2.7 | Design and build | Performance users and roles cloned from production roles; communication users | SEC | IPL | 2026-10-19 | 2026-10-30 | 10 | Task | Not started | 0%
2.8 | Design and build | Service virtualization stubs (mock iFlows) for endpoints that cannot take load | BTP | PPM | 2026-10-19 | 2026-10-30 | 10 | Task | Not started | 0%
2.9 | Design and build | Synthetic data factory: JEs, VSM configurations, invoices, VIM images, warranty claims | TDE | PPM | 2026-10-19 | 2026-11-04 | 13 | Task | Not started | 0%
2.10 | Design and build | Script Tier 1 UI scenarios (Fiori and SAP GUI) | PET | PPM | 2026-10-19 | 2026-11-04 | 13 | Task | Not started | 0%
2.11 | Design and build | Build non-UI injectors: iFlow payloads, JDBC JE volumes, file drops | PET | PPM | 2026-10-19 | 2026-10-30 | 10 | Task | Not started | 0%
2.12 | Design and build | Control-M batch replay schedule for the critical path | DSC | PPM | 2026-10-26 | 2026-11-04 | 8 | Task | Not started | 0%
2.13 | Design and build | Pre-prod refresh with Mock data plus config and transport parity | BAS | IPL | 2026-10-26 | 2026-10-30 | 5 | Task | Not started | 0%
2.14 | Design and build | Monitoring dashboards (Cloud ALM, IS, HANA) and results template | BAS | IPL | 2026-10-26 | 2026-10-30 | 5 | Task | Not started | 0%
2.15 | Design and build | Calibration run and scaling factor confirmation | PET | IPL | 2026-11-02 | 2026-11-03 | 2 | Task | Not started | 0%
M2b | Design and build | Ready to execute: pre-prod entry criteria met | IPL | IPL | 2026-11-02 | 2026-11-02 | 1 | Milestone | Not started | 0%
3 | Phase 3 Execute in pre-prod
3.1 | Execute | Cycle 1: component and interface throughput (CFIN JE, top iFlows, VIM, OneSource, DRC) | PET | PPM | 2026-11-03 | 2026-11-06 | 4 | Task | Not started | 0%
3.2 | Execute | Cycle 2: integrated peak hour (online plus interfaces) | PET | PPM | 2026-11-09 | 2026-11-13 | 5 | Task | Not started | 0%
3.3 | Execute | Cycle 3: month-end close and batch critical path | PET | PPM | 2026-11-12 | 2026-11-18 | 5 | Task | Not started | 0%
3.4 | Execute | Cycle 4: stress to break point and 8-hour soak | PET | PPM | 2026-11-16 | 2026-11-20 | 5 | Task | Not started | 0%
3.5 | Execute | Twice-weekly defect triage and tuning | ABAP | PPM | 2026-11-03 | 2026-12-04 | 24 | Task | Not started | 0%
3.6 | Execute | Results pack with PRD forecast after each cycle | PPM | IPL | 2026-11-06 | 2026-11-20 | 11 | Task | Not started | 0%
4 | Phase 4 Retest and gate
4.1 | Retest and gate | Retest failed Tier 1 scenarios after fixes | PET | PPM | 2026-11-23 | 2026-12-02 | 8 | Task | Not started | 0%
4.2 | Retest and gate | Performance test summary report and PRD forecast | PPM | IPL | 2026-12-01 | 2026-12-03 | 3 | Task | Not started | 0%
M4 | Retest and gate | Performance go / no-go gate | IPL | VP | 2026-12-04 | 2026-12-04 | 1 | Milestone | Not started | 0%
5 | Phase 5 PRD readiness and hypercare
5.1 | PRD readiness | PRD parity checks: HANA parameters, work processes, number ranges, IS tenant, Cloud Connector HA | BAS | IPL | 2026-12-07 | 2026-12-11 | 5 | Task | Not started | 0%
5.2 | PRD readiness | Going-Live Check verification and ECS PRD sizing confirmation | BAS | IPL | 2026-12-07 | 2026-12-11 | 5 | Task | Not started | 0%
M5a | PRD readiness | Tech go-live | CUT | VP | 2026-12-15 | 2026-12-15 | 1 | Milestone | Not started | 0%
5.3 | PRD readiness | Non-destructive PRD smoke: connectivity, read-only checks, synthetic monitors | PET | IPL | 2026-12-15 | 2026-12-23 | 7 | Task | Not started | 0%
5.4 | PRD readiness | Hypercare alert thresholds live, using the same KPIs | BAS | IPL | 2026-12-14 | 2026-12-31 | 14 | Task | Not started | 0%
M5b | Hypercare | Business go-live | CUT | VP | 2027-01-01 | 2027-01-01 | 1 | Milestone | Not started | 0%
5.5 | Hypercare | Peak monitoring, first two business weeks | BAS | IPL | 2027-01-04 | 2027-01-15 | 10 | Task | Not started | 0%
5.6 | Hypercare | First month-end close: performance watch and trial balance match | SME | IPL | 2027-02-01 | 2027-02-05 | 5 | Task | Not started | 0%
5.7 | Hypercare | Lessons learned and continuous performance regression proposal | IPL | VP | 2027-02-08 | 2027-02-12 | 5 | Task | Not started | 0%
Legend: orange = task, maroon = milestone, grey = complete task, pale column = current week. Program dates: UAT Oct 26 to Nov 20; cutover from Nov 23; tech go-live Dec 15; business go-live Jan 1.

## RACI
RACI by plan activity
R responsible, A accountable (exactly one per row), C consulted, I informed. Role codes are explained on the Read Me tab.
ID | Activity | VP VP IT / steering | IPL INTL perf lead | PPM PwC perf mgr | PET Perf eng team | TDE Test data eng | BAS Basis / HANA | ECS SAP ECS | BTP BTP integration | ABAP ABAP fix team | DSC DataStage / Control-M | SME Functional SMEs | LEG Legacy and SaaS owners | SEC Security / GRC | CUT Cutover lead | A check
0.1 | Name International performance test lead and PwC performance manager | A |  | C | [7 empty] | I |  |  |  | OK
0.2 | Present strategy; obtain steering approval and funding | A | R | C |  |  | I |  | I |  |  | I |  |  |  | OK
0.3 | Raise PwC change request for the performance workstream | A | C | R | [11 empty] | OK
0.4 | Contract specialist performance engineers and test data engineer | A | R | C | [11 empty] | OK
0.5 | ECS tickets: pre-prod and PRD config sheet, refresh plan, snapshots, upsize quote |  | A | I |  |  | R | C | [7 empty] | OK
0.6 | Request SAP Going-Live Check (confirm Enterprise Support entitlement) | I | A |  |  |  | R | C | [7 empty] | OK
0.7 | Agree pre-prod slot plan with cutover lead for Nov 2 to Dec 4 | A | R | I |  |  | C | [7 empty] | C | OK
0.8 | Legacy and SaaS owners decide: scale test instance or accept stub | I | A | C |  |  |  |  | C |  |  |  | R |  |  | OK
1.1 | Enable telemetry in SIT2: ST03N and STAD retention, SQLM, HANA expensive statements, IS trace |  | A | I |  |  | R |  | C | [6 empty] | OK
1.2 | Analyze Mock-2 runtimes: CFIN JE posting rate, load durations, job runtimes |  | I | A |  |  | R |  |  |  | C | C |  |  |  | OK
1.3 | Single-user baselines of Tier 1 transactions during SIT2 |  | I | A | R | [6 empty] | C |  |  |  | OK
1.4 | Interface latency baselines: OneSource, DRC and PAC, Pega, Ariba |  | I | A |  |  |  |  | R |  |  |  | C |  |  | OK
1.5 | Expensive SQL and custom code review: VIM, CFIN and AIF, VSM, enhancements |  | I | A |  |  | C |  |  | R |  | C |  |  |  | OK
1.6 | Technical hotspot checks: number ranges, IS limits, Cloud Connector, HANA parameters |  | A | I |  |  | R | C | C | [6 empty] | OK
2.1 | Collect inventory: 168 interfaces, RICEFW, Fiori and T-code usage, Control-M export |  | A | R |  |  |  |  | C |  | C | C |  |  |  | OK
2.2 | AI-assisted classification and draft risk scores |  | A | C | R |  |  |  | C | [6 empty] | OK
2.3 | Tier 1 sign-off workshop | I | A | C |  |  | C |  | C |  |  | C | C |  |  | OK
2.4 | Mine legacy volumes and build the workload model |  | I | A |  | R |  |  |  |  | C | C | C |  |  | OK
2.5 | KPI and acceptance criteria sign-off by process owners | I | A | R |  |  | C |  |  |  |  | C |  |  |  | OK
2.6 | NeoLoad infrastructure: controller, generators, network path to RISE, auth for perf users |  | I | A | R |  | C | C | [5 empty] | C |  | OK
2.7 | Performance users and roles cloned from production roles; communication users |  | A |  | C |  | C |  | C |  |  |  |  | R |  | OK
2.8 | Service virtualization stubs (mock iFlows) for endpoints that cannot take load |  | I | A | C |  |  |  | R |  |  |  | C |  |  | OK
2.9 | Synthetic data factory: JEs, VSM configurations, invoices, VIM images, warranty claims |  | I | A | C | R | [5 empty] | C |  |  |  | OK
2.10 | Script Tier 1 UI scenarios (Fiori and SAP GUI) |  | I | A | R | [6 empty] | C |  |  |  | OK
2.11 | Build non-UI injectors: iFlow payloads, JDBC JE volumes, file drops |  | I | A | R |  |  |  | C |  | C |  |  |  |  | OK
2.12 | Control-M batch replay schedule for the critical path |  | I | A | C |  | C |  |  |  | R |  |  |  |  | OK
2.13 | Pre-prod refresh with Mock data plus config and transport parity |  | A | I |  |  | R | C | [6 empty] | C | OK
2.14 | Monitoring dashboards (Cloud ALM, IS, HANA) and results template |  | A | I | C |  | R |  | C | [6 empty] | OK
2.15 | Calibration run and scaling factor confirmation |  | A | I | R |  | C | C | [7 empty] | OK
3.1 | Cycle 1: component and interface throughput (CFIN JE, top iFlows, VIM, OneSource, DRC) |  | I | A | R |  | C |  | C |  | C |  |  |  |  | OK
3.2 | Cycle 2: integrated peak hour (online plus interfaces) |  | I | A | R |  | C |  | C |  |  | C |  |  |  | OK
3.3 | Cycle 3: month-end close and batch critical path |  | I | A | R |  | C |  |  |  | C | C |  |  |  | OK
3.4 | Cycle 4: stress to break point and 8-hour soak |  | I | A | R |  | C |  | C | [6 empty] | OK
3.5 | Twice-weekly defect triage and tuning |  | I | A | C |  | C |  | C | R |  |  | C |  |  | OK
3.6 | Results pack with PRD forecast after each cycle | I | A | R | C |  | C | [8 empty] | OK
4.1 | Retest failed Tier 1 scenarios after fixes |  | I | A | R |  | C |  |  | C |  |  |  |  | C | OK
4.2 | Performance test summary report and PRD forecast | I | A | R | C |  | C | [8 empty] | OK
5.1 | PRD parity checks: HANA parameters, work processes, number ranges, IS tenant, Cloud Connector HA |  | A | I |  |  | R | C | C | [6 empty] | OK
5.2 | Going-Live Check verification and ECS PRD sizing confirmation | I | A |  |  |  | R | C | [7 empty] | OK
5.3 | Non-destructive PRD smoke: connectivity, read-only checks, synthetic monitors |  | A | I | R |  | C |  | C | [5 empty] | C | OK
5.4 | Hypercare alert thresholds live, using the same KPIs | I | A | C |  |  | R |  | C | [6 empty] | OK
5.5 | Peak monitoring, first two business weeks | I | A |  |  |  | R |  | C | C |  | C |  |  |  | OK
5.6 | First month-end close: performance watch and trial balance match | I | A |  |  |  | C |  |  |  | C | R | C |  |  | OK
5.7 | Lessons learned and continuous performance regression proposal | A | R | C | C | [10 empty] | OK
Where the accountable role also does the work, only A is shown (A implies R).

## Scenario Catalog
Scenario catalog with risk scoring
Score Volume, Criticality and Complexity 1 to 5. An override reason forces Tier 1. Thresholds are proposals until signed (Oct 23).
ID | Value stream | Scenario | Entry channel | Systems in path | Test type | Volume 1-5 | Criticality 1-5 | Complexity 1-5 | Risk score | Tier 1 override reason | Suggested tier | Primary KPI | Proposed threshold | Cycle | Stub needed? | Process owner | Status
OTC-01 | Order to cash | VSM truck order: configure, price, tax, save | Fiori / GUI | S/4 VSM, AVC, pricing, OneSource | Load | 3 | 5 | 5 | 75 | Revenue | Tier 1 | Save step response, p90 | 5 s or less | C2 | Decide |  | Draft
OTC-02 | Order to cash | Order change and reconfiguration | Fiori / GUI | S/4 VSM, AVC, OneSource | Load | 3 | 4 | 5 | 60 |  | Tier 1 | Save step response, p90 | 5 s or less | C2 | Decide |  | Draft
OTC-03 | Order to cash | Inbound dealer and legacy orders via API | API / iFlow | Legacy, BTP IS, S/4 | Throughput | 4 | 5 | 4 | 80 |  | Tier 1 | Orders per hour, error rate | 1.5x peak, under 0.5% errors | C1 | Decide |  | Draft
OTC-04 | Order to cash | Outbound delivery and goods issue | Fiori / GUI | S/4 LE | Load | 3 | 4 | 3 | 36 | Revenue | Tier 1 | Step response, p90 | 2 s or less | C2 | No |  | Draft
OTC-05 | Order to cash | Billing run with OneSource and output | Batch | S/4 billing, OneSource, forms | Throughput | 5 | 5 | 4 | 100 | Revenue | Tier 1 | Invoices per hour | 1.5x billing peak in window | C3 | Decide |  | Draft
OTC-06 | Order to cash | Invoice outbound to legacy apps | iFlow | S/4, BTP IS, legacy | Throughput | 5 | 4 | 3 | 60 |  | Tier 1 | Messages per hour, backlog | 1.5x peak, no backlog growth | C1 | Decide |  | Draft
OTC-07 | Order to cash | DRC Mexico CFDI to PAC and status back | Batch / iFlow | S/4 DRC, BTP, PAC | Throughput | 4 | 5 | 4 | 80 | Regulatory | Tier 1 | Create to stamped, p95 | Inside SAT stamping window | C1 | Decide |  | Draft
OTC-08 | Order to cash | Cash application and customer payments | Batch / Fiori | S/4 FI-AR, bank | Load | 3 | 4 | 4 | 48 |  | Tier 1 | Batch runtime | Fits window with 20% buffer | C3 | No |  | Draft
FIN-01 | Central Finance | Infor LN JE feed at month-end peak | JDBC | Infor LN, DataStage, S/4 CFIN, AIF | Throughput | 5 | 5 | 5 | 125 | Financial truth | Tier 1 | JE lines posted per hour | 1.5x month-end peak | C1 | No |  | Draft
FIN-02 | Central Finance | AIF error reprocessing at volume | Fiori / GUI | S/4 AIF | Load | 4 | 4 | 4 | 64 |  | Tier 1 | Reprocess rate | Backlog cleared same day | C3 | No |  | Draft
FIN-03 | Central Finance | Trial balance match S/4 versus legacy | Report | S/4, Infor LN | Load | 3 | 5 | 4 | 60 | Financial truth | Tier 1 | Report runtime; match | 30 min or less; 100% match | C3 | No |  | Draft
FIN-04 | Financial close | FX revaluation, depreciation, accruals | Batch | S/4 FI, AA | Batch | 4 | 5 | 3 | 60 |  | Tier 1 | Batch runtime | Fits close calendar | C3 | No |  | Draft
FIN-05 | Financial close | Financial statements and analytical apps | Fiori | S/4 HANA, CDS | Load | 3 | 4 | 4 | 48 |  | Tier 1 | Analytical response, p90 | 10 s or less | C2 | No |  | Draft
FIN-06 | Financial close | GL extracts to legacy and reporting | Batch / file | S/4, DataStage | Batch | 4 | 4 | 3 | 48 |  | Tier 1 | Extract runtime | Fits window with 20% buffer | C3 | No |  | Draft
FIN-07 | Financial close | Period open and close steps | Fiori / GUI | S/4 FI | Load | 2 | 5 | 3 | 30 | Financial truth | Tier 1 | Step response, p90 | 2 s or less | C3 | No |  | Draft
P2P-01 | P2P and VIM | Ariba PO replication to S/4 | iFlow | Ariba, BTP / CIG, S/4 | Throughput | 4 | 4 | 3 | 48 |  | Tier 1 | POs per hour | 1.5x peak | C1 | No |  | Draft
P2P-02 | P2P and VIM | Goods receipt and service entry | Fiori | S/4 MM | Load | 4 | 4 | 3 | 48 |  | Tier 1 | Step response, p90 | 2 s or less | C2 | No |  | Draft
P2P-03 | P2P and VIM | VIM OCR intake in bulk | File / iFlow | OpenText capture, S/4 VIM | Throughput | 5 | 4 | 4 | 80 | Known pain | Tier 1 | Invoices to DP doc per hour | 1.5x daily peak hour | C1 | Decide |  | Draft
P2P-04 | P2P and VIM | VIM approval workflow, concurrent approvers | Fiori | S/4 VIM, workflow | Load | 4 | 4 | 4 | 64 | Known pain | Tier 1 | Inbox and approve, p90 | 3 s or less | C2 | No |  | Draft
P2P-05 | P2P and VIM | Invoice posting and 3-way match | Batch / Fiori | S/4 VIM, MM, FI, OneSource | Load | 5 | 4 | 4 | 80 |  | Tier 1 | Invoices posted per hour | 1.5x peak | C2 | Decide |  | Draft
P2P-06 | P2P and VIM | Payment run and bank file | Batch | S/4 FI-AP, bank | Batch | 3 | 5 | 3 | 45 | Financial truth | Tier 1 | Payment run runtime | Fits window with 20% buffer | C3 | No |  | Draft
WAR-01 | Warranty | Pega claim inbound burst | API / iFlow | Pega, BTP IS, S/4 | Throughput | 4 | 4 | 4 | 64 |  | Tier 1 | Claims per hour, p95 latency | 1.5x burst, 1.5 s or less | C1 | Decide |  | Draft
WAR-02 | Warranty | Claim adjudication and credit memo batch | Batch | S/4 warranty, FI | Batch | 4 | 4 | 4 | 64 |  | Tier 1 | Batch runtime | Fits window with 20% buffer | C3 | No |  | Draft
WAR-03 | Warranty | Claim status back to Pega | iFlow | S/4, BTP IS, Pega | Throughput | 4 | 3 | 4 | 48 |  | Tier 1 | Messages per hour, backlog | 1.5x peak, no backlog growth | C1 | Decide |  | Draft
INT-01 | Integration and batch | Top 20 iFlow mix at design peak | iFlow | BTP IS, Cloud Connector | Throughput | 5 | 4 | 4 | 80 | Shared choke point | Tier 1 | Throughput, JMS depth | 1.5x peak, no backlog growth | C1 | No |  | Draft
INT-02 | Integration and batch | OneSource latency under concurrent load | API | S/4, OneSource | Load | 5 | 5 | 3 | 75 | Shared choke point | Tier 1 | Tax call, p95 | 800 ms or less, no timeouts | C2 | Decide |  | Draft
INT-03 | Integration and batch | Endpoint outage and backlog drain | iFlow | BTP IS, JMS | Resilience | 4 | 4 | 4 | 64 |  | Tier 1 | Drain time, loss | 60 min or less, zero loss | C4 | No |  | Draft
INT-04 | Integration and batch | Nightly Control-M critical path | Batch | Control-M, S/4, SOA, DataStage | Batch | 5 | 4 | 4 | 80 |  | Tier 1 | Critical path runtime | Fits window with 20% buffer | C3 | No |  | Draft
INT-05 | Integration and batch | Month-end batch chain | Batch | Control-M, S/4, DataStage | Batch | 5 | 5 | 4 | 100 |  | Tier 1 | Chain runtime | Fits close calendar | C3 | No |  | Draft
INT-06 | Integration and batch | DataStage and SOA jobs alongside online | Mixed | DataStage, SOA, S/4 | Load | 4 | 4 | 3 | 48 |  | Tier 1 | Online p90 during batch | Under 10% degradation | C3 | No |  | Draft
PLT-01 | Platform and mixed | Morning login storm and launchpad | Fiori | Web Dispatcher, IAS, S/4 | Load | 4 | 4 | 3 | 48 |  | Tier 1 | Launchpad load, p90 | 4 s or less | C2 | No |  | Draft
PLT-02 | Platform and mixed | Integrated peak hour, all streams | Mixed | All | Load | 5 | 5 | 5 | 125 |  | Tier 1 | All Tier 1 KPIs together | All met at PRD-equivalent | C2 | No |  | Draft
PLT-03 | Platform and mixed | Eight-hour soak | Mixed | All | Endurance | 4 | 4 | 3 | 48 |  | Tier 1 | Degradation over 8 h | Under 10%, no memory growth | C4 | No |  | Draft
PLT-04 | Platform and mixed | Stress to break point | Mixed | All | Stress | 4 | 4 | 4 | 64 |  | Tier 1 | Knee point | At least 1.5x design peak | C4 | No |  | Draft
PLT-05 | Platform and mixed | Top heavy reports and CDS views | Fiori / GUI | S/4 HANA | Load | 3 | 4 | 4 | 48 |  | Tier 1 | Report response, p90 | 10 s or less | C2 | No |  | Draft
T2-01 | Order to cash | Customer master replication to legacy | iFlow | S/4, BTP IS, legacy | Volume | 2 | 3 | 3 | 18 |  | Tier 3 | Messages per hour | 1.5x peak | Tier 2 | Decide |  | Draft
T2-02 | P2P and VIM | Supplier master sync to Ariba | iFlow | S/4, BTP / CIG, Ariba | Volume | 2 | 3 | 3 | 18 |  | Tier 3 | Messages per hour | 1.5x peak | Tier 2 | No |  | Draft
T2-03 | Central Finance | Exchange rate load | Batch | S/4 | Volume | 1 | 4 | 2 | 8 |  | Tier 3 | Runtime | Fits window | Tier 2 | No |  | Draft
T2-04 | Order to cash | Credit management check | Fiori / GUI | S/4 FIN-FSCM | Volume | 3 | 3 | 3 | 27 |  | Tier 2 | Step response, p90 | 2 s or less | Tier 2 | No |  | Draft
T2-05 | Integration and batch | Error notification and alert iFlows | iFlow | BTP IS | Volume | 3 | 2 | 2 | 12 |  | Tier 3 | Messages per hour | 1.5x peak | Tier 3 | No |  | Draft
| Tier 1 count | 35
| Tier 2 count | 1
| Rule | Score 48 or more, or any override reason (regulatory, financial truth, known pain, revenue, shared choke point) = Tier 1. 20 to 47 = Tier 2. Below 20 = Tier 3.

## Workload Model
Workload model: from daily volume to design load
Yellow cells are inputs. Rows marked EXAMPLE carry illustrative values only; replace every input with mined volumes by Oct 14.
Design headroom (x measured peak hour) |  |  | 1.5 |  | Capacity ratio PRD / pre-prod (from Scaling Model) |  |  |  | 2
ID | Scenario | Volume unit | Avg daily volume | Peak-day multiplier | Peak-hour share of day | Measured peak hour | Design load per hour | Pre-prod step 1 per hour (class B) | Pre-prod step 2 per hour (class C) | Minutes per business transaction incl. think time | Virtual users at design load | Test hours per cycle | Records needed (4 runs) | Source / status
OTC-01 | VSM truck order: configure, price, tax, save | orders | 400 | 1.8 | 15% | 108 | 162 | 81 | 162 | 6 | 17 | 2 | 1296 | EXAMPLE values, replace
OTC-02 | Order change and reconfiguration | [12 empty] | To mine
OTC-03 | Inbound dealer and legacy orders via API | [12 empty] | To mine
OTC-04 | Outbound delivery and goods issue | [12 empty] | To mine
OTC-05 | Billing run with OneSource and output | [12 empty] | To mine
OTC-06 | Invoice outbound to legacy apps | [12 empty] | To mine
OTC-07 | DRC Mexico CFDI to PAC and status back | [12 empty] | To mine
OTC-08 | Cash application and customer payments | [12 empty] | To mine
FIN-01 | Infor LN JE feed at month-end peak | JE lines | 250000 | 4 | 20% | 200000 | 300000 | 150000 | 300000 |  |  | 4 | 4800000 | EXAMPLE values, replace
FIN-02 | AIF error reprocessing at volume | [12 empty] | To mine
FIN-03 | Trial balance match S/4 versus legacy | [12 empty] | To mine
FIN-04 | FX revaluation, depreciation, accruals | [12 empty] | To mine
FIN-05 | Financial statements and analytical apps | [12 empty] | To mine
FIN-06 | GL extracts to legacy and reporting | [12 empty] | To mine
FIN-07 | Period open and close steps | [12 empty] | To mine
P2P-01 | Ariba PO replication to S/4 | [12 empty] | To mine
P2P-02 | Goods receipt and service entry | [12 empty] | To mine
P2P-03 | VIM OCR intake in bulk | invoices | 3000 | 1.5 | 18% | 810 | 1215 | 607.5 | 1215 |  |  | 2 | 9720 | EXAMPLE values, replace
P2P-04 | VIM approval workflow, concurrent approvers | [12 empty] | To mine
P2P-05 | Invoice posting and 3-way match | [12 empty] | To mine
P2P-06 | Payment run and bank file | [12 empty] | To mine
WAR-01 | Pega claim inbound burst | [12 empty] | To mine
WAR-02 | Claim adjudication and credit memo batch | [12 empty] | To mine
WAR-03 | Claim status back to Pega | [12 empty] | To mine
INT-01 | Top 20 iFlow mix at design peak | [12 empty] | To mine
INT-02 | OneSource latency under concurrent load | [12 empty] | To mine
INT-03 | Endpoint outage and backlog drain | [12 empty] | To mine
INT-04 | Nightly Control-M critical path | [12 empty] | To mine
INT-05 | Month-end batch chain | [12 empty] | To mine
INT-06 | DataStage and SOA jobs alongside online | [12 empty] | To mine
PLT-01 | Morning login storm and launchpad | [12 empty] | To mine
PLT-02 | Integrated peak hour, all streams | [12 empty] | To mine
PLT-03 | Eight-hour soak | [12 empty] | To mine
PLT-04 | Stress to break point | [12 empty] | To mine
PLT-05 | Top heavy reports and CDS views | [12 empty] | To mine
Measured peak hour = daily volume x peak-day multiplier x peak-hour share. Use the busiest hour of the busiest day (month-end days 1 to 3, billing cut-off).
Design load = measured peak hour x headroom. Class B (throughput) scenarios run at design / ratio in pre-prod for a PRD-equivalent result; class C (fixed limits) run at full design load.
Virtual users = design load per hour x minutes per transaction / 60 (Little's Law). Leave minutes blank for non-UI flows.
Records needed covers cycle run, retest and two spares at design rate. Size the synthetic data factory from this column.
Note on D3: Program default: 1.5 x measured peak hour. Covers growth and variance. Change only with steering agreement.

## Scaling Model
Scaling model: reading a 50% pre-prod
Enter the ECS configuration for both tiers. If not yet received, the assumed ratio (2.0, from VP IT: pre-prod is half of PRD) is used.
Capacity dimension | PRD | Pre-prod | Ratio PRD / pre-prod | Notes
Application servers (count) |  |  |  | App tier
Application tier vCPU (total) |  |  |  | App tier
Dialog work processes (total) |  |  |  | App tier
Background work processes (total) |  |  |  | Batch
SAPS, application tier |  |  |  | App tier
HANA vCPU |  |  |  | DB tier
HANA memory (GB) |  |  |  | DB tier
Integration Suite tenant (shared or separate?) |  |  |  | Class C: same limit, do not scale
Assumed ratio if ECS config not yet received |  | 2
Non-linearity derate for class B projections |  | 0.85
Capacity ratio used (bottleneck tier) |  | 2 |  | Smallest measured ratio across app and DB tiers, because the bottleneck tier limits throughput.
Metric class | Scales with SAP capacity? | Pre-prod test level | PRD translation rule | Examples
A Response time and single-thread runtime | No (1:1) | Real single-user and peak pacing | PRD forecast = pre-prod result (same CPU generation, same data volume) | VSM configure step, single batch job, one OneSource call
B Throughput and concurrency | Yes, not linearly | 50% of design, then ramp to break | PRD capacity = measured x ratio x derate | Concurrent users, invoices per hour, JE lines per hour
C Fixed shared and external limits | No (same limit) | 100% to 150% of PRD design load | PRD limit = pre-prod limit | BTP tenant, JMS, EOIO, Cloud Connector, number range locks, OneSource, PAC, Pega
Metric (link to scenario ID) | Class | Measured in pre-prod | PRD projection | PRD design target | Headroom | Verdict
OTC-05 Billing run, invoices per hour | B
FIN-01 JE lines posted per hour | B
P2P-03 VIM invoices per hour | B
INT-01 Top 20 iFlow mix, messages per hour | C
INT-02 OneSource call p95 (ms) | A
INT-04 Nightly critical path (min) | A
Headroom = projection / target for throughput metrics, target / projection for time metrics. PASS at 1.2x or better, MARGINAL 1.0 to 1.2x.
Note on C13: From VP IT: pre-prod is sized at half of PRD. Replace with ECS configuration when received.

## KPI Library
KPI library: proposed defaults
Process owners confirm per Tier 1 scenario by Oct 23. Thresholds apply at PRD-equivalent load.
Class | KPI | Proposed threshold | Measured with | Notes
Online, simple | Fiori or GUI dialog step response, 90th percentile | 2 s or less | NeoLoad, STAD | Excludes network latency outside RISE
Online, complex | VSM configure, price and save; VIM approval | 5 s or less | NeoLoad, STAD, SAT | Confirm with OTC and AP process owners
Online, analytical | Analytical Fiori apps and heavy reports, p90 | 10 s or less | NeoLoad, ST03N | Longer runs go to background
Online, system | Average dialog response time, system wide | 1,000 ms or less | ST03N | DB time under 40% of response
Online, launchpad | Fiori launchpad first load, p90 | 4 s or less | NeoLoad | Sensitive to role catalog size
Error rate | Failed transactions in load tests | Under 0.5% | NeoLoad | Functional errors raised as defects
Synchronous API | OneSource tax call, p95 | 800 ms or less, no timeouts | IS monitor, STAD | Validate against OneSource vendor SLA
Synchronous API | Inbound sync API via Integration Suite, p95 | 1.5 s or less end to end | IS monitor
Async interfaces | Sustained throughput versus design peak | 1.5x peak, no backlog growth | IS monitor, JMS
Resilience | Backlog drain after 1-hour endpoint outage | 60 min or less, zero loss | IS monitor, JMS | Run in cycle 4
Central Finance | JE lines posted per hour | 1.5x month-end peak | AIF monitor, DataStage logs
Central Finance | Trial balance S/4 versus legacy | 100% match; report 30 min or less | Recon report | Financial truth, Tier 1 override
DRC Mexico | eDocument create to PAC stamped, p95 | Inside SAT stamping window with margin | eDocument Cockpit | Confirm window with tax
VIM | OCR intake to DP document available | Within agreed minutes at peak | VIM analytics | Known pain point
Batch | Critical path versus batch window | Fits with 20% buffer | Control-M, SM37 | Per window: nightly, month-end
Batch | Single job runtime versus Mock-2 baseline | No more than 1.2x baseline | SM37, Control-M
Platform | App server and HANA CPU, sustained | 70% or less at PRD-equivalent | HANA Cockpit, OS monitor
Platform | HANA memory used versus allocation limit | 80% or less, no OOM | HANA Cockpit
Platform | Free dialog work processes | 20% or more free | SM66, ST03N
Platform | Update queue and enqueue waits | No backlog; enqueue wait near zero | SM13, SM12
Platform | Short dumps during test | No new TIME_OUT or memory dumps | ST22
Endurance | Degradation over 8 hours | Under 10%, no memory growth | NeoLoad, HANA Cockpit | Run in cycle 4

## Interface Inventory
Interface inventory (168 BTP interfaces)
Fill one row per interface. Risk score and suggested tier are calculated. Row EX shows the expected format.
ID | Interface name | Source | Target | Middleware | Pattern | QoS | Frequency | Avg messages per day | Peak messages per hour | Avg payload KB | Max payload KB | Volume 1-5 | Criticality 1-5 | Complexity 1-5 | Risk score | Suggested tier | Test approach | Stub needed? | Owner
EX | Billing invoice outbound to dealer system | S/4HANA | Legacy dealer app | BTP IS | Async | EO | Near real time | 8000 | 1200 | 12 | 250 | 5 | 4 | 3 | 60 | Tier 1 | Tier 1 scenario OTC-06 | Decide | BTP team
INT-001
INT-002
INT-003
INT-004
INT-005
INT-006
INT-007
INT-008
INT-009
INT-010
INT-011
INT-012
INT-013
INT-014
INT-015
INT-016
INT-017
INT-018
INT-019
INT-020
INT-021
INT-022
INT-023
INT-024
INT-025
INT-026
INT-027
INT-028
INT-029
INT-030
INT-031
INT-032
INT-033
INT-034
INT-035
INT-036
INT-037
INT-038
INT-039
INT-040
INT-041
INT-042
INT-043
INT-044
INT-045
INT-046
INT-047
INT-048
INT-049
INT-050
INT-051
INT-052
INT-053
INT-054
INT-055
INT-056
INT-057
INT-058
INT-059
INT-060
INT-061
INT-062
INT-063
INT-064
INT-065
INT-066
INT-067
INT-068
INT-069
INT-070
INT-071
INT-072
INT-073
INT-074
INT-075
INT-076
INT-077
INT-078
INT-079
INT-080
INT-081
INT-082
INT-083
INT-084
INT-085
INT-086
INT-087
INT-088
INT-089
INT-090
INT-091
INT-092
INT-093
INT-094
INT-095
INT-096
INT-097
INT-098
INT-099
INT-100
INT-101
INT-102
INT-103
INT-104
INT-105
INT-106
INT-107
INT-108
INT-109
INT-110
INT-111
INT-112
INT-113
INT-114
INT-115
INT-116
INT-117
INT-118
INT-119
INT-120
INT-121
INT-122
INT-123
INT-124
INT-125
INT-126
INT-127
INT-128
INT-129
INT-130
INT-131
INT-132
INT-133
INT-134
INT-135
INT-136
INT-137
INT-138
INT-139
INT-140
INT-141
INT-142
INT-143
INT-144
INT-145
INT-146
INT-147
INT-148
INT-149
INT-150
INT-151
INT-152
INT-153
INT-154
INT-155
INT-156
INT-157
INT-158
INT-159
INT-160
INT-161
INT-162
INT-163
INT-164
INT-165
INT-166
INT-167
INT-168

## Batch Inventory
Batch inventory (Control-M, SAP, DataStage, SOA)
Critical-path jobs first. Mock-2 runtime is the baseline. Buffer is calculated against the window.
ID | Job or chain | Scheduler | System | Frequency | Window start | Window end | Window minutes | Mock-2 runtime (min) | Pre-prod runtime (min) | Critical path? | Predecessors | Buffer vs window | Verdict | Owner
JOB-001
JOB-002
JOB-003
JOB-004
JOB-005
JOB-006
JOB-007
JOB-008
JOB-009
JOB-010
JOB-011
JOB-012
JOB-013
JOB-014
JOB-015
JOB-016
JOB-017
JOB-018
JOB-019
JOB-020
JOB-021
JOB-022
JOB-023
JOB-024
JOB-025
JOB-026
JOB-027
JOB-028
JOB-029
JOB-030
JOB-031
JOB-032
JOB-033
JOB-034
JOB-035
JOB-036
JOB-037
JOB-038
JOB-039
JOB-040
JOB-041
JOB-042
JOB-043
JOB-044
JOB-045
JOB-046
JOB-047
JOB-048
JOB-049
JOB-050
JOB-051
JOB-052
JOB-053
JOB-054
JOB-055
JOB-056
JOB-057
JOB-058
JOB-059
JOB-060
JOB-061
JOB-062
JOB-063
JOB-064
JOB-065
JOB-066
JOB-067
JOB-068
JOB-069
JOB-070
JOB-071
JOB-072
JOB-073
JOB-074
JOB-075
JOB-076
JOB-077
JOB-078
JOB-079
JOB-080

## Env Readiness
Pre-prod entry checklist (target: all green by Nov 2)
Status drives the readiness count at the bottom.
# | Area | Item | Owner | Due | Status | Evidence / notes
1 | Data | Pre-prod refreshed with Mock-converted data | BAS | 2026-10-30 | Open
2 | Data | Table sizes checked against PRD projection (ACDOCA, VBAK/VBRK, VIM, AIF) | BAS | 2026-10-30 | Open
3 | Data | Synthetic data pools loaded for cycles 1 to 4 plus retest | TDE | 2026-11-02 | Open
4 | Config | Transport and configuration parity with PRD confirmed | BAS | 2026-10-30 | Open
5 | Config | HANA parameters match PRD | BAS | 2026-10-30 | Open
6 | Config | Work process layout and operation modes match PRD | BAS | 2026-10-30 | Open
7 | Config | Number range buffering matches PRD design (FI, billing, eDocument) | BAS | 2026-10-30 | Open
8 | Config | ECS configuration sheet for pre-prod and PRD on file | ECS | 2026-10-16 | Open
9 | Integration | Integration Suite test tenant configured like PRD (JMS, retries, timeouts) | BTP | 2026-10-30 | Open
10 | Integration | Cloud Connector set up like PRD (HA where PRD is HA) | BTP | 2026-10-30 | Open
11 | Integration | Stubs live for endpoints that cannot take load | BTP | 2026-10-30 | Open
12 | Integration | Real endpoints confirmed for scenarios that use them, with agreed load windows | LEG | 2026-10-30 | Open
13 | Integration | DataStage JDBC path to CFIN staging working in pre-prod | DSC | 2026-10-30 | Open
14 | Integration | Control-M connected to pre-prod with replay schedule loaded | DSC | 2026-11-04 | Open
15 | Security | Performance users created from production business roles (no SAP_ALL) | SEC | 2026-10-30 | Open
16 | Security | Communication users with production-like authorizations | SEC | 2026-10-30 | Open
17 | Security | Authentication approach for scripted users agreed (SSO / IAS) | SEC | 2026-10-23 | Open
18 | Tooling | NeoLoad controller and generators reach RISE pre-prod | PET | 2026-10-23 | Open
19 | Tooling | Tier 1 scripts pass single-user validation | PET | 2026-11-02 | Open
20 | Monitoring | ST03N, STAD and SQLM retention extended | BAS | 2026-10-30 | Open
21 | Monitoring | HANA Cockpit, IS monitor and Cloud ALM dashboards ready | BAS | 2026-10-30 | Open
22 | Monitoring | Results template and PRD forecast sheet ready | PPM | 2026-10-30 | Open
23 | Operations | Snapshot before cycle 1 taken; restore tested | ECS | 2026-11-02 | Open
24 | Operations | Pre-prod slot calendar agreed with cutover lead | IPL | 2026-10-09 | Open
25 | Operations | Defect workflow and priority transport lane for performance fixes | PPM | 2026-10-30 | Open
26 | Governance | KPIs signed by process owners | PPM | 2026-10-23 | Open
27 | Governance | Calibration run complete; scaling ratio confirmed | PET | 2026-11-03 | Open
| Done | 0 of 27 items complete

## Risks and Decisions
Risk log and decision log
Score = likelihood x impact (1 to 5 each). 15 or more = High, 8 to 14 = Medium.
ID | Risk | Likelihood | Impact | Score | Rating | Mitigation | Owner | Review date | Status
R01 | Pre-prod contention with cutover rehearsal and UAT | 4 | 5 | 20 | High | Reserve Nov 2 to Dec 4 now; slot nights and weekends; PRD window as contingency | IPL | 2026-10-09 | Open
R02 | Team pulled into SIT2 and Mock-2 firefighting | 5 | 4 | 20 | High | Dedicated external performance team; SMEs ring-fenced at 25% | VP | 2026-10-09 | Open
R03 | Volumes unknown today | 5 | 3 | 15 | High | Mine legacy data in week 1; 1.5x headroom flagged as assumption | TDE | 2026-10-09 | Open
R04 | Legacy and SaaS endpoints cannot take load | 4 | 4 | 16 | High | Stub with mock iFlows; separate low-rate contract test against the real endpoint | LEG | 2026-10-09 | Open
R05 | Fixes arrive too late to retest | 4 | 5 | 20 | High | Shift-left in SIT2; twice-weekly triage; priority transport lane | PPM | 2026-10-09 | Open
R06 | Pre-prod data not production-shaped | 3 | 4 | 12 | Medium | Refresh from Mock load; check table sizes against PRD projection | BAS | 2026-10-09 | Open
R07 | Scaling misread leads to false confidence | 3 | 4 | 12 | Medium | Three-class model, ECS config sheet, calibration run, class C at full load | IPL | 2026-10-09 | Open
R08 | SSO blocks scripted performance users | 3 | 3 | 9 | Medium | Agree authentication approach for performance users in week 2 | SEC | 2026-10-09 | Open
R09 | Performance defect cannot be fixed by Dec 15 | 3 | 5 | 15 | High | Pre-agreed workarounds (scheduling, parallelization) and hypercare alerts | IPL | 2026-10-09 | Open
R10 | OneSource or PAC vendor limits unknown | 3 | 4 | 12 | Medium | Request vendor rate limits and SLAs in week 1; design retries and timeouts | BTP | 2026-10-09 | Open
R11 | Number range serialization on Mexico documents | 2 | 5 | 10 | Medium | Verify buffering design in SIT2; test billing and DRC at full design load | BAS | 2026-10-09 | Open
Decision log
ID | Decision | Options |  |  |  | Recommendation | Decider | Needed by | Status
D01 | Stand up performance assurance as a funded workstream | Fund now / absorb in existing teams / defer |  |  |  | Fund now with a named International owner and PwC CR | VP | 2026-10-09 | Pending
D02 | Specialist performance team | External partner / offshore / internal only |  |  |  | External specialists (about 6) so SIT2 and UAT are not drained | VP | 2026-10-09 | Pending
D03 | Pre-prod reservation Nov 2 to Dec 4 | Exclusive / time-sliced with cutover / none |  |  |  | Time-sliced with agreed slots, nights and weekends | VP | 2026-10-09 | Pending
D04 | Endpoint strategy per legacy and SaaS system | Real instance / stub / hybrid |  |  |  | Hybrid: stub for load, real endpoint for low-rate contract test | IPL | 2026-10-16 | Pending
D05 | Performance gate as input to tech go-live | Formal gate / advisory |  |  |  | Formal gate on Dec 4 | VP | 2026-10-09 | Pending
D06 | PRD window before cutover (option C) | Use / do not use |  |  |  | Hold as contingency; decide by Nov 20 based on pre-prod results | VP | 2026-11-20 | Pending
D07 | Load tool | Keep NeoLoad / switch |  |  |  | Keep NeoLoad for this go-live; revisit after hypercare | IPL | 2026-10-09 | Pending

## Team
Team, FTE and duration
FTE-weeks drive the change request. Name each person once confirmed.
Role | Code | Source | FTE | Start | End | Weeks | FTE-weeks | Named person
International performance test lead (owner) | IPL | International | 1 | 2026-10-05 | 2027-02-12 | 18.7 | 18.7
PwC performance test manager | PPM | PwC | 1 | 2026-10-05 | 2026-12-23 | 11.4 | 11.4
Performance engineers (NeoLoad scripting and execution) | PET | Specialist partner or offshore | 4 | 2026-10-12 | 2026-12-23 | 10.4 | 41.6
Test data engineer (synthetic data factory) | TDE | PwC or partner | 1 | 2026-10-07 | 2026-12-04 | 8.4 | 8.4
Basis and HANA performance engineer | BAS | International or PwC, plus ECS | 1 | 2026-10-05 | 2027-01-15 | 14.7 | 14.7
ABAP performance developers (fix team) | ABAP | PwC | 2 | 2026-10-12 | 2026-12-11 | 8.7 | 17.4
BTP Integration Suite engineer | BTP | Integration team | 1 | 2026-10-12 | 2026-12-23 | 10.4 | 10.4
DataStage and Control-M engineer | DSC | International | 0.5 | 2026-10-12 | 2026-12-04 | 7.7 | 3.85
Functional SMEs: OTC/VSM, CFIN, P2P/VIM, warranty, tax (5 x 25%) | SME | Ring-fenced from program | 1.25 | 2026-10-12 | 2026-12-04 | 7.7 | 9.625
Security and GRC | SEC | International | 0.25 | 2026-10-19 | 2026-11-06 | 2.7 | 0.675
Total |  |  | 13 |  |  |  | 136.75
Legacy and SaaS owners (Infor LN, Pega, OneSource, Mexico PAC, OpenText, Ariba) are named contacts, not FTE. SAP ECS and SAP Enterprise Support engage through tickets and service sessions.